Overview of the TPDP work proramme

(Prepared by the IPPC Secretariat)

1. Background

This paper presents an overview of the current subjects in the work programme of the Technical Panel on Diagnostic Protocols (TPDP).

This document presents two attachments:

- In attachment 1 there is the update on activities of the TPDP from May 2019 to June 2020 that was presented to the Standards Committee (SC) via eDecision due to the cancellation of the the SC May 2020.

- In attachment 2 there is the approved TPDP Specification 01 (also available on the website at: https://www.ippc.int/en/publications/1297/).

The Standard Setting Unit (SSU) of the IPPC Secretariat provides support to the work of the TPDP and to the work of the SC. The current SSU staff are presented in the linked chart.

2. Subjects in the TPDP work programme

Currently there are 19 subjects in the TPDP work programme, under various stages of development, to be developed as annexes to ISPM 27 (Diagnostic protocols for regulated pests). Note that the term “subject” refers to specific diagnostic protocols, as listed below. The full List of topics for IPPC standards is available at https://www.ippc.int/en/core-activities/standards-setting/list-topics-ippc-standards/list.

- Genus Ceratitis (2016-001), priority 1 (under development)

- Striga spp. (2008-009), priority 1 (under development )

- Tephritidae: Identification of immature stages of fruit flies of economic importance by molecular techniques (2006-028), priority 1 (“pending status”)

- Pyricularia oryzae (syn. Magnaporthe oryzae) on Triticum (2019-002), priority 1 (under development)

- Microcyclus ulei (2019-003), priority 1 (call for authors)

- Puccinia graminis f. sp. tritici UG 99 (2019-004), priority 1 (under development)

- Mononychelus tanajoa (2018-006), priority 1 (under development)

- Citrus leprosis virus (2018-025), priority 1 (under development)

- Psyllid vectors of Candidatus Liberibacter solanacearum (2018-030), priority 1 (under development)

- Begomoviruses transmitted by Bemisia tabaci (2006-023), priority 2 (under development)

- Candidatus Liberibacter spp. on Citrus spp. (2004-010), priority 2 (under development)

- Amaranthus palmeri (2019-006), priority 2 (“new”)

- Solanum rostratum (2019-007), priority 2 (“new”)

- Pospiviroid species (except Potato spindle tuber viroid (DP 7)) (2018-031), priority 2 (“new”*)

- Acidovorax avenae subsp. citrulli (2018-032), priority 2 (“new”*)

- Moniliophthora roreri (2019-005), priority 3 (“new”)

- Meloidogyne mali (2018-019), priority 3 (“new”*)

- Cronartium comandrae (2018-015), priority 4 (“new”*)

- Revision of DP 5 (Phyllosticta citricarpa (McAlpine)) Aa, (2019-011) No priority (“new”*)

3. Adopted diagnostic protcols annexes to ISPM 27

Currently there are 29 adopted  diagnostic protcols annexes to ISPM 27. The adopted DPs are available at https://www.ippc.int/en/core-activities/standards-setting/ispms/.

Recommendations to the TPDP:.

- The TPDP is invited to:

note the current subjects in the TPDP work programme;

assign/reassign discipline leads and referees to each subject;

review the adopted diagnostic protcols and, if appropriate, identify the need for revising DPs and submit revisions to the SC, with a justification.

consider potential implementation of standards by contracting parties and identify potential operational and technical implementation issues, when coordinating the development of DPs. Provide information and possible recommendations on these issues to the SC.

- ATTACHMENT 1

update to the Standards committee(SC) on activities of the Technical Panel on Diagnostic Protocols (TPDP) FROM MAY 2019 TO june 2020

(Prepared by the IPPC Secretariat with input from the TPDP Steward)

1. Background

More information about the Technical Panel on Diagnostic Protocols (TPDP) can be found at https://www.ippc.int/en/core-activities/standards-setting/expert-drafting-groups/technical-panels/technical-panel-diagnostic-protocols/.

The Stewards for the Technical Panel on Diagnostic Protocols (TPDP) are:

Ms Janyani Nimanthika WATHUKARAGE (Steward)

Mr Álvaro SEPULVEDA LUQUE (Assistant Steward)

The IPPC Secretariat support for the TPDP are:

Ms Adriana G. MOREIRA (lead)

Ms Aoife CASSIN (support)

- The TPDP membership and contact information can be found on the International Phytosanitary Portal (IPP). Table 1 shows a simplified version of the TPDP membership as of June 2020.

Table 1. TPDP membership (as of June 2020) and expertise of its members.

| Participant role | Name (country) | Expertise | Term expires |
| --- | --- | --- | --- |
| Steward | Ms Janyani Nimanthika WATHUKARAGE (Sri Lanka) |  |  |
| Assistant steward | Mr Álvaro SEPULVEDA LUQUE (Chile) |  |  |
| Member | Mr Robert TAYLOR (New Zealand) | Bacteriology (and backup for mycology) | May 2021 (2nd term) |
| Member | Ms Liping YIN (China) | Botany | April 2023 (3rd term) |
| Member | Mr Norman B. BARR (United States) | Entomology | July 2022 (2nd term) |
| Member | Ms Juliet GOLDSMITH (Jamaica /CAHFSA) | Entomology | November 2024 (2nd term) |
| Member | Ms Géraldine ANTHOINE (France) | Nematology | April 2024 (3rd term) |
| Member | Mr Brendan RODONI (Australia) | Virology (and back up for bacteriology) | July 2022 (2nd term) |
| Member | Ms Vessela Assenova MAVRODIEVA (United States) | Virology | March 2025 (1st term) |
| Member | Ms Julie PATTEMORE (Australia) | Mycology | March 2025 (1st term) |
| Member | Ms Yazmin Rivera RIVERA (United States) | Mycology | March 2025 (1st term) |

- As of March 2020, the TPDP welcomed new members Ms Vessela Assenova MAVRODIEVA (Virology), Ms Julie PATTEMORE (Mycology) and Ms Yazmin RIVERA (Mycology).

- The IPPC Secretariat issued a new call for a Botanist to join the TPDP and this call will close on 1 August 2020.

2. TPDP work programme

2.1 Update on work programme

The TPDP work programme currently comprises of 19 diagnostic protocols (DPs) under six disciplines in various stages of development.

On 29 August 2019 the IPPC Secretariat opened a call for DP authors for the following high priority diagnostic protocols on the work programme of the TPDP. The call closed on 1 November 2019 and the TPDP selected drafting groups for four of the six topics, via e-Decisions:

Citrus leprosis virus (2018-025) (drafting group initiated)

Psyllid vectors of Candidatus Liberibacter solanacearum (2018-030) (drafting group initiated)

Puccinia graminis f. sp. tritici UG 99 (2019-004) (drafting group initiated)

Pyricularia oryzae (syn. Magnaporthe oryzae) on Triticum spp. (2019-010) (drafting group initiated)

Microcyclus ulei (2019-003) (no appropriate expert nominations submitted)

Mononychelus tanajoa (2018-006) (no appropriate expert nominations submitted)

A new call was issued in May 2020 for the remaining diagnostic protocols, however only one expert CV was received for the drafting of Mononychelus tanajoa (2018-006) and no submissions were received for Microcyclus ulei (2019-003) and therefore the drafting cannot be initiated for both of these topics.

The planned DP Notification Period for Striga spp. (2008-009) in July 2020 will not go ahead as planned this year as there are still technical questions from the country consultation that the Discipline Lead and drafting group need to address.

- Figure 1. Number of diagnostic protocols per discipline currently in the IPPC TPDP work programme.

  - Tentative work plan for 2020 - 2021

The TPDP will not have the opportunity to meet face-to-face in 2020 but virtual meetings may be possible, if deemed necessary by the Panel. The IPPC Secretariat is providing them with regular updates.

The draft DP on Candidatus Liberibacter spp. on Citrus spp. (2004-010) was due to go for first consultation in 2020 but the drafting group and discipline lead were not responsive on the established timeframe.

The TPDP will continue to work on the draft DPs on its work programme, none of which is currently expected to be finalized and adopted in 2020. However, it is expected that many of them will progress through the standard setting process. There are expert consultations tentatively planned to take place in the second half of 2020 for at least two draft diagnostic protocols on the work programme:

Genus Ceratitis (2016-001) and

Begomoviruses transmitted by Bemisia tabaci (2006-023)

In addition, the new drafting groups for the aforementioned subjects in the work programme will send a first draft to the Secretariat by 01 December 2020, if technically feasible.

The DP Notification Period for Striga spp. is now tentatively planned for January 2021 pending the resolution of technical questions raised in the 2019 consultation period.

3. TPDP recommendations to the SC

The TPDP discussed recommendations to the SC as usual at their annual meeting. The last meeting took place in August 2019 in Melbourne, Australia. The IPPC Secretariat advises SC members to read the meeting report carefully prior to responding to these recommendations. The list of recommendations are compiled below as listed in the report. Some of the recommendations points were adjusted or removed, as later discussions by the TPDP and developments of events.

Please note that some recommendations are being addressed in other papers to the SC (e.g.  “Possible ways to shorten the length of time to develop diagnostic protocols, particularly in the case of emerging pests” that was due to be presented to the SC in November 2019 but it was deferred and will be presented via eDecision in June 2020).

The TPDP recommendations are grouped based on the IPPC Strategic Framework 2020-2030.

Regarding commodity- and pathway-specific ISPMs, the SC is invited to:

- note that the scope of DPs should be clearly defined in the framework of commodity and pathway standards

note that the development of DPs should still be based on pest taxonomy rather than commodity, otherwise the scope of concerned pests would be considerable and very difficult to achieve

note that the TPDP considered it too early to provide detailed feedback

note that the TPDP considered that “inspection standards” may be needed and possible in the future, and that TPDP could help in that prospect, provided that the main pests of concern have been defined previously

note that the TPDP considered that High-Throughput Sequencing (HTS) technologies are promising, but that it is premature to consider them for DPs since development of such technologies is very fast, and also taking into consideration the need for laboratory capacity in the majority of countries

note that the TPDP strongly expressed its willingness to be involved at the beginning of the development of such standards, to avoid duplications, to understand potential gaps and build stronger relationships with the SC and the new technical panel.

Regarding diagnostic laboratory networking, the SC is invited to:

agree that the TPDP gather different sources of information (manual, guides, videos) from different regions, in order to identify gaps in the existing manual of diagnostic protocols

agree that, in collaboration with the SC and IC, the TPDP develops or revise manuals and guidelines when needed (e.g. the existing manual of diagnostic protocols, or guidelines on proficiency tests)

consider amending Specification TP 1 in order to allow the TPDP to participate to the activities described above

note that the TPDP recommended that a CPM recommendation on “Facilitating shipment and transport of reference material and specimens, to support diagnostic activities for regulated pests” be developed, and asked Mr Brendan RODONI and Ms Juliet GOLSMITH, supported by Ms Françoise PETTER to draft a justification for that purpose to be discussed during the next TPDP meeting

note that TPDP is willing to take the lead in organizing the first international workshop on diagnostic laboratories in 2021, and asked Mr Norman BARR, supported by Mr Brendan RODONI, to draft a detailed proposal (justification, programme, resource mobilization) to be discussed during the next TPDP meeting.

Regarding pest outbreak alert and response systems, the SC is invited to:

note that diagnostic networking could improve the support already given to these systems by the current activities of the TPDP, and pass this information to the IC.

Regarding the emerging and fast-spreading pests, the SC is invited to:

note that developing a DP implies following an IPPC process, which makes difficult to issue the DP in time

note that in case of an emergency, consideration could be given to making available to contracting parties information on other type of diagnostics sourced from NPPOs, RPPOs or other bodies, but gathering the data would require a strong international network and further resources allocated to the IPPC Secretariat

note that the TPDP noted that the process to include new topics to the work programme could be speeded up, with better communication between the several bodies involved and making use of the TPDP as part of it.

Regarding analysis of draft diagnostic protocols added to the work programme as requested by the SC, the SC is invited to:

agree that the draft DP for Psyllid vectors of ‘Candidatus Liberibacter solanacearum’ (2018-030) be developed at species level

agree that it is feasible to develop a DP for Pospiviroid species (except Potato spindle tuber viroid (DP 7)) (2018-031) and that the DP should cover plants and seeds

agree that it is feasible to develop a DP for Acidovorax avenae subsp. citrulli (2018-032) and to note that it may be beneficial to liaise with the International Seed Testing Association (ISTA), the International Seed Federation (ISF) and the International Seed Health Initiative (ISHI)

consider changing the priority from 2 to 1 as Acidovorax avenae subsp. citrulli has a high economic impact, especially for developing countries, and is highly seed-transmitted

agree that the draft for Meloidogyne mali (2018-019) is at species level, and to note that if there is a need to develop at genus level, additional guidance from the SC should be given on which species should be focused on, as for other DPs (e.g. Anguina)

agree that it is feasible to develop a DP for Cronartium comandrae (2018-015), and to note that during the development the scope may change to include other species.

Regarding the International Year for Plant Health, the SC is invited to:

agree that the TPDP should participate at the workshop on plant health diagnostics foreseen in the draft programme of the International Plant Health conference being organized within the framework of the 2020 International Year for Plant Health (IYPH) from 5 to 8 October 2020, and should gather information from different sources for this purpose.

Attachment 2

SPECIFICATION

TP 1
Technical Panel on Diagnostic Protocols

(2012)

Title

Technical Panel on Diagnostic Protocols (2004-002).

Reason for the technical panel

Proper pest detection and pest identification are crucial for the appropriate application of phytosanitary measures. In particular, contracting parties need proper diagnostic procedures for determination of pest status and pest reporting (ISPM 8:1998, Determination of pest status in an area; ISPM 17:2002, Pest reporting), and the diagnosis of pests in imported consignments (ISPM 13:2001, Guidelines for the notification of non-compliance and emergency action). ICPM-6 (2004) recognized that there was a need for international diagnostic protocols within the framework of the IPPC and approved the formation of a technical panel on diagnostic protocols.

Scope and purpose

The Technical Panel on Diagnostic Protocols (TPDP) develops diagnostic protocols (DPs) within the framework of ISPM 27:2006 and develops guidance on related issues.

Tasks

The TPDP should undertake the following:

- Identify the need for DPs to be developed based on the guidance paper on “Criteria for the prioritisation of diagnostic protocols” (TPDP, July 2010), including considering suggestions for new DPs (i.e. put forward by national plant protection organizations (NPPOs), regional plant protection organizations, expert working groups (EWGs) or other technical panels), and submit subjects for new protocols to the Standards Committee (SC).

Identify specialists for the development or revision of a DP (authors, editorial team, experts to be consulted) and if applicable provide advice to the SC accordingly.

Produce or supervise the production or revision of DPs.

Submit draft DPs to the SC.

Review adopted DPs regularly, identify the need for revising DPs and submit revisions to the SC.

Consider aspects of quality assurance related to the development of DPs and their application. Where necessary establish general guidance on the criteria for methods to be included in DPs (e.g. validation).

Provide specific advice to the SC and other technical panels or EWGs on issues related to the correct nomenclature of pests.

Under the direction of the SC, consider other topics related to diagnosis of regulated pests.

Review appropriate draft International Organization for Standardization (ISO) standards under the Subcommittee “horizontal methods for molecular biomarker analysis” (TC34/SC16), identify standards of significance for the IPPC, and seek guidance from the SC on whether to provide comments to ISO.

In drafting an ISPM, consider whether the new standard could affect in a specific way (positively or negatively) the protection of biodiversity and the environment, and if so, the impact should be identified, addressed and clarified in the draft standard.

Consider implementation of standards by contracting parties and identify potential operational and technical implementation issues. Provide information and possible recommendations on these issues to the SC.

Provision of resources

Funding for the meeting is provided by the IPPC Secretariat (FAO). As recommended by ICPM-2 (1999), whenever possible, those participating in standard setting activities voluntarily fund their travel and subsistence to attend meetings. Participants may request financial assistance, with the understanding that resources are limited and the priority for financial assistance is given to developing country participants.

Collaborator

To be determined.

Steward

Please refer to the list of topics for IPPC standards posted on the IPP (see https://www.ippc.int/index.php?id=207776).

Expertise

Members of this panel should primarily have diagnostic expertise (where appropriate taxonomic) with at least one member representing each discipline: entomology, acarology, nematology, mycology, bacteriology, virology (including viroids and phytoplasma) and botany. Between them, participants should have practical expertise in the use of morphological and molecular/biochemical diagnostic techniques, in quality assurance and in phytosanitary procedures.

Participants

Details of TPDP membership may be found on the IPP:

https://www.ippc.int/index.php?id=tpdp&no_cache=1&L=0. Panel members are selected by the SC for a 5-year term. The SC reviews the composition of the panel on a regular basis. The SC may renew individual memberships for additional terms.

References

The IPPC, relevant ISPMs and other national, regional and international standards and agreements as may be applicable to the tasks, and discussion papers submitted in relation to this work.

- European and Mediterranean Plant Protection Organization (EPPO) DPs

- International Seed Testing Association.

Discussion papers

Participants and interested parties are encouraged to submit discussion papers to the IPPC Secretariat (ippc@fao.org) for consideration by the technical panel.

Publication history

This is not an official part of the specification

2004-04 ICPM-6 added topic Diagnostic protocols for specific pests (2004-002)

2004-04 SC approved specification

2004-11 SC revised and approved specification (rev. 1)

2007-05 SC revised and approved specification (rev. 2)

2011-05 SC revised and approved specification (rev. 3)

2011-11 reformatted

2011-12 applied consistency in line with the decision made by SC May 2009

2012-04 SC added task 9 and approved specification (rev. 4)

2012-11 SC replaced task regarding implementation issues

2013-03 Secretariat corrected publication history

Specification TP 1. 2012. Technical Panel on Diagnostic Protocols. Rome, IPPC, FAO.

Publication history last updated: January 2013

TPDP main page on IPP: https://www.ippc.int/en/core-activities/standards-setting/expert-drafting-groups/technical-panels/technical-panel-diagnostic-protocols/

https://www.ippc.int/en/core-activities/standards-setting/calls-experts/

See List of topics for IPPC standards: https://www.ippc.int/en/core-activities/standards-setting/list-topics-ippc-standards/list

TPDP 2019 meeting report: https://www.ippc.int/en/publications/88295/

These dates were correct at the time of the meeting however due to the Covid-19 pandemic the meeting has been moved to 2021. This should not affect the decision of the SC on this point.