Tentative technical panel on diagnostic protocols (TPDP) work plan 2020-2021

(Prepared by the IPPC Secretariat)

1. Background

This paper presents a tentative work plan 2020-2021 for the Technical Panel on Diagnostic Protocols (TPDP). It should be read in conjuction with the document under agenda item 4.2 on the TPDP work programme, the List of topics for IPPC standards (LOT) and the action points list from the last TPDP meeting in 2020-08 Melbourne.

In attachment 1 of this document there is a tentative timeline for the draft diagnostic protocols (DPs) in the work programme in which there is a DP drafting group (mainly subjects with priority 1 and from the last IPPC call for topics in 2018).

In attachment 2 of this document there is a figure of the flow of a DP in the IPPC standard setting process, as presented in the brochure “An Introduction for Authors of IPPC Diagnostic Protocols”.

2. Draft DPs for consultation period in 2021 (01 July)

From the current 19 subjects in the TPDP work programme, there are 9 under development that have the potential to be submitted to the next IPPC consultation period in July 2021.

The following subjects (i.e. diagnostic protocols) in the work programme have the potential to be presented to the IPPC contracting parties at the next consultation period in July 2021. To note that, for the “new” draft DPs they still need to undergo expert consultation prior to be discussed by the TPDP.

- Genus Ceratitis (2016-001), priority 1

- Pyricularia oryzae (syn. Magnaporthe oryzae) on Triticum (2019-002), priority 1

- Puccinia graminis f. sp. tritici UG 99 (2019-004), priority 1

- Mononychelus tanajoa (2018-006), priority 1

- Citrus leprosis virus (2018-025), priority 1

- Psyllid vectors of Candidatus Liberibacter solanacearum (2018-030), priority 1

- Revision of DP 5 (Phyllosticta citricarpa (McAlpine)) Aa, (2019-011), no priority assigned

- Begomoviruses transmitted by Bemisia tabaci (2006-023), priority 2: presented to TPDP however, it did not went to expert consultation

- Candidatus Liberibacter spp. on Citrus spp. (2004-010), priority 2: presented to TPDP (and expert consultation). New information is available about the pest and diagnosis

It is to point out that for the draft DP for Microcyclus ulei (2019-003) - priority 1, the IPPC Secretariat opened two calls for authors but not sufficient nominations were received. Also, contact was made with some concerned countries to try to identify experts, however without success.

Scope of draft DPs. For the draft DP with pending status Tephritidae: Identification of immature stages of fruit flies of economic importance by molecular techniques (2006-028), priority 1, a revised proposal to adjust the scope was made by the discipline lead and it is planned to be discussed at next virtual meeting or via TPDP e-decision forum with the aim to be approved for presentation to the IPPC Standards Committee (SC).

Other note about the scope is for the draft DP for Puccinia graminis f. sp. tritici UG 99 (2019-004). The Department of Plant Protection and Production of FAO suggested to expand the scope to various races, not only Ug99 because there have been numerous new races / strains, and therefore the use of an international standard only for Ug99 would be very limited.

For the draft DP for Citrus leprosis virus (2018-025), it was also pointed out by a TPDP member the need to look into the scope, hence there are “two major types” of this virus: cytoplasmic Leprosis virus complex caused by Cilevirus and nuclear leprosis virus complex caused by Dichorhavirus. Thus, the scope should be well described in the diagnostic protocol.

Requests for revisions of adopted DPs. In the TPDP Specification TP 1 task 5 it mentions that the TPDP should be reviewing adopted DPs regularly and identify the need for revising DPs. It is important to recall that the inclusion of new requests of draft DPs into the TPDP work programme it needs to be agreed by the SC, as the SC has the oversight for the technical panels work.

To bear in mind that depending on the type of revisions the draft DP may undergo the full cycle of the IPPC standard setting process. The SC May 2013 defined the criteria for DP revision as a technical revision that should be done by the TPDP as follows:

- Editorials

- Taxonomic changes that do not affect the identification of the pest (and do not change the diagnosis)

- Addition of validation data relating to the methods already on the DP

- Improved specification of method, e.g. additional descriptors such as amount of DNA

- Pest information

- New information on distribution of official notification

- New host that may help the diagnosis reported in an official notification and does not affect the diagnosis.

Other revisions different from the above, would need to be subject to the normal DP adoption process (i.e. consultations, redrafting, SC approval, notification period, SC adoption).

As a follow up from the last meeting of the TPDP in 2019 there was the possibility for revision of DP 21: ‘Candidatus Liberibacter solanacearum’, DP 25: Xylella fastidiosa and DP 27: Ips spp., therefore something to reconsider

The IPPC Secretariat received some requests for revisions for some adopted DPs (below). The plan is to discuss these proposals at next virtual meeting or via TPDP e-decision forum with the aim to be approved for presentation to the IPPC SC.

DP 03: Trogoderma granarium Everts (adopted in 2012). The request was submitted by one of the authors of the original drafting group. The objective is to include a qPCR test to differentiate T. granarium Everts and T. variabile Ballion (Coleoptera: Dermestidae) from the rest of Dermestidae beetles.

DP09 Genus Anastrepha Schiner (adopted in 2015). The request came from the discipline lead and TPDP member of the orginal drafting group. The objective is to update with additional molecular methods to provide new ability to confirm species status of immature life stages or adults that are insufficiently preserved for morphological examination of adults.

3. Draft DPs for approval for DP Notification Period - 01 July 2021

The draft DP for Striga spp. (2008-009) is to be presented to the DP notification period, i.e. adoption by the Standards Committee (SC) on behalf of the Commission on Phytosanitary Measures (CPM).

This draft went for consultation period in 2019 and received 242 comments (2019: Striga draft DP and the compiled comments). The DP drafting group addressed the marjority of the comments and it was forwarded to the referee which provided further insights and revisions. However, there are still some technical comments that need to be addressed and decisions to be made to be presented to the TPDP.

4. Other draft DPs

For the other draft DPs in the work programme there is a need to open call for authors to compose the DP drafting groups. It is important to point out that the other draft DPs are priority 2, 3 or 4, however it is known that if there are available experts to draft the DPs, these coul be advanced in the process. Advice is being sought from the TPDP on how to proceed with the calls, noting that in 2021 there will be another IPPC call for topics: standards and implementation, and new proposals for DPs may be submitted.

The following are the DPs in the TPDP work programme:

- Amaranthus palmeri (2019-006), priority 2

- Solanum rostratum (2019-007), priority 2

- Pospiviroid species (except Potato spindle tuber viroid (DP 7)) (2018-031), priority 2

- Acidovorax avenae subsp. citrulli (2018-032), priority 2

- Moniliophthora roreri (2019-005), priority 3

- Meloidogyne mali (2018-019), priority 3

- Cronartium comandrae (2018-015), priority 4

5. Other documents

Annually, the TPDP reviews / revises the following documets that are linked with the task 6 of the TPDP Specification TP 01, on aspects of quality assurance related to the development of DPs and their application:

- “Quality assurance issues associated with diagnostic protocols for regulated pests”

- “Best practices for sequencing: Using DNA sequences to diagnose a pest”

- “Interpretation of results from LAMP tests”

Also, the TPDP reviews / revises the Instruction to authors, its working procedures and the checklists for discipline leads and referees.

Due to the current situation of the cancelation of the face to face meeting, it is suggested that for the documents TPDP e-decisions / foruns can be open. And that for the Instrauction to authors, working procedures and checklists, if any TPDP member identifies a need for revision at any time, it can be informed to the Secretariat.

6. IPPC Strategic Framework 2020-2030

In the last TPDP meeting (2019) the TPDP had productive and positive discussions on the impact of the new IPPC Strategic Framework 2020-2030 in its work. Some recomnedations were submitted to the SC for their comments and decisions, as would entail an “expansion” in the TPDP scope of working procedures. More information is available in document under agenda item 5.1. The SC will have a meeting in 23 September 2020, and the recommendations from the TPDP will be further discussed, specially regarding the role and innitiatives proposed for the strategic development agenda on “Laboratories networking”.

Moreover, the TPDP recommended that a CPM recommendation on “Facilitating shipment and transport of reference material and specimens, to support diagnostic activities for regulated pests” be developed, noting that a justification needs to be prepared to be presented to the SC.

Recommendations to the TPDP:

- The TPDP is invited to:

note the current subjects in the TPDP work programme;

assign/reassign discipline leads and referees to each subject;

discuss and assign the 2020-2021 work plan proposals (Plan A or Plan B) for the current subjects in the TPDP work programme to reach first consultation in July 2021;

note the 2020-2021 work plan for Striga spp. (2008-009) to reach DP Notification Period in July 2021;

review the adopted diagnostic protcols and, if appropriate, identify the need for revising DPs and submit revisions to the SC, with a justification;

discuss and provide recommendation to the Secretariat on call for author for the reminaing DPs in the work porgramme;

discuss and provide recommendation on how to proceed with the documents on quality assurance and the possible CPM Recommendation;

agree on tentative dates for next virtual meetings.

- ATTACHMENT 1

Tentative TPDP work plan 2020-2021

Timeline for draft diagnostic protocols

(Prepared by the IPPC Secretariat)

- 1. Objective: Draft diagnostic protocols (DPs) approved for consultation period in 2021 (01 July)

Main steps:

- Expert consultation on draft DPs

- TPDP discussion and approval

- IPPC Editor

- Standards Committee (SC) discussion and approval

- Plan A: Expert consultation 05 Dec 2020 – 15 January 2021

- Plan B: Expert consultation 15 January – 15 February 2021

- 2. Objective: Draft DPs approved for DP Notification Period - 01 July 2021

Draft DP in the work programme: Striga spp. (2008-009)

- Main steps:

- Finalize responses to comments and revise draft DPs

- TPDP discussion and approval

- Editor

- Standards Committee (SC) discussion and approval

Work flow to develop an IPPC diagnostic protocol

(see the brochure “An Introduction for Authors of IPPC Diagnostic Protocols”)

IPPC expert consultation on draft diagnostic protocols: https://www.ippc.int/core-activities/expert-consultation-draft-diagnostic-protocols/

More information on the IPPC Procedure Manual for Standard Setting: https://www.ippc.int/en/publications/85024/

IPPC Strategic Framework 2020-2030 as presented to the Commission on Phytosanitary Measures (CPM-15,to take place in 2021). Slight adjustments will be made. Link: https://www.ippc.int/en/publications/88125/