Communication and advocacy plan for the Outcome 3 of the FAO Global Action for Fall Armyworm Control

Risk of FAW introduction and spread to new areas reduced

|  | Communications and Advocacy Plan Second semester 2020 – First semester 2021 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ACTIVITIES |  | 2020 |  |  |  |  | 2021 |  |  |  |  | 2022 |  |  |  |
|  |  | 1Q | 2Q | 3Q | 4Q | 1Q |  | 2Q | 3Q | 4Q | 1Q |  | 2Q | 3Q | 4Q |
| - Produce, distribute and promote guidelines on FAW prevention |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 1.1 IPPC guidelines on FAW prevention are developed and published online |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 1.2 Produce a short video for IPPC social media to launch and promote the publication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 1.3 Prepare social media visuals with key messages and highlights from the publication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 1.4 Organize and promote the launch event |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Finalize the FAW webpage on the IPPC website |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 2.1 A mock-up is ready to be presented to the Technical Working Group for comments and suggestions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 2.2 The FAW page on the IPP is revamped and accessible from the IPP homepage |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Develop digital campaigns |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 3.1 Produce and distribute short videos on FAW and the role of the IPPC community within the FAO Global Action to be shared on IPPC social media and the IPPC website |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 3.2 Collect inspiring stories from the field to be featured on the IPPC FAW webpage and shared with NSP for inclusion in the FAW newsletter |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 3.3 Prepare a simple toolkit on FAW identification and preparedness, including factsheets, social media visuals, and videos |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 3.4 Produce infographics on FAW prevention and preparedness to be posted on the IPPC website and social media |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Organize and promote IPPC/FAW events |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 4.1 Prepare a draft programme of events to be circulated internally for planning purposes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 4.2 Include relevant events, meeting documents, and materials on the FAW calendars |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 4.3 Prepare and post relevant headline news on the IPPC website |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Develop an IPPC 2021 publications plan on FAW |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Publications plan to be discussed, drafted and presented to the IST for inclusion in the 2021 IPPC publications plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Preparing training materials to be distributed to relevant stakeholders (possible including a brochure) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |