Minutes of the virtual meeting of the Working Group to develop e-Learning materials on phytosanitary export certification system

Thursday 15 April 2021 20h00-22h30 (Rome time)

Opening and meeting arrangements

The IPPC Secretariat (hereinafter: “The Secretariat”) welcomed the participants. The Working Group (WG) elected M Damian CLARKE as Chairperson and M Avtar VIRK as rapporteur.

The agenda of the meeting was adopted and is presented in Appendix 1.

The list of participants is presented in Appendix 2.

The Secretariat noted that, at the date of the meeting, 7 activities have been drafted by the Secretariat and experts (A, B, C, D, E, F, and G) and posted on the dedicated Dropbox, this represents all activities foreseen for modules 1 and 2, which are dedicated to private stakeholders (appendix 3).

The Secretariat presented a new version of the draft activity A, which took in account the comments made by the expert during the previous meeting held on 25 March 2021. The experts provided further comments, and these comments having been discussed, agreed on a final version, ready to be transmitted to COLEACP.

The Secretariat presented a new version of the draft activity B, which took in account the comments made by the expert during the previous meeting held on 25 March 2021. The experts provided further comments, and these comments having been discussed, agreed on a final version, ready to be transmitted to COLEACP.

The Secretariat presented a new version of the draft activity C, which took in account the comments made by the expert during the previous meeting held on 25 March 2021. The experts provided further comments, and these comments having been discussed, agreed on a final version, ready to be transmitted to COLEACP.

The Secretariat presented the draft activity E. The experts noted that some elements in this draft, dealing with food safety, could be considered as out of the scope of the phytosanitary export certification. Also, an expert drew the attention of the WG on the fact that the part addressing traceability could be redundant with the draft activity D – Traceability.  The drafter of this activity agreed to review the draft, in such way to withdraw all elements out of the scope of the e-Learning. The drafter of draft activity D declared that he will verify the consistency between drafts E and D regarding traceability.

The WG raised the issue of the editorial verification of the draft proposed (quality of English). The representative of COLEACP declared that COLEACP can take this verification in charge. Confirmation of this will be sent to the Secretariat.

The representative of COLEACP confirmed that, as soon as the final versions of the activities are transmitted, the COLEACP will start the transposition in e-Learning, including preparation of questionnaire.

The WG agreed on the following stages.

- -Just after the meeting, the Secretariat will put the final versions of parts A, B and C on the dedicated Dropbox for possible last comments of the experts.

- -On Tuesday 20 April, the Secretariat will transmit the final versions of parts A, B and C to COLEACP for transposition in e-Learning, or will address the last comments, if any, with experts concerned, and transmit the version after.

- -By Friday 23 April, the drafter of activity E will send a reviewed version of part E to the Secretariat for posting on Dropbox.

- -By Thursday 29 April, the drafters of activities H to R, regarding modules 3- Export inspector and 4-Export supervisor, will send a draft to the Secretariat to be posted on the Dropbox, however there are recommended to send their drafts before if possible, as soon as there are completed.

- -By Friday 30 April, the experts will provide comments on the new version of activity E. After this date the Secretariat will address the comments with the experts. After agreement of the experts, the final version of activity E will be transmitted to COLEACP for transposition in e-Learning.

- -On Wednesday 12 May, next WG meeting, the drafts will be discussed by the experts. The first drafts to be discussed will be D and G.

The Chairperson thanked the participants and closed the meeting.

Appendix 1: Agenda

# PROVISIONAL Agenda

Updated 2021-03-31

| AGENDA ITEM |  | Duration (mn) | DOCUMENT NO. | PRESENTER |
| --- | --- | --- | --- | --- |
| 1 | Opening of the Meeting | 5’ | -- | IPPC Secretariat |
| 2 | Meeting Arrangements | 5’ |  | Denis ALLEX |
| 2.1 | Election of the chairperson |  |  | IPPC Secretariat All participants |
| 2.2 | Election of the rapporteur |  |  | Chairperson |
| 2.3 | Adoption of the Agenda |  | 01_ WG e-L EXP_2021_Tel_Apr | Chairperson |
| 3 | Administrative matters | 5’ |  |  |
| 3.1 | Documents list |  | link | IPPC Secretariat |
| 3.2 | List of participants |  | 02_ WG e-L EXP_2021_Tel_Apr | IPPC Secretariat |
| 4 | Development of the e-learning course |  |  | IPPC Secretariat |
| 5.1 | A-Overview of phytosanitary certification | 10’ | - | IPPC Secretariat |
| 5.2 | B-Plant pests and their control | 10’ | - | IPPC Secretariat |
| 5.3 | C-Collaboration with plant and plant product providers/NPPO | 10’ | - | IPPC Secretariat |
| 5.4 | D-Traceability | 20’ | - | Damian CLARKE |
| 5.5 | E-Transmission of information to workers | 15’ | - | Roberto PAPA |
| 5.6 | F-Collaboration (re) exporters) NPPO | 20’ | - | IPPC Secretariat |
| 5.7 | G-Phytosanitary (re)export certificate | 20’ | - | Avtar VIRK |
| 5.8 | Discussion on other modules | 20’ |  | Chairperson |
| 8 | Any Other Business | 5’ | -- | Chairperson |
|  | Confirmation date of next meeting |  |  |  |
| 9 | Close of the Meeting |  | -- | Chairperson |

Appendix 2: Participants list

# Participants list

# (Updated 2021-04-15)

| Participant Role | Name, mailing address, telephone | Email address |
| --- | --- | --- |
| Member Not present | Ms. Rosa BERNARDO Head of area for border control and phytosanitary agreements Ministry of Agriculture Fisheries and Food- SPAIN | mbernarc@mapa.es |
| Member Present | Mr. Damian CLARKE Senior adviser Ministry of Primary Industries – NEW ZEALAND | damian.clarke@mpi.govt.nz |
| Member Present | Ms. Rocio Leila FERNANDEZ Professional analyst in plant protection National Service for Agrifood health and quality (SENASA)-ARGENTINA | rfernand@senasa.gov.ar |
| Member Not present | Mr. Marcus McELVAINE Senior export specialist United States Department of Agriculture – USA | marcus.mcelvaine@usda.gov |
| Member Not present | Mr. Ignacio MENENDEZ Regional coordinator of Plant health inspections Ministry of Agriculture, Fisheries and food- SPAIN | ignacio.menendez@correo.gob.es |
| Member Present | Mr. Roberto PAPA Federal Superintendent Ministry of Agriculture Livestock and Food Supply- BRAZIL | roberto.papa@agricultura.gov.br |
| Member Present | Mr. Bruno SCHIFFERS Senior expert on training COLEACP (Comité de liaison Europe Afrique Caraibe Pacifique) | Bruno.schiffers@coleacp.org |
| Member Not present | Mr. Josiah SYANDA Phytosanitary expert Kenya Plant Health Inspectorate Service (KEPHIS)-KENYA | jsyanda@kephis.org |
| Member Present | Mr. Avtar VIRK Senior Specialist International Phytosanitary Standards Canadian Food Inspection Agency (CFIA) –CANADA | avtar.virk@canada.ca |
| Implementation and Capacity Development Committee Present | Mr Ahmed M. Abdellah ABDELMOTTALEB Plant Health Officer- Plant Protection and Quarantine Dep., Ministry of Municipality and Environment Doha, Qatar. | bidoeng@yahoo.com |
| IPPC Secretariat Not present | Mr. Brent LARSON Agricultural Officer International Plant Protection Convention Secretariat (IPPC) Food and Agriculture Organization of the United Nations (FAO/UN) | Brent.Larson@fao.org |
| IPPC Secretariat Not present | Ms. Sarah BRUNEL Agricultural Officer International Plant Protection Convention Secretariat (IPPC) Food and Agriculture Organization of the United Nations (FAO/UN) | Sarah.Brunel@fao.org |
| IPPC Secretariat Present | Mr. Denis ALLEX International Phytosanitary Specialist International Plant Protection Convention Secretariat (IPPC) Food and Agriculture Organization of the United Nations (FAO/UN) | Denis.Allex@fao.org |
| IPPC Secretariat Present | Mr. Descartes KOUMBA Agricultural Officer International Plant Protection Convention Secretariat (IPPC) Food and Agriculture Organization of the United Nations (FAO/UN) | Descartes.Koumba@fao.org |
| IPPC Secretariat Not present | Mr. Chiluba MWAPE International Phytosanitary Specialist International Plant Protection Convention Secretariat (IPPC) Food and Agriculture Organization of the United Nations (FAO/UN) | Chiluba.Mwape@fao.org |
| IPPC Secretariat Not present | Mr. Artur SHAMILOV Agricultural Officer International Plant Protection Convention Secretariat (IPPC) Food and Agriculture Organization of the United Nations (FAO/UN) | Artur.Shamilov@fao.org |

Appendix 3:

IPPC (IC) Working group to develop e-Learning material on phytosanitary export certification system

Structure of the modules

|  | Activity | Module 1 Plants and plant products providers | Module 2 Exporters and re-exporters | Module 3 Export inspectors | Module 4 Export supervisors | IPPC guides references Also CIPV, ISPMs 7, 12, 23 | Working group member in charge of developing content |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | Overview of phytosanitary certification | 1h00 | 1h00 | 1h00 | 1h00 | x | Secretariat Draft posted 5/03 Draft finalized 15/04 |
| B | Plant pests and their control | 1h00 | 1h00 | - | - | x | Secretariat Draft posted 9/03 Draft finalized 15/04 |
| C | Collaboration plants and pp providers /NPPO | 1h00 | - | - | - | x | Secretariat Draft posted 9/03 Draft finalized 15/04 |
| D | Traceability | 0h30 | 0h30 | - | - |  | Damian CLARKE Draft posted 9/04 |
| E | Transmission of information to workers | 0h30 | 0h30 | - | - |  | Rocío Leila FERNANDEZ/Roberto PAPA Draft posted 23/03 |
| F | Collaboration (re)exporters /NPPO | - | 1h00 |  |  | x | Secretariat Draft posted 12/03 |
| G | Phytosanitary (re)export certificate | - | 1h30 | - | - | x | Avtar VIRK/Damian CLARKE Draft posted 10/03 |
| H | Collaboration NPPO/private stakeholders | - | - | 1h00 |  | Guide exp 10. NPPO and Stakeholder Relationships in Promoting Compliance in Phytosanitary Export Certification | Secretariat |
| I | Measures for certifications | - | - | 1h30 | - | Guide exp 7. Certification for Specific Requirements 7.1. Requirement that the plants or plant products are taken from a PFA, PFPS, PFPP or ALPP 7.2. Requirement that the consignment be produced under a product certification scheme which ensures freedom from the pest 7.3. Treatment and certification 7.4. Export inspection as a stand-alone measure for certification 7.5. Measures required during transport | Ahmed ABDELMOTTALEB |
| J | Preparing the phytosanitary (re)export certificate | - | - | 1h30 | - | Guide exp 6 Obtaining the Importing Country’s Requirements 6.1. Sources of official information 6.2. Official information to be collected | Ahmed ABDELMOTTALEB |
| K | Issuing the phytosanitary certificate | - | - | 1h30 | - | Guide exp 8 Preparation and Issuance of Phytosanitary Certificates 8.1. Contents of phytosanitary certificates 8.2. Attachments to the phytosanitary certificate 8.3. Format 8.4. Specific considerations for the preparation and issuance of a phytosanitary certificate 8.5. Authorized personnel 8.6. Duration of validity of phytosanitary certificates 8.7. Considerations for preparing and issuing a phytosanitary certificate of re-export Guide exp 11 Record-keeping | Ahmed ABDELMOTTALEB |
| L | Non compliances | - | - | 1h00 | - | Guide exp 9 Invalid Phytosanitary Certificates | Secretariat and Avtar VIRK |
| M | The human resources | - | - | - | 1h00 | Guide exp 9 Requirements of the National Phytosanitary Export Certification System 4.1. Management requirements 4.2. Operational requirements for export certification | Damian CLARKE |
| N | Collaboration and communication NPPO/private stakeholders | - | - | - | 1h00 | Guide Stakeholders 2 Stakeholders: Definition, Benefits, Challenges and Roles. 2.1 Definition of stakeholder 2.2 The benefits of involving stakeholders 2.3 Challenges associated with stakeholder relations 2.4 The role of NPPOs in managing stakeholder input Guide Stakeholders 4 Stakeholder Input on Phytosanitary Operations 4.1 General considerations 4.3 Regionalization 4.4 Pest surveillance 4.5 Export certification and inspection systems 4.6 Eradication programmes and contingency plans 4.7 Systems approaches for pest risk management 4.8 Education and training 4.9 Government–industry agreements Appendix 6 Stakeholder Involvement in Establishing and Implementing a Systems Approach for Pest Risk Management | Secretariat |
| O | Organizing the certification | - | - | - | 1h30 | Guide exp 3 Export Certification Functions of the NPPO Guide exp 5 Obligations, Responsibilities and Activities of the NPPO of the Exporting Country | Ahmed ABDELMOTTALEB |
| P | Organizing preparation and issuance of phytosanitary (re)export certificate | - | - | - | 1h30 | Guide exp 8 Preparation and Issuance of Phytosanitary Certificates 8.1. Contents of phytosanitary certificates 8.2. Attachments to the phytosanitary certificate 8.3. Format 8.4. Specific considerations for the preparation and issuance of a phytosanitary certificate 8.5. Authorized personnel 8.6. Duration of validity of phytosanitary certificates 8.7. Considerations for preparing and issuing a phytosanitary certificate of re-export Guide exp 11 Record-keeping ePhyto website https://www.ephytoexchange.org/landing/index.html | Rocío Leila FERNANDEZ/ Ahmed ABDELMOTTALEB |
| Q | International collaboration | - | - | - | 1h30 | Guide exp 3 Export Certification Functions of the NPPO Guide exp 6 Obtaining the Importing Country’s Requirements 6.1. Sources of official information 6.2. Official information to be collected Guide Stakeholders 6 Liaison with international and regional Stakholders 6.1. Regional and sub-regional cooperation 6.2. International cooperation | Roberto PAPA |
| R | Management of non-compliances and review of the system | - | - | - | 1h30 | Guide exp 9 Invalid Phytosanitary Certificates Guide exp 12 Non-compliance Guide exp 13 Review | Secretariat /Avtar VIRK |
|  | TOTAL | 4h00 | 5h30 | 7h30 | 9h00 |  |  |