Commission on Phytosanitary Measures

STRATEGIC PLANNING GROUP MEETING

IPPC STRATEGIC FRAMEWORK 2020-2030: MID-TERM MONITORING AND EVALAUTION IN 2025

(Prepared by the IPPC Secretariat with inputs of the IC lead for the IC Subgroup on the IPPC Observatory)

This paper presents an overview of the mid-term evaluation of the IPPC Strategic Framework 2020–2030 Development Agenda Items (SF DAIs). The mid-term review aims to assess the progress made, identify key achievements, and address challenges in implementing the eight SF DAIs.

- Background

The IPPC Observatory is responsible for monitoring the implementation of the International Plant Protection Convention (IPPC), International Standards for Phytosanitary Measures (ISPMs), and CPM Recommendations. Monitoring and evaluation of the SF DAIs is one of the mandates of the IPPC Observatory. Therefore, it is also one of the IPPC observatory priority topics, “Develop baseline measures to monitor the impacts of and record/report benefits of the Strategic Framework 2020-2030” (2018-52). This topic has been included in the IPPC Observatory 2021-2024 workplan.

CPM-16 (2022) agreed that the IPPC Observatory would contribute to monitoring the achievements of the objectives outlined in the IPPC Strategic Framework 2020–2030. CPM-17 (2023) requested that the IPPC Secretary consider establishing a new position of programme manager, to coordinate, monitor, report and mobilize funds for the programme.  CPM-18 (2024) noted that the IPPC Strategic Framework project manager should be hired before strategic framework monitoring activities commence, following which the IPPC Observatory would provide the necessary support.

Despite its exclusive mandate to deliver the monitoring and evaluation of the strategic framework, the IPPC Observatory has not been able to start working on this task since no dedicated project manager position, as requested by CPM-17, has been established at the IPPC Secretariat in addition to no financial resource allocation for its sustainable setting. These issues had been discussed at several Implementation and Capacity Development Committee (IC) meetings.

The government of Canada allocated USD 31,521 for the IPPC Observatory Study on E-Commerce. Activities for this study are currently ongoing and planned to be finalised in 2025. More information on the IPPC Observatory Study on E-Commerce is provided in paper 08_SPG_2024_Oct (agenda item 7.3).

The government of the Republic of Korea earmarked USD 30,000 for the IPPC Observatory activities from its contributions to the IPPC Multi-Donor Trust Fund. This amount will be used to support the general IPPC Observatory activities, while the specific allocation of funds will be determined at a later stage.

During its May 2024 meeting, the IC discussed the importance of monitoring and evaluation of the IPPC Strategic Framework 2020–2030 DAIs to understand what was achieved, what were the challenges and what was remaining. Thus, the IC invited the CPM Bureau to discuss and provide guidance on the mid-term monitoring and evaluation of the SF DAIs in 2025t. The importance of the mid-term evaluation in 2025 was further discussed during the CPM Bureau September 2024 virtual meeting.

- Terms of Reference of mid-term monitoring and evaluation of the IPPC Strategic Framework 2020-2030 DAIs

The monitoring and evaluation framework to be developed for the 2025 mid-term evaluation will serve as the foundation for the final evaluation in 2030. The key objectives for the 2025 evaluation include:

- Gathering data and conducting a thorough analysis of progress for each DAI.

- Assessing the relevance, effectiveness, and impact of the framework.

- Identifying achievements, implementation challenges, and bottlenecks.

- Proposed Approach and Timeline

Planning Phase:

- Define the scope and objectives of the evaluation.

- Develop the evaluation framework and criteria.

- Identify key stakeholders and form an evaluation team.

- Design data collection methods (e.g., desk reviews, interviews).

Data collection Phase:

- Conduct a document review of the strategic framework, implementation reports,

monitoring plans for each DAI, and any other relevant materials.

- Gather quantitative data on progress indicators, such as implementation milestones,

financial reports, and outputs.

- Conduct key informant interviews with respective governing body leads and members, staff, partners, and stakeholders.

- Organize independent focus groups to review the DAIs or specific aspects if necessary and feasible.

Data analysis phase:

- Analyze quantitative data (progress, outcomes, and resources used) to assess effectiveness and implementation efficiency.

- Synthesize qualitative data from interviews.

- Assess the framework’s relevance in the current context and its adaptability.

- Evaluate the sustainability of the progress made and the potential long-term impact.

Reporting phase:

- Draft the evaluation report detailing findings on relevance, effectiveness, and

sustainability.

- Prepare recommendations to enhance the framework and its implementation.

- Design various formats for presenting findings, such as executive summaries and infographics.

- Share draft findings with key stakeholders for validation and feedback.

- Finalize the evaluation report based on stakeholder input.

Dissemination and Follow-up:

- Present findings to key stakeholders through a specific number of events.

- Create an article summarizing the findings for publication.

- Resource requirements

To deliver this important task, the IPPC Observatory will hire an expert consultant with expertise in monitoring, evaluation and learning, with experience delivering similar assignments. Additionally, IPPC Observatory staff and a communications expert will be involved throughout the whole process under the oversight of the Implementation and Facilitation Unit Lead.  The IC Subgroup on IPPC Observatory, as well as all other governing bodies for each SF DAIs will be involved in the mid-term evaluation and provide necessary input.

The cost of the mid-term monitoring and evaluation of the IPPC Strategic Framework 2020-2030 DAIs is estimated USD 53 250. The budget is detailed below:

| IPPC SF DAIs mid-term monitoring and evaluation 2025 |  |  |  |
| --- | --- | --- | --- |
|  | days | rate (USD) | total (USD) |
| MEL specialist | 80 | 450 | 36,000 |
| IPPC Observatory Coordinator | 30 | 300 | 9,000 |
| Comms | 15 | 350 | 5,250 |
| Admin support | 10 | 300 | 3,000 |
| Total |  |  | 53,250 |

- Recommendations

The SPG is invited to:

Share and discuss its views regarding the mid-term monitoring and evaluation of the IPPC Strategic Framework 2020-2030 DAIs, the proposed TORs and budget;

Mobilize resources through contracting parties' voluntary contributions to undertake this activity;

Consider sharing this paper, or a modified version of it, with the CPM and/or the CPM Bureau with a request to allocate necessary resources.