Commission on Phytosanitary Measures

# STRATEGIC PLANNING GROUP MEETING

Update on the Africa Phytosanitary Programme (APP)

(Prepared by the IPPC Secretariat)

Introduction

The International Plant Protection Convention (IPPC) Secretariat is implementing the Africa Phytosanitary Programme (APP), to empower plant health national authorities, namely, national plant protection organizations (NPPOs) and stakeholders, with the capacity in science and digital technology necessary to rapidly detect and respond to and recover from outbreaks of plant pests that have regulatory, economic, and environmental consequences. The IPPC implements APP in collaboration with the Food and Agriculture Organization of the United Nations (FAO) and the African Union Department of Agriculture, Rural Development, Blue Economy, and Sustainable Environment. APP is designed to enhance the resilience of Africa’s plant health systems against significant plant pests.

APP implementation kicked off in September 2023 with a Train-the-Trainer workshop in Cairo, Egypt, organized together with USDA-APHIS and FAO regional office for Near East (FAORNE). The IPPC envisages implementing APP in all 54 African countries and has adopted a phased in approach, starting with 11 countries in the pilot phase. These are: Cameroon, the Democratic Republic of Congo, Egypt, Guinea Bissau, Kenya, Mali, Morocco, Sierra Leone, Uganda, Zambia, and Zimbabwe. Egypt, Kenya, Uganda, Zambia and Zimbabwe are also among the countries that the IPPC Secretariat supported to complete Phytosanitary Capacity Evaluations (PCEs).

Below are some progress updates

Countries

Currently, the IPPC Secretariat is focusing on supporting the 11 pilot countries to carry out activities to effectively implement the programme.  This will ensure that they have adequate training, materials and resources to conduct active and regular pest monitoring and detection using the APP tools, before introducing the second phase of 10 additional countries. The 11 pilot countries (NPPOs) provided work plans aligned with the 2023 APP strategy.

The secretariat received nominations of phase two countries and plans to engage countries from Eastern and West Africa, on their readiness to participate in APP. Burundi, Somalia, South Sudan, Niger and Liberia will be invited to virtual meetings to discuss their selection of pests and finalise the nominations. The secretariat foresees implementation challenges in some of these countries e.g. political instability, travel restrictions for UN staff, and under-developed phytosanitary infrastructure.

Once all phase two countries have been selected, they will be asked to provide lists of five pests of economic, environmental, and regulatory importance. The United States Department of Agriculture Animal and Plant Health Inspection Service (USDA APHIS) will support the development of survey protocols and digital applications for these pests (excluding any already reported by pilot countries).

The Train-the-trainer workshop for the second phase is planned for the second half of 2025. The NPPO of South Africa expressed interest in hosting this workshop.

Participants from last year's Train-the-Trainer workshop for pilot countries were expected to organize national-level training workshops for phytosanitary personnel to learn to use the APP tools and tablet computers. So far, the Democratic Republic of Congo (DRC), Egypt, Guinea-Bissau, Kenya, Sierra Leone, Uganda and Zambia have conducted training at the national level.

The IPPC Secretariat proposes supporting the pilot countries to conduct comprehensive national-level training and improve their pest surveillance and outbreak response and management. The secretariat will request support from USDA’s technical team to facilitate the training.

APP Governance

To provide guidance and coordination in the implementation of APP activities, the Operational Coordination Group (OCG), Technical Working Group (TWG) and Communications Working Group (CWG) were formed. The IPPC team developed the terms of reference for each group, reviewed them together with the two regional plant protection organizations (RPPOs)- AU-IAPSC and NEPPO, and invited nominations from the relevant organizations.

The OCG comprises representatives from NPPOs, RPPOs, Regional Economic Communities (RECs), and invited partners. The group will coordinate, oversee, and monitor the delivery of APP and will meet monthly.

The OCG had its initial meeting on 17 July. The group has eight out of 14 expected members, including representatives from the NPPO of Kenya and Mali, FAO Uganda, FAO subregional office for central Africa, AU-IAPSC and NEPPO. The latter two have the role of Chair and Vice Chair respectively and are collaborating with the secretariat to receive nominations to fill all the positions on the OCG.

The TWG was established to provide ongoing technical support to the IPPC Secretariat and participating countries, including bridging knowledge gaps to ensure effective APP implementation. The first meeting was on 24 July and the 17-member group includes representatives from African regional and international plant health and agricultural organisations such as ANSES France, USDA, CABI, CIRAD, International Centre of Insect Physiology and Ecology (ICIPE) and International Institute of Tropical Agriculture (IITA).

A SharePoint folder has been created for the TWG to share and work on documents online including pest prioritization processes for the pests of concern in the pilot countries.

Seven of 11 expected nominations for the CWG have so far been received. The Chair and Vice Chair of the OCG will coordinate with the secretariat to receive all nominations by 26 September.

The first meeting is planned for October, during which the group will review the draft APP communications plan.

Technical support

Staffing

The IPPC Secretariat proposed some staff to continue supporting APP implementation and supporting the pilot countries. The team members are:  Arop Deng- IPPC Officer in Charge and Team Lead for the Integration and Support Team, John Gilmore- Agriculturist and Foreign Service Officer, Tanja Lahti- IPPC Meetings Associate, Artur Shamilov- Standards Setting Officer, Descartes Koumba- Implementation Facilitation Officer, Tommaso Teti- Project management and resource mobilization specialist, and Anita Tibasaaga- Communication specialist.

This interim APP team has monthly meetings with NPPOs of the 11 pilot countries. During the monthly meetings, NPPOs receive an update from the secretariat and share their implementation progress updates or discuss other programme-related matters.

The team proposes the recruitment of Geographic Information System (GIS) specialist to support technical backstopping for NPPOs on using the APP mobile applications and liaising with USDA developers.

Descartes Koumba was requested to draft Terms of reference (ToRs) for a GIS specialist, in consultation with colleagues at the secretariat and USDA/APHIS. The secretariat will check if FAO has rosters for GIS specialists.

Tablets

Through APP, the IPPC Secretariat committed to providing NPPOs in the participating countries with at least 50 tablets per country. During the September 2023 workshop, each country received 5-6 tablets, one for each national participant.

By September 2024, the secretariat had dispatched 40 additional tablets to each country. So far, Cameroon, Guinea-Bissau, Kenya, Mali, Uganda, Zambia, Zimbabwe and Egypt acknowledged receipt of the tablets, while the DRC, Morocco and Sierra Leone are yet to clear the consignments at the border customs offices.

The secretariat maintains a record/log of the individual phytosanitary technician assigned to a particular tablet at the country level and works with NPPO-nominated IT focal persons and FAO country office focal person to support the countries.

The United Nations International Computing Centre (UNICC) provides technical IT support and hosts the APP GIS Hub. The secretariat is working with UNICC to complete the registration of tablets.

Field supplies

The secretariat is working with FAO’s procurement unit to source vendors for assorted field supplies such as bucket insect traps and pheromones. Bid solicitation ends on 23 September.

The secretariat will engage the APP Technical Working Group (TWG) to identify other procurable field supplies such as diagnostic kits and other supplies indicated in countries’ operation plans.

Survey protocols

USDA APHIS developed survey protocols for the pests listed by the pilot countries. The Secretariat has so far received 10 protocols and expects to receive 18 more soon.

Budget and planning

APP's initial funding of USD 250 000 was from USDA. Additional funding will support the procurement and distribution of more tablets to the second set of countries, the acquisition of field supplies, and the provision of onsite and virtual technical support to countries.

The IPPC Secretariat is expecting funds from the Government of the United Kingdom and the European Commission (for three IPPC work areas).

The agreement with the UK is in its final review stage. Funding will be for two years, with 700 000 Pounds released in the first year and 250 000 in the following year. Project support is expected to start in October or November 2024.

The agreement with the European Commission is pending approval signatures and is expected to start on 1 November. Funding will be for three years for a value of more than USD 600 000.

The team will draft a two-year work plan and budget to anticipate APP activities. This plan will be shared with donors, FAO and IPPC management team for review and approval.

Communication and visibility

The APP brochure was developed and published via FAO’s PWS. It is available in English, French, Arabic and Portuguese, which are the languages spoken by the pilot countries, and most other African countries.

The IPPC Secretariat maintains an APP webpage on the IPPC website, with information about the project, photos, updates and access to the APP GIS Hub. Ten news articles on APP have been published so far on the website.

APP has been mentioned in FAO news and African regional media outlets (print, TV, audio) at least 40 times in the last one year. This media coverage has raised awareness about APP and the IPPC’s support to countries in strengthening their national phytosanitary and pest monitoring capacity. Here are some examples, Egypt, Uganda, FAO RNE, FAO Kenya, African Union.

Planned communications work includes a social media campaign and supporting countries to document their training and field activities.

Social media is also being used to increase visibility and awareness about APP on Twitter, Facebook and LinkedIn. This information is amplified and reposted by FAO country offices, FAO liaisons offices, NPPOs and RPPOs with online presence.

Advocacy and outreach

Osama El-Lissy, former IPPC Secretary travelled to all pilot countries to discuss APP with the political and technical leadership of the ministries responsible for the work of NPPOs.

He met cabinet ministers in the Cameroon, Democratic Republic of Congo, Egypt, Guinea-Bissau, Kenya, Mali, Sierra Leone, Zambia, Zimbabwe and representative of ministers in Morocco and Uganda.

The Secretary wrote to the ministers after the meetings, providing a recap of discussions and affirming commitments to support APP.

Recommendations

SPG is invited to:

Note the report

Discuss the report and make recommendations on the APP plans moving forward.