CPM Focus Group on Sea Containers – Action Plan (as approved by the CPM Bureau (October 2024)

| Month, Year | Key activity | Outputs and deliverables |
| --- | --- | --- |
| July 2024 | VIRTUAL MEETING (9 and 11 July) Identify key activities to support ToR and populate action plan, including: - Establish sub-groups on: - Regulatory and Non-regulatory Options, Costs and Benefits - Multilateral Frameworks - Data Model (DM) of the World Customs Organization (WCO) - CTU Code Update - Data and Risk - Sea Container Design, Innovations and Trials - Planning Group for Workshop 2026 - Identify gaps in knowledge and/or activities taking place - Draft action plan commenced. | - Sub-groups formed and members identified along with relevant ToR activities to be addressed through these groups. - Focus Group action plan drafted for finalization in October 2024 prior to CPM Bureau October 2024 meetings. - Consider initial meetings for sub-groups prior to October 2024 virtual meeting. |
|  | - Prepare initial communications to stakeholders on the Recommendation and the Focus Group. - Identify channels to obtain feedback on the Recommendation. - Preparing/issuing communications on the Rotterdam Symposium. - Prepare an engagement plan for Focus Group members to engage with appropriate bodies e.g. WCO, IMO and industry associations. Tasks relating to ToR activity #6 | - Communication products - Established communication channels (consider mechanism for oversight of information received) - Develop common talking points |
| September 2024 | - Prepare initial compendium of known emerging and evolving innovations, research and other information to be reviewed over following two years. | - Identified known trials underway. - Utilise identified knowledge to assist to formulate work of the sub-groups and agenda for 2026 workshop. |
|  | Initial meetings of sub-groups where feasible, to consider future steps and focus. | - Initial considerations from sub-groups to assist in determining side sessions to be held during December 2024 physical meeting. |
| October 2024 | VIRTUAL MEETING (01 October 2024) - Review and finalize draft action plan for presentation to the Bureau in October 2024. - Develop agenda for December 2024 physical meeting. - Consider stock-take of activities for small working groups. - Provide requests from UNECE informal working group relating to the revision of the CTU Code. | - Finalized action plan for the Focus Group. - Consider focus and outcomes of December 2024 physical meeting / develop agenda. - Initiate compiling consolidated listing of known innovations and trials - Initiate outlines of workplans for small groups. - Finalized proposal to UNECE informal working group for revision of the CTU Code. |
| October 2024 | Present draft Action Plan to Bureau (23rd – 25th October) Activity relates to task #8 of the ToR | - Approved action plan - Action plan to CPM for noting |
| November 2024 | 11 November – Symposium Rotterdam Activity relates to task #2 of the ToR | - Report of the Symposium relating to the Recommendation |
| December 2024 | PHYSICAL MEETING (09-13 December 2024) Key agenda items: - Outline for 2026 workshop - Identification of any trials that could be promoted - Updates from small working groups and review of activities - Break out meetings for some small groups Activities relate to all tasks of the ToR | - Physical meeting in Rome - Progress reports from small groups - Outline for 2026 workshop |
| March 2025 | CPM-19 (17-21 March 2024) - Approved action plan and INF paper to CPM-19 for noting. |  |
| First half 2026 |  | - Updated CTU Code |
| June 2025 | MEETING (dates TBC) - Review outcomes of CPM-19, review and update Action Plan. - Identify arrangements for workshop in 2026 and related activities. | - Virtual meeting; or given content a physical meeting may be required. |
| September 2025 | MEETING (dates TBC) - Work to analyze the information gathered in activities 1-4 of the ToR. Provide recommendations to CPM that are consistent with the pest risk on preferred options for regulatory and/or non-regulatory actions including additional guidance and whether development of an ISPM is feasible and desirable, and draft specifications for such actions as necessary. Relates specifically to activity #5 of the ToR | - Preliminary identification on the FGs emerging position. |
| October 2025 | - Bureau and SPG updated action plan and emerging recommendations |  |
| June 2026 | MEETING (dates TBC) - Review outcomes of CPM-20, review and update Action Plan. - Confirm arrangements for workshop in 2026 including all presenters and materials. | - Virtual meeting; or given content a physical meeting may be required. |
| June - September 2026 | - Industry-government Workshop to review experiences with the IPPC Recommendation. | - May need a year to plan, but also need sufficient time afterwards to analyze and draw conclusions. |
| October 2026 | - Bureau and SPG updated action plan and emerging recommendations. |  |
| December 2026 | - Prepare final report and recommendations for CPM-21, as per the ToR expected outputs and advice on future guidance |  |