INTEGRATION OF NROS IN THE AFRICA PHYTOSANITRAY PROGRAMME (APP) IMPLEMENTATION

(Prepared by the IPPC Secretariat)

Background

- The Africa Phytosanitary Programme (APP) is an initiative of the International Plant Protection Convention (IPPC), in collaboration with the African Union Commission on Agriculture, Rural Development, Blue Economy, and Sustainable Environment (ARBE), and implemented alongside the Food and Agriculture Organization of the United Nations (FAO). The APP aims to enhance the resilience of Africa’s phytosanitary systems against plant pests that pose regulatory, economic, and environmental challenges. The programme seeks to empower Africa’s plant health professionals by providing training, fostering collaboration, leveraging resources, and enhancing knowledge sharing, all aimed at preventing and managing the impact of plant pests in the region.

- Following two years of APP implementation, since its launch in September 2023, and in anticipation of launching Phase Two (with eight new countries), it is pertinent to gain a clearer understanding of the management, coordination, and implementation of APP. Additionally, it is important to assess the IPPC Secretariat's commitment and the additional workload that APP entails for the involved Secretariat staff. As requested by the CPM Bureau, this paper aims to clarify the importance of APP coordination and management within the IPPC Secretariat, ensuring that the APP implementation strategy aligns with the Secretariat's mission.

APP objectives and support to countries

- The APP, the first continent-wide phytosanitary programme, is designed to assist all 54 African countries in preventing and managing plant pests, thereby reducing their impact on food security and trade. The APP aims to empower national plant protection organizations (NPPOs) across Africa to utilize scientific methods and modern technologies to proactively monitor, efficiently detect, and effectively respond to plant pests and diseases of significant economic, regulatory, and environmental importance.

- APP implementation is a key mechanism for executing continent-wide plant health strategies, as outlined in the Plant Health Strategy for Africa (PHSA), and for promoting safe trade under the African Continental Free Trade Area (AfCFTA) Agreement. Pilot countries identified five priority pests, and through APP, the IPPC, supported by the United States Department of Agriculture Plant Health Inspection Service (USDA APHIS), develop field survey protocols and provided countries with state-of-the-art tablets for effective and timely pest surveillance, pests identification and control.

- Through the APP, pilot countries benefited from regional training for a select group of experts (5-6) who then serve as national trainers for other national phytosanitary professionals. Each country received approximately 50 tablets configured for data collection using survey protocols and mobile applications (Field Maps and Survey 1, 2, 3), which are accessed through individual ESRI user accounts. Data collected by surveyors is transferred to a georeferenced database (APP GIS HUB) dedicated to each country and hosted on the IPP. In addition to the mobile application tools, through APP, the IPPC Secretariat is procuring complementary field materials, such as traps, lures, and pheromones. Depending on the financial resources mobilized, the programme also plans to support countries in organizing their APP national trainings. To date, Guinea-Bissau, Cameroon, and Kenya have received support for these trainings, with at least two experts from other countries attending the APP refresher trainings3 both held separately in Douala, Cameroon and Nairobi, Kenya in January 2025.

- To ensure the programme sustainability, the APP implementation strategy must be refined to achieve the programme's objectives without compromising the ongoing or advancing activities of the IPPC Secretariat. This should include clearly defining the roles of the partners involved in the implementation, adjusting the IPPC Secretariat's involvement, and refining the deployment with mid-term phases according to available resources.

- APP sustainability also will depend on a better integration of the IPPC tools and activities. Indeed, since its launch, it has been agreed that the APP team should be composed of representatives from IPPC Secretariat units and teams. The objective being that APP countries should, through this program, request to conduct PCEs, contribute to strengthening their capacities through the IPPC plant health campus, facilitate the integration of the ePhyto solution, contribute to emerging pests' assessment through POARS and even to fulfil their NROs.

- During its March meeting the CPM Bureau agreed to redefine the APP implementation strategy to achieve programme objectives without compromising ongoing or advancing activities, which include enhancing integration of APP with IPPC tools and activities (PCEs, IPPC Plant Health Campus, ePhyto, POARS and NROs); and proposed for the new IPPC secretary to consider a suitable and sustainable long-term strategy for APP including a better integration to IPPC activities, reputational risk, and adapting the scope and the management  with the available resources.

Recommendations

- The IC Team is invited to:

- Discuss and recommend proposals to better integrate National Reporting Obligations in the Africa Phytosanitary Programme implementation.

APP webpage: https://www.ippc.int/en/about-app/

APP GIS HUB: https://gpp.ippc.int/