Commission on Phytosanitary Measures

# STRATEGIC PLANNING GROUP

IPPC OBSERVATORY: Final REVIEW AND EVALUATION OF THE IPPC STRATEGIC FRAMEWORK DEVELOPMENT AGENDA ITEMS

(Prepared by the IPPC Secretariat with input from the IC Subgroup on the IPPC Observatory Lead)

Introduction

Review and evaluation of the IPPC Strategic Framework 2020-2030 Development Agenda Items (SF DAIs) is one of the mandates of the IPPC Observatory. Initially planned as a mid-term review, the exercise aimed to assess and evaluate progress, achievements and challenges in implementing the eight (8) SF DAIs, as a mid-term stock taking exercise. It is also one of the IPPC Observatory priority topics: “Develop baseline measures to monitor the impacts of and record/report benefits of the Strategic Framework 2020–2030” (2018-52).

Background

During its May 2024 meeting, the IC discussed the importance of mid-term review and evaluation of the IPPC SF DAIs in 2025 and invited the CPM Bureau to discuss and provide guidance. The secretariat developed provisional terms of reference with clear objectives and scope of the exercise and presented it to the CPM Bureau and the Strategic Planning Group (SPG) in October 2024. During these presentations, the secretariat explained that the mid-term review and evaluation was intended to create a framework that would serve as a foundation for the final evaluation of the SF DAIs.

The SPG expressed wide support for the relevance and importance of this work, agreeing on the importance of the final review and evaluation, which would be more impactful if conducted closer to the development of the next IPPC strategic framework. Based on the feedback from the bureau and SPG, the secretariat made minor revisions to the terms of reference, and presented it to CPM-19. The CPM-19 agreed on the importance of monitoring and evaluation of the IPPC Strategic Framework 2020–2030 DAIs implementation, and advised to undertake the exercise prior to initiating work on the development of the next IPPC Strategic Framework (ideally in 2027), with a revised terms of reference that would allow assessment of all DAIs at different stages of development, provided to CPM-20 (2026).

Second round of consultations: revised terms of reference

Following the CPM-19 decisions, the secretariat revised the terms of reference and undertook another consultation with the IC Subgroup on the IPPC Observatory and the IC. With the feedback and suggestions received from these consultations, the terms of reference were revised to include modularity and scalability, so that the assessment could be adapted to each phase and be applied to DAIs at varying levels of maturity—from concept to advanced implementation. Additionally, core and optional criteria were added so that the evaluation exercise could be tailored for each DAI.

The secretariat presented the revised terms of reference to the CPM Bureau in June 2025, which noted the revisions and requested the secretariat to present the revised terms of reference to SPG in October.

The consolidated version of the terms of reference, incorporating all revisions, is presented in Appendix 1. This document serves as a high-level guiding framework for the final review and evaluation of the IPPC SF DAIs. Its purpose is to outline the scope, principles, phases, and overall approach, while maintaining sufficient flexibility to accommodate potential challenges or adjustments during implementation.

With the revisions made to the terms of references, the cost of the exercise is estimated to be between USD 60,000 and 70,000.

Recommendation

The SPG is invited to:

review and discuss the revised terms of reference for the final review and evaluation of the IPPC Strategic Framework 2020–2030 Development Agenda Items, as presented in Appendix 1, in line with CPM-19 (2025) recommendation.

- APPENDIX 1: Finale review and evaluation of the IPPC Strategic Framework 2020-2030 Development Agenda Items: revised terms of reference

  - Purpose and Objectives

The evaluation aims to:

- Assess the relevance, progress, and effectiveness of the DAIs against the IPPC Strategic Framework 2020-2030 objectives.

- Identify factors influencing progress or limited implementation.

- Provide actionable recommendations for strengthening implementation, adaptability, and sustainability.

- Support evidence-based decision-making and strategic alignment of the DAIs.

  - Evaluation Principles

- Modularity: Evaluation components will vary by implementation progress for each DAI.

- Scalability: Evaluation depth and scope will align with each DAI's complexity and progress.

- Adaptability: Evaluation criteria and tools will be tailored based on available data and context.

- Participation: Stakeholders will be engaged throughout to ensure relevance and ownership.

- Equity, inclusivity and ethics: The evaluation will promote inclusive participation and uphold ethical standards, ensuring fair representation across genders, regions, institutions, and stakeholder groups, while safeguarding confidentiality and informed consent.

  - Evaluation Framework The evaluation will apply a tiered framework aligned with the stage of each DAI:

| Tier | DAI stage of implementation | Focus areas |
| --- | --- | --- |
| 1 | Concept phase – pre-implementation | Relevance, theory of change/ overall implementation plan, stakeholder engagement |
| 2 | Early implementation | Theory of change/ overall implementation plan, progress, process efficiency, institutional support |
| 3 | Advanced implementation | Theory of change/ overall implementation plan, outcomes, sustainability, potential impact |

  - Each DAI will be evaluated using core criteria applicable to all tiers, and optional criteria based on the level of progress in terms of implementation:

- Core criteria: relevance, alignment with IPPC and the IPPC Strategic Framework 2020-2030, stakeholder engagement

- Optional criteria: efficiency, sustainability, long-term impact

Note: the core criteria will be applied to all DAIs, whereas the optional criteria will be selected based on the DAI’s stage of implementation and in consultation with key stakeholders to ensure contextual relevance.

  - Evaluation Phases and Activities

  - Planning Phase

- Define DAI-specific evaluation scope and objectives.

- Classify each DAI by the level of progress in terms of implementation.

- Adapt evaluation questions and criteria accordingly.

- Identify key stakeholders and assemble evaluation team.

- Design appropriate data collection strategies.

  - Data Collection Phase

- Conduct desk review of DAI-related documents, reports, and plans.

- Gather quantitative data on progress indicators where available.

- Conduct interviews with governing body leads, IPPC secretariat staff, partners, and NPPOs, RPPOs, and stakeholders.

- Organize focus groups for selected DAIs, as needed.

Note: the evaluation will apply mixed-method approaches, including both qualitative and quantitative techniques, as appropriate to each DAI.

  - Data Analysis Phase

- Analyse quantitative data to assess implementation efficiency and outputs.

- Synthesize qualitative insights from interviews and focus groups.

- Evaluate adaptability, relevance, and sustainability.

- Draw cross-cutting findings and comparative insights.

  - Reporting Phase

- Develop tailored evaluation outputs:

  - Brief summaries for Tier 1 DAIs

  - Standard reports for Tier 2 and 3 DAIs

- Include executive summaries and infographics for accessibility.

- Share preliminary findings with stakeholders for validation.

- Compile and finalise report incorporating feedback.

  - Dissemination and Follow-up

- Present findings to stakeholders in appropriate forums.

- Publish a report.

- Develop a follow-up action plan with lessons learned and best practices to feed the development of the next IPPC strategic framework beyond 2030.

- Findings will aid and inform priority setting, resource allocation and the design of future DAIs.