Commission on Phytosanitary Measures

# STRATEGIC PLANNING GROUP

update on the africa phytosanitary programme (app)

(Prepared by the IPPC Secretariat)

- Background

- The International Plant Protection Convention (IPPC) Secretariat is implementing the Africa Phytosanitary Programme (APP), to empower phytosanitary officers of national plant protection organizations (NPPOs) and relevant national stakeholders, with modern science and advanced digital tools to boost their capacity to rapidly detect, respond to and recover from outbreaks of plant pests that have regulatory, economic and environmental consequences.

- The APP is designed to enhance the resilience of Africa’s plant health systems against significant plant pests and is envisaged to support all African countries, starting with a pilot phase of 11 countries. The IPPC is implementing APP in collaboration with the Food and Agriculture Organization of the United Nations (FAO) and the African Union Department of Agriculture, Rural Development, Blue Economy, and Sustainable Environment.

- 2. APP implementation - Phase two

- APP Phase two was launched with a Train-the-trainer (ToT) workshop from 23-27 June 2025 in Mpumalanga Province, South Africa. Nine countries joined this phase: Algeria, Cape Verde, Chad, the Republic of Congo, Liberia, Malawi, Senegal, South Africa and Tunisia, bringing the number of participating countries to 20.

- FAO Deputy Director-General Beth Bechdol delivered a recorded video message, emphasising APP’s contribution to building a critical mass of phytosanitary personnel across Africa, equipped to prevent and address plant pest threats that jeopardise food security, agricultural trade, economic growth and the environment.  John Henry Steenhuisen, the Honourable Minister of Agriculture of South Africa, delivered his remarks through the Head of the NPPO of South Africa. Also present were representatives from the European Commission, USDA APHIS, AU-IAPSC and NEPPO.

- Phytosanitary officers from six pilot countries- Cameroon, Guinea-Bissau, Kenya, Mali, Zambia and Zimbabwe shared their experiences in APP implementation. They presented their progress and highlighted successes, challenges, gaps and opportunities.

- Each of the twenty APP participating countries in the two phases have submitted their APP national implementation plans (2025-2027) and the APP GIS HUB has been updated to include the nine countries in phase 2.

- 3. Surveillance capacity development

- 3.1. APP trainings

- In January 2025, the secretariat combined national training of two of the pilot countries with refresher training for officers trained in Cairo. The Kenya Plant Health Inspectorate Service (KEPHIS) hosted refresher training for English-speaking pilot countries (Egypt, Kenya, Sierra Leone, Uganda, Zambia and Zimbabwe) while the NPPO of Cameroon hosted similar training for French-speaking countries (Guinea-Bissau, Cameroon, Democratic Republic of Congo, Mali and Morocco). Both sessions were facilitated by the IPPC Secretariat team.

- From September to December, the IPPC Secretariat will support NPPOs from eight APP participating countries to conduct or plan national training of plant health officers in Zimbabwe, South Africa, Uganda, Zambia, Sierra Leone, Egypt, Morocco and Malawi. So far, Zimbabwe, South Africa and Uganda have completed their workshops.

- The participants, who attended the ToT workshops and became master trainers, will pass on the knowledge and skills to their peers, strengthening national capacity in pest surveillance, diagnostics, identification and reporting and promoting regional collaboration.

- In July 2025, IPPC Secretariat held two online training sessions on the use of APP mobile applications, mapping and GIS-HUB for English and French-speaking participants from the 20 APP participating countries.

- The republication of the field survey protocols via FAO’s Publication Workflow System (PWS) is ongoing. So far, the Field survey guidance for Rhynchophorus ferrugineus, Field survey guidance for Spodoptera frugiperda and Field survey guidance for Bactrocera spp have been published and are available via FAO's document repository. All other protocols, pending final publication, can be accessed on the APP webpage under Training materials here. Once all English versions have been published, they will be republished in FR, PT and AR. The secretariat will also develop training videos on survey protocols for some pests and the APP GIS Hub.

- 3.2. Tablets and field supplies

- The IPPC Secretariat dispatched tablets to all 11 countries in phase one. Nine of these have distributed the tablets and submitted lists of recipient phytosanitary inspectors. The other two countries are Sierra Leone and Morocco which intend to conduct national training first. The countries are already using the APP digital tools to conduct surveillance for major pests; however, Kenya, Mali and Cameroon are the most active users. The IPPC Secretariat procurement of 400 tablets for the countries in phase two is in the advanced stage of inspection prior to shipment.

- Field survey supplies such as pheromone lures, insecticide strips and fruit fly traps for Phase One countries are currently being delivered, through FAO country offices, which will in turn hand them over to the NPPOs.

- 4. APP staff support and governance

- 4.1. APP staff support

- At the IPPC Secretariat, Avetik Nersisyan- Senior Agricultural Officer, oversees APP activities. IPPC Secretariat held interviews on 1 and 2 September 2025 to recruit an APP Support Specialist to support finance and budgeting, replacing Tommaso Teti and Marko Benovic who left the secretariat. Other secretariat staff supporting APP are Arop Deng, Descartes Koumba, Levon Rukavishnikov, Tanja Lahti, Anita Tibasaaga and Alessandra Falcucci, a GIS Specialist, supporting the mapping and mobile application work. The team meets weekly to discuss programme updates and review plans.

- 4.2. Governance and funding

- The current global coordination of APP is organized around the APP’s Coordination Group, Technical Working Group and Communication Working Group (OCG, TWG and CWG), which support the secretariat in implementing APP.

- As recommended by CPM-19, the Secretariat developed governance options and Terms of Reference for an APP International Steering Committee. The CPM Bureau reviewed these at its June meeting but deferred a final decision until a new IPPC Secretary is appointed.

- The IPPC Secretariat developed a detailed two-year APP action plan (2025-2026) outlining the activities of the programme and published it on the IPPC website.

- In March, the United Kingdom of Great Britain and Northern Ireland, through the International Biosecurity Programme provided ~USD 1.2 million (£ 950 000) for APP implementation for two years. Additional funding of USD 600 000 until 2027 is from the European Commission. At CPM-19, FAO Director-General QU Dongyu announced FAO's additional allocation of USD 500 000 in its Programme of Work and Budget for 2026-27 to support the IPPC's work on APP and ePhyto.  This was reconfirmed during FAO Conference in July 2025.

- In March 2025, on the sidelines of CPM-19, the IPPC Secretariat invited African countries, APP donors and partners to a side meeting to discuss APP implementation. The African Union Inter-African Phytosanitary Council (AU-IAPSC) urged a more active role in APP implementation, decision-making and advocacy. Countries requested support in resource mobilization for APP implementation, noting that APP is a unique and relevant programme, but funding is a big issue. The meeting proposed identifying a champion to promote the programme or highlighting a country with notable progress.

- The IPPC Secretariat also created an APP Multidonor Trust Fund (MDTF) for contributions from donors and contracting parties.

- In August 2025, the IPPC Secretariat held a successful meeting with the leadership of the United Kingdom’s International Biosecurity Programme (IBSP) to discuss progress of APP implementation and future opportunities for funding.

- 5. APP integration with FAO and other IPPC activities

- The Secretariat is liaising with the Digital FAO and Agro-informatics Division (CSI) to support the Geographic Information System (GIS) component of APP, including developing field survey maps, managing user accounts in software programmes by Esri and sharing existing FAO mapping layers in APP country maps. CSI provides technical support when needed and jointly supervises the APP GIS specialist with the IPPC Secretariat.

- The Secretariat has also integrated some IPPC e-learning courses – pest surveillance and National Reporting Obligations from the Plant Health Campus into the APP training programme as they relate to APP’s objectives. Participants in APP training are encouraged to complete these courses. Furthermore, the Pest Outbreak Alert and Response System (POARS) steering group made a presentation during the ToT in South Africa, highlighting the POARS criteria for assessing emerging pests and outlining areas of collaboration with APP.

- Further integration is possible with the IC Team on National Reporting Obligations (NROs), which requested to assess the list of regulated pests identified by countries implementing APP countries and to identify opportunities for pest reporting on IPP, based on data collected by APP countries.

- The IPPC Secretariat has also initiated collaboration with CABI to develop response plans for selected APP priority plant pests in three pilot countries.

6. APP forward planning

- Each of the twenty APP participating countries in the two phases have submitted their APP national implementation plans (2025-2027).

- 7. Communication

- The IPPC Secretariat produced a video giving an overview of APP, intended for NPPOs, RPPOs, current and prospecting donors and national leadership. The video aims to create awareness about the pest problem in Africa and how the IPPC, through APP is contributing to solutions through capacity development for digital pest surveillance. The video is available in English, French, Arabic, Spanish and Russian.

- In 2025, the APP has been mentioned in national, regional and international news media about 60 times, which is a 42 percent increase from mentions last year.

- mentioned in FAO news and African regional media outlets (print, TV, audio) at least 45 times, creating awareness about the IPPC’s support to countries in strengthening their national phytosanitary and pest monitoring capacity.

- Following the launch of ToT of APP phase two, the IPPC and APP were mentioned in over 10 news articles in the region. A continent-wide news release was issued, and social media visibility was greatly enhanced through tailored messaging and collaboration with the NPPO of South Africa.

- In September 2025, the secretariat published a news feature article on APP implementation success in Mali. The article highlights Mali’s commitment to implementing the programme, aligning it with national aspirations and seeking strong partnerships and collaboration for enhanced pest surveillance. The Secretariat will develop more success stories from the countries, with Zimbabwe planned next as well as a planned Question and Answer interview with the Executive Directors of the two Regional Plant Protection Organizations (RPPOs) in Africa.

- For the upcoming national training, the IPPC Secretariat has shared two generic roll-up banners with the countries,  created customized certificates and social media content to promote the workshops  on social media, creating visibility for APP. Countries have also received guidelines to document the workshops e.g. through news articles, photography and inviting the media.

- The APP webpage was updated to include news articles, photo albums, training materials, presentations, APP work plan and reports and revised overview text.

Recommendations

- The SPG is invited to:

provide any recommendations for the effective implementation of Africa Phytosanitary Programme.