update on 2025 activities and work plan for 2026

(Prepared by the IPPC Secretariat)

### Background

- The International Plant Protection Convention establishes several reporting obligations which are the responsibility of the contracting parties to the Convention. Contracting parties should at least report on the following:

- a single Official Contact Point (Art. VIII 2 of the IPPC);

- a description of its official national plant protection organization (Art. IV 4 of the IPPC);

- phytosanitary requirements, restrictions and prohibitions which are currently in force (Art. VII 2b of the IPPC);

- specific points of entry (for consignments of particular plants or plant products required to be imported only through those specific points) (Art. VII 2d of the IPPC);

- lists of regulated pests, using scientific names, which are currently in force (Art. VII 2i of the IPPC);

- pest reporting, i.e. reporting regarding occurrence, outbreak and spread of pests (Art. VIII 1a of the IPPC);

- emergency actions (Art. VII 6 of the IPPC).

- The IC established an IC Team on NROs to provide guidance and technical support on the issues relating to NROs.

- The purpose of this paper is to provide an update on activities related to NROs since the last meeting in April 2025 and to prepare the work plan for 2026.

### Follow up on CPM decisions on NROs

- During the last meeting, the IC team on NROs discussed the IC decisions on the CPM-19 outcomes related to NROs. The IC team on NROs noted the IC recommendation that the activation of the IC Subgroup on NROs being put on hold and recommended to activate it when the allocation agreed by CPM-19 will be available and requested the secretariat to follow up the resource allocation for NROs activities during the IC meeting in May and during the next bureau meeting in June 2025.

- The IC team considered the IC endorsement to include of a new bullet in the “Related official information “section of the “IPPC country page”, as an optional feature, to link to the NPPO system to verify phytosanitary certificates by PC number, QR code, or any other similar information, if an accessible system is available and noted the IC agreement to maintain the process in place for the Official Contact Point (OCP) nomination, without making the provision of the official NPPO stamp mandatory.

- During the April meeting, the IC team agreed to prioritize the activities of NROs workplan for 2025 that are not budget associated and to consider when the resources will be available the activities of Section 2 of the workplan and agreed that if the allocation of resources proposed by CPM-19 is available in short term, an extraordinary meeting of IC team on NROs could be scheduled to prioritise the activities to be implemented.

- The IC team noted the request for a NROs presentation to be developed for the 2025 IPPC Regional Workshop on how to support countries to fulfill their obligations.

- Indeed, several of the actions identified were contingent upon the allocation of resources approved by CPM-19 for these activities.  Implementation of this decision was postponed until the new Secretary of the IPPC takes office. The Bureau agreed that addressing these strategic and budgetary issues should await the appointment of the new Secretary, to determine how they fit within his vision for governance. Consequently, the meeting to discuss the allocation of NROs funding was not scheduled as the new Secretary is expected to effectively start his appointment early October, and the related activities remain on hold.

- In preparation for the 2025 IPPC Regional workshops, a presentation was developed to raise awareness on the NROs and remind the crucial role of the IPPC official contact Point to fulfill the country commitments. Some statistics on the NROs were provided to give an overview of level of reporting and a particular emphasis was placed on reminding the contracting parties of their obligations, and once again stressing that funding for NRO activities remains a key issue.

- Despite the lack of allocated resources for NRO activities, the Secretariat continues to perform basic tasks, including updating contact information on the IPP country profiles and providing support to countries regarding inquiries and questions related to NROs.

### Procedure to verify the actualization of the country’s information

- During the April meeting, the IC team discussed the concern raised by UK about the territories having their dedicated NROs page on the IPP considering that they are part of a contracting party which signed the Convention.

- IC team reminded that according to the IPPC, the NROs commitment are for the contracting parties while recognizing the sensitivity and potential legal concerns associated with this issue requiring case-by-case analysis and requested the secretariat to work on a proposed procedure to adjust the NRO features and to consult the legal office to have more clarification on the ways to address the issue.

- The Secretariat develop a draft written procedures and the outcomes of that discussion are presented in the meeting paper NRO_VM2_03.

### Integration of NROs in APP activities

- During the last meeting, the IC team appreciated the opportunity to integrate NROs as an APP component and to align the APP objectives with NROs, particularly pest reporting. In fact, APP could contribute to analyzing how to efficiently streamline pest reporting, generate pest status with digital tool and notify on the IPP website.

- The IC team noted that the integration of NROs in APP should also include some NROs activities in the APP training programme and consider how the APP implementation could contribute to elaborating the list of Regulated pests of APP beneficiary countries.

- The analysis of the NROs for APP beneficiary countries presented in the meeting paper NRO_VM2_04.

- Moreover, in the framework of the implementation the e-learning courses on Surveillance and on NROs are strongly promoted as part of the NRO activities approved for 2025. In fact, participants to the APP national trainings in Kenya and Cameroon on January 2025 as well as the Train the trainers’ workshop for APP phase 2 countries in South Africa (June 2025) were requested to complete the two eLearning’ courses before the trainings. This allowed around 200 plant health officers who completed these courses and APP countries are regularly invited to include the IPPC Plant Health campus as part of their national training plan.

### 2026 NROs work plan

- Considering that resource allocation for NROs activities is not yet confirmed the, the proposed 2026 work plan includes several key activities, such as activating the IC Subgroup on NROs, revising the NROs guide, providing targeted support to IPPC Contact Points and IPP editors to streamline reporting obligations, and enhancing the IPP platform.

- The activities approved one year ago in the 2025 work plan were not implemented and the workplan for next year be updated with expectation that the necessary resources will be secured. Below is the list of proposed activities for IC Team approval and that will be integrated in the 2026 work plan.

- Activate the IC Subgroup on NROs

- Display a user-friendly pest report on new system / platform

- Draft the 2026 annual NROs report

- Support IPPC Contact Points and IPP editors

- Organize NROs global training workshop

- Revision of NROs guide

- Promote the e-learning course national reporting obligations

- The IC Team is invited to:

- note the update on NROs activities

- discuss NROs activities implemented in 2025.

- review and approve the proposed activities for the work plan for 2026 presented in paragraph 19.

- request the Secretariat to develop the NROs paper for the IC November meeting based on the outcomes of the October meeting