TPDP virtual meeting October 2025

Work programme 2025-2026

Review of the status of draft Diagnostic Protocols (DPs)

(Updated: 2025-07-25)

| Topic N. | Current Title | Priority | Discipline Lead | Referee | Status | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| 2006-028 | Tephritidae: Identification of immature stages of fruit flies of economic importance by molecular techniques | 1 | Juliet GOLDSMITH | David OUVRARD | Draft DP under development | Secretariat to share the documents on the scope with the TPDP -> see document 06_TPDP_Tel_2024 (done) Presented to the 2024 TPDP meeting in Yokohama. Next steps: - Expert consultation June 2025: Call for authors: authors currently working on the draft. No estimated time for EC. July 2025: referee changed to David. No updates on the development of the DP.Norman: The Lead Author has communicated with drafting team. Still in stage of drafting. |
| 2018-025 | Citrus leprosis virus | 1 | Andrew APPIAH |  | Draft DP under development | Draft DPs back to Secretariat: 01 February 2024 Draft DPs for expert consultation: 05 February – 01 March 2024* (*one month of expert consultation) Draft DPs revision based on expert consultation: 04-18 March 2024 Draft DPs to editor: 19 March – 02 April 2024 Draft DPs revision based on editor’s final review: 03 April 19 April 2024 TPDP revision and approval (e-decision or virtual meeting) – tight deadline: 30 April or 02 May 2024 SC e-decision for approval for consultation period (final deadline): 01 June 2024 First draft exists, but not yet ready, need to follow up with – not ready for EC For 2025 TPDP face to face meeting (1st draft ready, but some hiccups with some authors, and thus will hand pick an expert June 2025: Vessela to be contacted by Andrew to share updates July 2025: Vessela communicated that there is no first draft ready. Next virology expert to be appointed as referee. |
| 2018-030 | Psyllid vectors of Candidatus Liberibacter solanacearum | 1 | Norman BARR | Juliet GOLDSMITH | Draft DP under development | Next step”: expert consultation Follow up with lead author (probably to consultation period in January 2025, to discuss in detail at the next face to face meeting) Deadline to drafting group: 1 June 2024 Progressing well, not likely to be ready by beginning of august. First draft likely after F2F meeting. Progressing. June 2025: First draft available, illustrations are missing. July 2025 (update provided by David O., the lead author): multi species protocol with no methods available for morphology. More illustrations need to be added to ease ID: pictures to be taken. There have been developments, first draft available in few months. The goal is to submit it for EC and then TPDP will revise it. Norman: Authors returned comments on draft DP to Lead Author in June 2025. The protocol is nearly ready for EC. Not sure workload is appropriate to complete EC and be included in April 2026 Consultation. The above protocols will require a lot of attention during this period. But if not, should be ready for January 2027. |
| 2019-003 | Microcyclus ulei | 1 | Sietse VAN DER LINDE | Adrian DINSDALE | Topic added to the List of topics (drafting group incomplete) | Drafting group formed at the 2023 TPDP meeting Next step: follow up with the authors and draft the DP The IPPC secretariat will follow up with the DP drafting group to inform about the situation. Target next F2F meeting 2025 Robert Taylor:as interim primary contact point for this draft until new discipline lead June 2025: Robert to follow up with the authors, no draft for the next f2f meeting. July 2025: to get in touch with the lead author. Sietse and Adrian new DL and Referee. |
| 2019-010 | Pyricularia oryzae (syn. Magnaporthe oryzae) on Triticum spp. | 1 | Adrian DINSDALE | Sietse VAN DER LINDE | Draft DP under development | Next step: draft the DP Follow up with lead author, there is no draft, drafting group unresponsive – consider finding a new lead author, but check with the current group first. Geraldine can suggest an expert if needed. There is a DP drafting group. It needs to follow up with the authors. The IPPC secretariat will follow up with the DP drafting group to inform about the situation. Target next F2F meeting 2025 Geraldine – interim focal point Call for DP authors in November 2024 June 2025: Part of the protocol is already drafted. The new author will need to be contacted. July 2025: Molecular part is drafted by Renault. Kerry to be involved. Adrian and Sietse new DL and Referee. |
| 2019-011 | Revision of DP 5 (Phyllosticta citricarpa (McAlpine)) Aa | 1 | Adrian DINSDALE | Robert TAYLOR | Pending status | Proposal for revision of DP 05: Phyllosticta citricarpa presented to the TPDP meeting in Yokohama. (see document 22_TPDP_2024_Oct) SC May 2025 approved the termination of the pending status. June 2025: DP drafting group authors are committed July 2025: Adrian new DL, Sietse to stay as an author. Rob to stay as the referee. |
| 2021-001 | Revision of DP 03: Trogoderma granarium Everts | 1 | Norman BARR | David OUVRARD Juliet GOLDSMITH | Draft DP under development | Next step: To expert consultation Draft is not ready for expert consultation, Norman will try to encourage the group. Norman indicated (via email) that the draft would be ready by Northen hemisphere summer of 2024 for EC No draft yet – follow up, to try to get it by August June 2025: To check in with lead author. Not available for the f2f July 2025: In June 2025 confirmed that lead author cannot continue as lead for DP. Other authors did not reply to DL’s email. Action: Can IPPC SC reach out to members and see if still interested in role. We may need to ask Ian Marsh to be lead if still interested in the protocol or we need to make another call for authors. |
| 2021-016 | Spodoptera frugiperda (Fall Armyworm) | 1 | Juliet GOLDSMITH | Norman BARR | Draft under development | Drafting group formed at the 2023 TPDP meeting Next step: follow up with the authors and draft the DP done. DP drafting group contacted and committed. Draft promised by early august by authors. Lead author is not reachable. Secretariat to try to follow up with the lead author. Diego (Columbia). Follow-up done; author is online again. F2F meeting in 2025? June 2025: Lead author to still provide a first draft but he’s not reactive. Julia (RUSSIA), author of the drafting group, is not available anymore and that delayed the drafting. July 2025: Juliet contacted Diego, but there was no draft available. Some sections to be completed, especially the morphological ID. Juliet and Jim to revise the other sections. |
| 2021-017 | Drosophila suzukii (Diptera: Drosophilidae) | 1 | Norman BARR | Juliet GOLDSMITH | Draft DP under development | Good draft, needs last review Next steps: To expert consultation Norman via email: draft to be sent to the secretariat end of July 2024 Draft ready for EC. Currently in review by referee. To be sent to the secretariat end of July 2024 Presented to the 2024 TPDP meeting in Yokohama. Expert consultation in May 2025. June 2025: To assess if we receive any major comments from EC July 2025: EC comments being addressed. Next version expected in August 2025. Possible to submit for referee check in Nov 2025, the TPDP e-decision in Dec 2025, and version to editor in January 2026. |
| 2021-025 | Tomato brown rugose fruit virus | 1 | Andrew APPIAH | Géraldine ANTHOINE, | Draft DP under development | Next steps: Follow up with the drafting group and produce a draft DP No draft, Vessela to discuss the plan with DP drafting group: try to produce a draft by 1 June Tentative for the 2025 TPDP face to face meeting June 2025: To Andrew to get updates from Vessela. July 2025: TPDP revised during the face to face meeting in Angers |
| 2018-032 | Acidovorax avenae subsp. citrulli | 2 | Robert TAYLOR | Géraldine ANTHOINE | Draft DP under development | Draft in progress, not seen yet, third author disappeared. Kohei Osaki, Agriculture, Forestry and Fisheries Research Council, Japan has been accepted as another co-author for this protocol. The group is now working on a draft. Unlikely protocol will be ready for face to face meeting in Japan. Tentative for the 2025 TPDP face to face meeting June 2025: New author onboard, not sure if a draft will be provided in time for the f2f meeting. July 2025: meeting organized, first draft almost ready, likely by the end of 2025. To undergo EC (to be opened early 2026). TPDP to revise at the 2026 face to face meeting. |
| 2019-006 | Amaranthus palmeri | 2 | Vijayasankar RAMAN | Juliet GOLDSMITH | Draft DP under development | No draft, Norman to follow up with Colette Next steps: Follow up with the drafting group and produce a draft DP Authors requested more time to perform diagnostic assessments before drafting methods. Protocol not ready for face to face in Japan. IPPC secretariat will follow up with the authors and inform about the new DL. June 2025: Initial draft ready, needs to be revised by DL and referee July 2025: revised at the 2025 face to face meeting. |
| 2019-007 | Solanum rostratum | 2 | Vijayasankar RAMAN | Géraldine ANTHOINE | Draft DP under development | No draft, Norman to reach out Next steps: Follow up with the drafting group and produce a draft DP Authors generated a first outline for draft that requires additional information and then DL review before presenting to EC or TPDP. Protocol not ready for face to face in Japan. IPPC secretariat will follow up with the authors and inform about the new DL. June 2025: Initial draft ready, needs to be revised by DL and referee July 2025: Vijay to be contacted |
| 2021-014 | Dickeya spp. on Solanum tuberosum | 2 | Robert TAYLOR | Géraldine ANTHOINE | Draft DP under development | First draft, needs revision Next step: To expert consultation There is an updated EPPO protocol, take into account the updated version – if needed Have received a draft. Needs to be edited into IPPC format but all the technical information is included. Could consider for expert consultation A draft could be presented at the face to face meeting. Presented to the 2024 TPDP meeting in Yokohama. July 2025: revised by the TPDP, CC in Jan 2026. |
| 2018-015 | Cronartium comandrae Peck | 4 | Sietse VAN DER LINDE | Géraldine ANTHOINE | Draft DP under development | First draft reviewed by referees; second draft need an extra expert. TPDP agreed with Yasmin to contact further authors if needed Next step: to finalize draft for expert consultation. Last update: DL consulted with the lead author for the and they have reached out to a few other North American SMEs without much success to review the DP, so they will proceed with what the two-author team has drafted if no responses are received one last time. Possibly ready by early summer to have it reviewed by the referee before entering the Expert Consultation. DL has the draft, but have not reviewed yet. Planning to review to submit by mid-August. Presented to the 2024 TPDP meeting in Yokohama. Next steps: - Expert consultation June 2025: Next expert consultation, new version available, new diagram July 2025: Sietse new DL. For EC in Nov 2025 |
| 2023-009 | High-throughput sequencing identification of pure culture of phytopathogenic regulated bacteria isolated from plants | 2 | Mr. Robert TAYLOR (NZ, 2023-11) | Adrian DINSDALE Sietse VAN DER LINDE | Topic added to the List of topics | Already met with the Lead author. Under progress. June 2025: Draft in June, the sections of this DP might be different than the other ones, the group might need to review it. Update by Yazmin by the end of June if there is something to be discussed at the f2f. July 2025: Rob as the new DL, Adrian as the referee. Target to have the first draft: end of 2025 to go for EC early 2026. |
| 2023-010 | Alopecurus myosuroides | 3 | Vijayasankar RAMAN (US, 2023-10) | Mme. Géraldine ANTHOINE (FR, 2023-10) Dr. Norman BARR (US, 2023-10) | Topic added to the List of topics | Authors to be selected at the TPDP meeting in Yokohama (see documents 23_TPDP_2024_Oct and 24_TPDP_2024_Oct) IPPC secretariat will follow up with the authors and inform about the new DL. June 2025: Progress ongoing, initial draft ready but some sections are incomplete. New subspecies discovered. Work in progress. July 2025: get updates from Vijay |
| 2023-013 | Bactrocera zonata and Bactrocera correcta | 2 | Dr. Norman BARR (US, 2023-10) Ms. Juliet GOLDSMITH (SR, 2023-10) | Mme. Géraldine ANTHOINE (FR, 2023-10) | Topic added to the List of topics | Topic is being merged with B. zonata. A draft version is expected by August 30 for EC. Presented to the 2024 TPDP meeting in Yokohama Expert consultation in May 2025. July 2025: EC comments and Editor comments on EC submission being addressed. Expect revision in September. Possible to submit for referee check in Nov 2025, the TPDP e-decision in Dec 2025, and version to editor in January 2026. |
| 2023-016 | Bactrocera tsuneonis and Bactrocera minax | 2 | Dr. Norman BARR (US, 2023-10) | David Ouvrard | Topic added to the List of topics | Very early stage. June 2025: The drafting team is working on the first draft. July 2025: In early July, lead author provided a draft to discipline lead but is still waiting some minor edits from team. Waiting for update for version to prepare for EC. Not sure workload is appropriate to complete EC and be included in April 2026 Consultation. The above protocols will require a lot of attention during this period. But if not, should be ready for January 2027. |
| 2023-026 | Avocado sun blotch viroid | 1 | Andrew APPIAH (GH, 2023-10) |  | Topic added to the List of topics | Meeting has been held with the Lead author to develop timelines for drafting the DP. Draft DP being developed. June 2025: Good progress, but no full first draft. One of the co-authors is not active. July 2025: full draft is ready for EC in 2025. New virology expert to be the new Referee. Geraldine to be the interim Referee in between. |
| 2023-029 | Thaumatotibia leucotreta | 1 | Ms. Juliet GOLDSMITH (SR, 2023-10) | Dr. Norman BARR (US, 2023-10) David OUVRARD | Topic added to the List of topics | Early stages June 2025: Good progress, first draft. Now is back with the authors. Might be available for the f2f meeting. July 2025: revised at the 2025 f2f meeting. EC in 2025. |

Recommendation

- The TPDP is invited to

review the entire workplan and ask the discipline leads for an update on each topic.