TPDP work plan 2025-2026

Expert consultation period 1 November – 1 December 2025

DPs:

- Acidovorax avenae subsp. Citrulli, priority 2***

- Tomato brown rugose fruit virus, priority 1

- Amaranthus palmeri, priority 2

- Cronartium comandrae Peck, priority 4 → draft already available

- Avocado sun blotch viroid, priority 1 → draft already available***

- Thumatotibia leucotreta, priority 1

Deadlines:

Option 1: editing after TPDP revision

- Revised DP to be sent back to secretariat: by 15 October 2025

- Expert consultation period: 1 November – 1 December 2025

- Revision based on EC comments: 1 January –1 February 2026

- Revision by TPDP (virtual meeting or e-decision): 2 – 16 February 2026

- Editing: March - April 2026 (editor available for 1 DP in March and 3 DPs in April)

- Revision based on editor’s feedback: April-May 2026

- DP to be presented to SC: 1 June 2026

- Country consultation: July 2026

Option 2: editing before TPDP revision

- Revised DP to be sent back to secretariat: by 15 October 2025

- Expert consultation period: 1 November – 1 December 2025

- Revision based on EC comments: 1 – 20 December

- Editing: January 2026 (editor available for 2 DPs)

- Revision based on editor’s feedback: 2 – 23 February 2026

- Revision by TPDP (virtual meeting or e-decision): March 2026

- DP to be presented to SC: 1 June 2026

- Country consultation: July 2026

*** Acidovorax avenae subsp. Citrulli and Avocado sun blotch viroid are planned for Expert Consultation period either in November 2025 or January 2026, however they will not undergo Country Consultation in 2025 (and therefore will not be edited) as the TPDP will revise them at the 2026 face to face meeting.

Expert consultation period 15 January – 27 February 2026 (flexible)

DPs:

- Acidovorax avenae subsp. Citrulli, priority 2

- High-throughput sequencing identification of pure culture of phytopathogenic regulated bacteria isolated from plants, priority 2

- Bactrocera tsuneonis and Bactrocera minax, priority 2 (tentative)

Deadlines:

- Revised DP to be sent back to secretariat: by 5 January 2025

- Expert consultation period: 15 January – 27 February

- Revision based on EC comments: 1 January –1 February 2026

- Revision by TPDP: Face to face meeting in September 2026

- Editing: October 2026

- Country consultation: January 2027

Country Consultation 30 January – 30 April 2026

DPs:

- Dickeya spp., priority 2

Deadlines:

- Revised DP to be sent back to secretariat: by 15 October 2025

- Editing: 19 – 31 October

- Revision based on editor’s feedback: 1 – 24 November

- SC to revise and approve for CC (e-decision): 1 – 15 December 2025

- Revision based on possible comments from SC: 10 – 20 December 2025

Country Consultation 01 July – 30 September 2026

DPs:

- Drosophila suzukii, priority 1

- Bactrocera zonata and correcta, priority 2

Deadlines:

- Revised DP to be sent back to secretariat: by 1 December 2025

- Revision by TPDP (virtual meeting or e-decision): 2 – 20 December 2026

- Editing: already performed, maybe a quick revision in January 2026 (editor available for 3 weeks)

- SC to revise and approve for CC (e-decision): February – March 2026

- Revision based on possible comments from SC: April 2026

Tentative (see above):

- Tomato brown rugose fruit virus, priority 1

- Amaranthus palmeri, priority 2

- Cronartium comandrae Peck, priority 4

- Thumatotibia leucotreta, priority 1

Tentative DPs for 2026 TPDP face to face meeting (21-25 September, venue TBD):

- Acidovorax avenae subsp. Citrulli, priority 2

- Avocado sun blotch viroid, priority 1 → draft already available

- Bactrocera tsuneonis and Bactrocera minax, priority 2

- High-throughput sequencing identification of pure culture of phytopathogenic regulated bacteria isolated from plants, priority 2

*Drafts to be sent to secretariat by 15 July 2026

Instructions to Authors

From draft report:

agreed to have a blank template as annex 1 to be of easier reference for authors;

agreed to include the information from the “template” (current appendix 1) into a new appendix;

agreed that Geraldine and Juliet would work on appendix 1;

agreed that the David would work on the current appendix 2;

agreed that this new appendix be developed/updated to expand on RPA, HTS, sequencing and other methods;

asked Robert TAYLOR to draft this appendix 3 by end of 2025 and then be circulated to the TPDP (via e-forum or TPDP virtual meeting);

agreed to include guidance to the authors to “avoid personal communication. However, if necessary, to be direct (i.e. direct from the primary source to the DP drafting group), recent and relevant” [to decide where to include – suggested on “inclusion of a test”];

agreed to include the statement that IPPC DPs are not scientific reviews;

agreed to add instructions requesting the DP authors to provide a rationale for inclusion/exclusion of a test to be shared with the discipline lead and thus, with the TPDP.

agreed that for permissions, to follow “the line” of first the DP drafting group, then the discipline lead and then the IPPC secretariat.

invited Adrian and Sietse to update and revise current appendix 8 by end of 2025;

Responsibilities:

- Appendix 1: Geraldine and Juliet by end of 2025

- Appendix 2: David by March 2026

- Appendix 3 (RPA, HTS, sequencing, etc): Rob by end of 2025

- Appendix 8: Adrian and Sietse by end of 2025

Notes

Editor’s availability:

- October (last 2 weeks)

- November (1.5 weeks, before SC)

- January (3 weeks)

- March (1 week - assuming CPM is in March)

- April (3.5 weeks)

- May (1 week, before SC)

- June (2 weeks)