2026 Strategic Work Plan: Standard Setting Unit

(Prepared by the IPPC Secretariat)

Background

This paper presents a tentative work plan for 2026 of the work of the Standard Setting Unit (SSU). The current SSU staff and their main areas of work are presented in the linked chart.

A tentative work plan for the 2025 year was presented to the Standards Committee (SC) in November 2024 in the paper “17_SC_2024_Nov” and is available on the International Phytosanitary Portal (IPP).

A tentative work plan for 2026 is provided in Annex 1. A tentative calendar is provided in Annex 2. After the November 2025 SC meeting, this document and its annexes will be made available on the IPP (https://www.ippc.int/en/core-activities/standards-setting/).

Besides providing support to the Standards Committee (SC) and its direct activities (e.g. discussion papers, calls, e-decisions and meetings organization), the SSU also provides support to the overall management and activities of the IPPC Technical Panels, some CPM focus groups, liaison with FAO translation services, and of the IPPC Secretariat. Moreover, since 2025 the SSU had the overall coordination of the IPPC Regional Workshops.

The SSU also provides support to other IPPC subsidiary bodies (e.g. CPM Bureau and Strategic Planning Group (SPG)) and continues to be the focal points for the activities related to two development agenda items in the IPPC Strategic Framework 2020-2030:

- commodity and pathways standards; and

- laboratory diagnostic networking.

The SSU members also represent IPPC Secretariat in different meetings organized by FAO and partners.

It is planned that the 2026 SC meetings will take place physically in FAO HQ, and the dates will be updated when communicated by FAO.

SC May: May 2026

SC-7: May 2026

SC November: November 2026

Pending decisions to be taken by the SC, the following draft ISPMs and documents are planned to be presented for adoption and consultation periods for 2026.

- Adoption by CPM-20 (2026):

It is foreseen that the following draft ISPMs will be presented to the CPM-20 (09-13 March 2026) for adoption:

- Tentative 2 draft ISPMs:

Draft revision of ISPM 26 (Establishment and maintenance of pest free areas for fruit flies (Tephritidae)) (2021-010);

Draft annex Field inspection (2021-018) to ISPM 23 (Guidelines for inspection);

- Tentative 2 draft PTs:

Draft annex to ISPM 28: Irradiation treatment for Paracoccus marginatus (2023-034); and

Draft annex to ISPM 28: Irradiation treatment for Planococcus lilacinus (2023-035);

2 diagnostic protocols adopted by the SC to CPM-20 for noting:

DP 35 Meloidogyne mali; and

DP 36 Genus Pospiviroid.

Consultation period on draft Specifications (01 July to 30 September, 90 days)

Revision of ISPM 3 Guidelines for the export, shipment, import and release of biological control agents and other beneficial organisms

Protocols (DPs) consultation period January 2026: (30 January – 03 May. 90 days consultation period):

Dickeya spp. (2021-014);

Drosophila suzukii (2021-017); and

Bactrocera zonata and correcta (2021-013).

Diagnostic Protocol Notification Period 2026 (1 July – 15 August):

Dickeya spp. (2021-014);

Drosophila suzukii (2021-017); and

Bactrocera zonata and correcta (2021-013).

First consultation 2026 (01 July- 30 September. 90 days consultation period):

- Draft ISPMs:

Draft commodity standards International movement of Citrus fruit (2023-019) to ISPM 46;

Draft commodity standards International movement of seeds of Phaseolus vulgaris (2023-008);

Draft commodity standards International movement of Malus domestica fruit for consumption (2023-024); and

Safe provision of humanitarian aid in the phytosanitary context (2021-020).

Draft Diagnostic Protocols (DPs): (01 July- 30 September. 90 days consultation period):

Tomato brown rugose fruit virus (2021-025);

Thaumatotibia leucotreta (2023-029);

Amaranthus palmeri (2019-006); and

Cronartium comandrae Peck (2018-015)

Second consultation 2026 (01 July – 30 September. 90 days consultation period):

- 2 Draft ISPMs:

Draft commodity standards International movement of fresh Musa spp. fruit (2023-028) to ISPM 46; and

Draft commodity standards International movement of fresh Colocasia esculenta for consumption (2023-023).

- Draft PT:

Draft annex to ISPM 28: Irradiation treatment for Pseudococcus baliteus (2023-033).

Planned meetings for 2026:

SC May, SC-7 and SC November,

Technical panels:

Technical Panel on Diagnostic Protocols (TPDP): Tentative 21-25 September 2026

Technical Panel on Phytosanitary Treatments (TPPT): Tentative 05-09 October Rome, Italy 2026

Technical Panel for the Glossary (TPG): Tentative December 2026

Technical Panel on Commodity Standards (TPCS): Tentative: September/October 2026

Expert Working Groups (EWG)

Safe provision of humanitarian aid in the phytosanitary context (2021-020), priority 1. 2-6 March 2026 in Nadi, Republic of Fiji. More information on the call for EWG members: https://www.ippc.int/en/calls/2025-10-ippc-call-for-experts-expert-working-group-safe-provision-of-humanitarian-aid-in-the-phytosanitary-context/;

Draft specification: Annex Remote audits (2023-031) to ISPM 47 (Audit in the phytosanitary context), priority 1;

Draft specification: Revision of ISPM 12 (Phytosanitary certificates) (2023-020), priority 1;

Revision of the draft reorganized pest risk analysis ISPM (2023-037), priority 1 (Specification09 76); -; and

Draft specification: Revision of ISPM 23 (Guidelines for inspection) (2023-014), priority 2.

CPM Focus Groups

CPM Focus Group on Laboratory Diagnostic Network (tentative: 2nd quarter / June 2026); and

CPM Focus Group on Sea Containers.

Other meetings:

Webinar on Safe provisions of food and other humanitarian aid (tentative for February 2026);

Side session during CPM-20 (2026): IPPC commodity standards;

Side session during CPM-20 (2026): Sea Containers;

Tentative side session CPM-20 (2026): APP;

Tentative: scientific session during CPM-20 (2026): Safe provisions of humanitarian aid in phytosanitary context; and

Tentative Workshop, third quarter 2026: Sea Containers

Overall IPPC 2026 Regional Workshops coordination:

Delivery of at least 3 Regional Workshops

Latin America: End August 2026. Lima, Peru (Comunidad Andina).

Africa: 25-28 August 2026. Libreville, Gabon

Near East and North African

Asia:

Caribbean: TBD

Europe and Central Asia: First week of September 2026 in Uzbekistan

Southwest Pacific: 17–21 August 2026

Other activities:

IPPC ongoing Call for Topics: Standards and Implementation

Publication of adopted ISPMs (all FAO languages)

Ink amendments to adopted ISPMs (all FAO languages)

Language review groups (LRGs, in Ar, Ch, Ru and Sp)

Calls for experts, call for DP authors, calls for discussion papers and information material

E-Decisions

Expert Consultation on Draft Diagnostic Protocols

Webinars (Call for Topics)

OCS training

- Workshops with Technical Panels

SSU awareness raising and training materials:

Videos on Standards Committee and Technical Panels

Video on Safe provision of food and other humanitarian aid to prevent the introduction of plant pests during an emergency situation

Liaison: On behalf of the IPPC, some SSU staff conduct liaison activities with the following organizations (and others):

- World Trade Organization – Sanitary and Phytosanitary (SPS) Committee and Secretariat

Convention on Biological Diversity (CBD) and Biological Diversity Conventions Group

International Atomic Energy Agency (IAEA) - FAO Joint Division

World Food Programme (WFP)

United Nations Economic Commission for Europe (UNECE)

World Organization for Animal Health (WOAH)

Biological Weapons Convention (BWC) of the UN

World Custom Organization (WCO)

International Maritime Organization (IMO)

Phytosanitary Measures Research Group (PMRG)

International Forestry Quarantine Research Group (IFQRG)

Recommendations to the Standards Committee (SC):

The SC is invited to:

- note the tentative list of activities for 2026;

note the tentative dates for the SC meetings in 2026;

discuss any potential EWGs for 2026; and

provide comments and suggestions.

Annex 1

IPPC Secretariat - Standard Setting Unit (SSU)

2026 work plan – TENTATIVE

(Updated on 2025-10-17)

Standards Committee (SC) May 2026 (XX to XX May 2026):

Tentative points for agenda:

- Draft ISPMs for approval for first consultation:

- draft ISPMs:

- Draft annex International movement of Citrus fruit (2023-019) to ISPM 46

- Draft annex International movement of seeds of Phaseolus vulgaris (2023-008)

- Draft annex International movement of Malus domestica fruit for consumption (2023-024)

- Safe provision of humanitarian aid in the phytosanitary context (2021-020)

- Draft Specifications for approval for consultation

- Revision of ISPM 3 Guidelines for the export, shipment, import and release of biological control agents and other beneficial organisms

- Summary of e-decisions

- Review of technical panels (from May 2025 to April 2026):

- Technical Panel for the Glossary (TPG)

- Technical Panel on Phytosanitary Treatments (TPPT)

- Technical Panel on Diagnostic Protocols (TPDP)

- Technical Panel on Commodity Standards (TPCS)

- Review of the List of Topics for IPPC standards (LOT)

- CPM-20 follow-ups

- Standards committee

- SC & IC update and enhancing synergies

Standards Committee working group (SC-7) May 2026 (XX to XX May 2026), draft ISPMs:

- Draft ISPMs for approval for second consultation:

- draft ISPMs:

- Draft annex International movement of fresh Musa spp. fruit (2023-028) to ISPM 46

- Draft annex International movement of fresh Colocasia esculenta for consumption (2023-023)

Standards Committee November 2026 (XX to XX November 2026, FAO HQ):

Tentative points for agenda:

- Draft ISPMs for approval for recommendation to the Commission on Phytosanitary Measures (CPM-20) for adoption:

- Draft annex International movement of fresh Musa spp. fruit (2023-028) to ISPM 46

- Draft annex International movement of fresh Colocasia esculenta for consumption (2023-023)

- Issues raised from the first consultation period

- Approval of draft specifications

- Summary of E-decisions

- SC / IC interactions

- Updates

Annex 2

STANDARD SETTING 2026 - TENTATIVE CALENDAR

For updates, please check the IPPC calendar at https://www.ippc.int/en/year/calendar/

| Quarter | Date | Activity | Venue | Category |
| --- | --- | --- | --- | --- |
| 1st | 05 January – 20 Feb 2026 | DP notification period |  | Standard Setting |
|  | 30 January – 03 May 2026 | Consultation period on draft diagnostic protocols | - | Standard Setting |
|  | XX March 2026 | Objection period deadline for adoption of ISPMs closure (“three weeks prior CPM”) | - | Governance |
|  | 01 March 2026 | Posting draft ISPMs to SC May | - | Governance |
|  | 2-6 March 2026 | EWG o Safe provision of humanitarian aid in the phytosanitary context (2021-020) | Nadi, Fiji | Standard Setting |
|  | XX-XX March/April 2026 | CPM-20 | FAO HQ | Governance |
| 2nd | 12 May 2026 | International Day of Plant Health | FAO HQ - RED ROOM |  |
|  | XX-XX May 2026 | Standards Committee May (SC) | FAO HQ | Governance |
|  | XX-XX May 2026 | Standards Committee working group (SC-7) | FAO HQ | Governance |
|  | Mid-June 2026 | Focus Group on Laboratory Diagnostic Networking | TBD | Governance |
| 3rd | July | 1 EWG (see priorities 1): Annex to ISPM 47: Remote audits Revision of ISPM 12 | TBD | Standard Setting |
|  | 01 July – 30 September 2026 | Consultation period on draft ISPMs and CPM Recommendations | - | Consultation period |
|  | 01 July – 30 September 2026 | Consultation period on draft specifications | - | Consultation period |
|  | XX -XX August 2026 | IPPC Regional Workshops | (various) | Expert input / Capacity development |
|  | XX Aug – XX September 2026 | IPPC Regional Workshops | (various) | Expert input / Capacity development |
|  | 21-25 September 2026 | TPDP Face-to-face meeting | TBC | Standard Setting |
| 4th | XX-XX October 2026 | CPM Bureau | XXX |  |
|  | XX-XX October 2026 | Tentative - Strategic Planning Group | XXX | Other |
|  | XX-XX October 2026 | TPPT Face-to-face meeting | FAO HQ | Standard Setting |
|  | XX-XX November 2026 | Standards Committee (SC) | FAO HQ: GERMAN ROOM | Governance |
|  | September / October 2026 | TPCS Face-to-face meeting | TBC | Standard Setting |
|  | December | EWG (see priorities 1): Annex to ISPM 47: Remote audits Revision of ISPM 12 | TBD | Standard Setting |
|  | XX-XX December 2026 | TPG | - | Standard Setting |

2025 SSU Work Plan: https://www.ippc.int/en/publications/94186/

See calendar on IPP: https://www.ippc.int/year/calendar/

Annexes to ISPM 46 (Commodity-specific standards for phytosanitary measures)

For more information, please visit the webpage: https://www.ippc.int/en/core-activities/external-cooperation/