## Slide 1
ACTION PLAN
MERLE B. PALACPAC
GERALD GLENN F. PANGANIBAN

## Slide 2
No. | Action | Anticipated results | Deadline/milestone | Responsible
1 | Set-up an internal system to manage information exchange in the BPI | A more effective information exchange mechanism in the agency | 3rd week of July | Merle and Glenn
2 | Upload available information to the IPP and APPPC | Updated country information | 3rd week of July 2011 | Merle and Glenn
3 | Train the existing BPI SPS Focal (from Crop Protection, Crop Production, Research, Quarantine) Group on the use of IPP and APPPC | Increased awareness among NPPO officials on the importance of using the IPP | 1st week on September 2011 | Merle and Glenn
4 | Assign FG members for each subject that requires information in the IPP and APPPC | Definition of functions and responsibilities | 2nd week of September 2011 | Merle and Glenn
5 | Compile information to be published on the IPP Portal and APPPC | To meet obligation and to share information | 2nd week of October 2011 | Merle and Glenn and BPI Colleagues

## Slide 3
6 | Screen information to be uploaded | To verify the information for correctness to be provided in the website | 3rd week of October 2011 | Merle and Glenn and BPI Colleagues
7 | Train the Plant Quarantine Officers all over the Philippines to use the IPP and APPPC website | To increase awareness and participation in the use of IPP portal | 1st week of November 2011 | Merle and Glenn
8 | Orient the Stakeholders of the BPI on the use of the IPP and APPPC (government, academe and industry) | To increase awareness and use of the IPP and APPPC | January 2012 | Merle and Glenn and BPI Colleagues
9 | Continuous and regular updating of information on the IPP | Current and relevant information uploaded in the IPP | July 2011-Future | Merle, Glenn and BPI colleagues

## Slide 4
How do I upload again???
Where do I start? Hmmm….
MARAMING SALAMAT!