Report of the 2nd Meeting of Expert Working Group on

Phytosanitary Capacity Development

23-27 May 2011

Montego Bay, Jamaica

Report of the Expert Working Group on

Phytosanitary Capacity Development

23 –27 May 2011

Montego Bay, Jamaica

- Opening of the Meeting

1. Mrs. Ana Peralta, IPPC, Implementing Officer opened the meeting.  She welcomed and thanked the participants for coming to the second meeting of the Expert Working group on Capacity Development. Mr. Dalton Hastings, Montego Bay Export Complex Manager in the  Ministry of Agriculture, welcomed the members and presented small gift baskets containing Jamaican condiments and fruits to members.

II. Purpose of the meeting

2. The IPPC Implementation Officer, Ms. Ana Peralta, outlined the objectives of the meeting. She explained that at CPM-5 it was agreed that an Expert Working Group (EWG) would be created to review and refine the Phytosanitary Capacity Development Operational Plan and to assist the Secretariat with developing national phytosanitary capacity. The EWG would also consider the need for a permanent subsidiary body to deal with phytosanitary capacity development and assist the CPM in providing advice on  advocacy and resource mobilization related to capacity development.

III. Adoption of Agenda

3. The agenda as appended (Appendix 1) was adopted after two (2) modifications. The IICA representative Ms. Ana Marisa Cordero will give a presentation about project STDF 108 and distance learning  facilities in IICA. The second modification to the agenda was related to developments with the IDB/USDA/IICA PRA Pilot Project for Central America.

4, Full introductions were made with each member giving a brief description of their background.  A list of participants and their contact details are appended (Appendix 2)

IV. Election of Rapporteur and Chair

5. The group selected Mr. Craig Fedchock, from the United States of America as the        chairperson of the meeting and Mrs. Shelia Harvey from Jamaica, as rapporteur.

V. Update from the IPPC Secretariat

6. The representatives of the IPPC Secretariat provided information on all related activities of the Secretariat , relevant for the work of the EWG and in particular the developments and works undertaken for databases, coordination of projects and other capacity development activities.

Agenda Item 1: Work Plan and Strategies

1. The new version of the document “Work plan and Budgets” was presented and revised .The amended version is attached as Appendix 3. The revised work plan and budget will be  presented to the June 2011 Bureau meeting.

2. The SWOT analysis for Subsidiary Bodies was discussed at length by the group. It was updated to reflect other strengths and weakness from the discussion. Based on that discussion, the EWG decided that the best course of action is to recommend to CPM, through SPTA and the Bureau, the establishment of a Subsidiary Body on Capacity Development  (SBCD). The STDF will be providing additional comments to this analysis.

3. As a consequence of the preceding SWOT analysis, the EWG, concluded that one  function of the SBCD would be guiding the identification of standards implementation difficulties.

4. The EWG prepared an explanatory paper in support of the establishment of the SBCD, including a draft TOR and accompanying rules of procedure. See Appendix 4.

Agenda Item 2: Information and Decisions

1. The group discussed the terms of reference for an award on Capacity Development and agreed upon the criteria. See Appendix 5.

2. The group discussed the establishment of a Roster of Experts and agreed to its implementation, following a review of the database by the EWG. Main issues discussed included the structure of the database, confidentiality issues, need for a search function according to expertise, including designation for special categories, such as PCE facilitators, need for uploading documents, disclaimer for the quality of the data contained and for the competence of the experts contained in the database.

3. The Secretariat presented a demo concept of the  projects and activities database that was warmly received by the EWG. Considerable discussion took place on the need for further resourcing of this activity. A provisional figure of 200.000 U$S was identified as needed for development and mainstreaming of the application in the IPP.

Agenda Item 3: Advocacy and Resource Mobilization

1. The Chair informed the EWG about two active initiatives concerning advocacy and resource mobilization. These include the drafting of an IPPC strategy for resource mobilization  and the commitment by the USDA to provide assistance to the IPPC for the development of a communication strategy.

The EWG then discussed 2 tables, one related to advocacy entitled “Human resources and organizational development: Ideas and concepts (Promotion of IPPC issues in curricula of Universities, Centers of Excellence and other institutions at national and international level to build capacities). See Appendix 6.

The second table concerns “Capacity Development Resource Mobilization: Concepts and proposals as a contribution to the overall IPPC Resource Mobilization Strategy“ . The EWG provided inputs to the table on the eight (8) strategic areas. See Appendix 7.

2. It was agreed that additional tables would be rationalized and reviewed post meeting. The inputs for these tables (“Develop tools and guidelines for preparing National Phytosanitary Action Plans”  and “Advocacy Materials: ISPMs - Proposed Concepts and messages for discussion”) would be revisited at a later date.

Agenda Item 4: Capacity Development Projects

1. Project STDF/PG/350

An overview of the project was provided by the Secretariat.

The Secretariat expressed appreciation to the hard work of the EWG in preparation of this and to the expressions of support provided by contracting parties and institutions. The discussion on the implementation of the project ensued with the following agreements:

- Review the logframe and budget and resubmit to STDF.

- To issue a call for availability of technical resources (manuals, SOPs , training materials and electronic media). The IPPC will prepare a call to be directed to NPPOs and RPPOs. A template call for technical resources will be prepared by the Secretariat for use by EWG members, to approach relevant institutions in their regions for provision of technical resources where they exist. The call will be open for a duration of 2 weeks with a possible extension of two additional weeks.

- Compare available material to a priority listing of technical resources produced by the EWG and prioritize the manuals, SOPs and training kits to be developed under the project. The prioritization includes consideration of 5 topics proposed by the SC. See Appendix 8.

- The EWG discussed various options for the coordination of the activities of the project and agreed  that given the diversity of the technical resources to be produced, multiple collaborators would be contracted.

- Based on the prioritization of the technical resources to be produced, and in consultation with the EWG, possible collaborators will be identified to  develop the technical resources.

- The in kind contribution of the IPPC will be to manage the project and ensure its completion. In addition to  IPPC staff resources, FAO-OEKP will provide advice and address IPR related issues, as appropriate, concerning use of third parties material.

- The EWG will be the forum to review and assess technical resources provided under the project and  to provide general oversight.

- The EWG will closely coordinate and consult with IPPC subsidiary bodies and related groups in the production of technical resources under the project .

- The project will provide support to an IDB /USDSA/IICA proposal for training in PRA in Central America, in the form of the updating of  IPPC-PRA training course and associated E-learning module. The IAGPRA shall be invited to assist in the updating of the material of the PRA course. IICA will be the principal collaborator to develop the associated E-learning module. The project will allocate 50.000 U$S for this activity.

2. IRSS

The Secretariat provided an overview of the project and explained that the EU provided support to partially fund the project in 2011. There is no guarantee from the EU for further support. An update on IRSS activities was provided which included a report on the briefing of the Standards Committee and the subsequent agreement to collaborate on the identification of potential challenges by contracting parties for the implementation of ISPMs 4 and 6.

In addition the Secretariat reported the ongoing activity of the conduct of PCEs globally and informed that anonymous data could be a valuable source of information for IRSS.

Furthermore, the Secretariat indicated that the work on the project and activities database and the development of the expert roster was ongoing and will be central to the establishment of the Help Desk. It was also  informed that the RPPOs had been consulted on a draft IRSS questionnaire in 2009 and 2010 and no feedback was received.

The Secretariat invited the EWG members to advise on the modalities for concrete contributions to the implementation of the IRSS program.

It was agreed:

- The EWG will provide comments on the IRSS questionnaire prepared under the project. The EWG member from the Asia region agreed to contact the APPPC requesting that it shares its experience in a similar activity conducted biannually for its member countries, with a view to improving the questionnaire.

- That the EWG will be the steward of the IRRS programme as there is a direct link between the review and support system and the implementation mandate of the EWG. The EWG considered that the EWG is the natural fit for providing oversight to the IRSS program development.

- A six months case study on “Implementation challenges of ISPM :6 ” could be conducted under the IRSS program, on a regional basis, with support of the regional representation in the EWG. The EWG will draft TORs for the conduct of the case study and agreed that this work could complement the future review of this ISPM.

- The EWG would assist in the implementation of the Help Desk in an advisory capacity, in particular when addressing regional concerns.

It was proposed by the EWG to maintain dialogue with the SC using the E-dialogue mechanism.

3. PCE

The Secretariat introduced a perspective on a training of trainers program for discussion and an indicative program for phytosanitary consultants was provided. See Appendix 9 . The phytosanitary consultants course program concerns the development of a cadre of phytosanitary expertise for potential use in projects. A more specific program for training of facilitators of the PCE tool was also discussed. The EWG agreed that these courses are highly relevant and that the phytosanitary consultants course could targeted to a wider audience. It was agreed that this training could be packaged with the PCE facilitators training and submitted as a single project to the STDF as a potential donor.

Discussions also centered on the possibility for charging fees for this type of course or for sub-contracting the course to an external technical institution.  Further consultations of this topic with regard to funding will be needed, in particular with the Bureau.

4. E-learning

E-learning was discussed in terms of collaboration with the IDB/IICA/USDA on a PRA training course in Central America.  The EWG supported the involvement of the IPPC in the project and the collaboration with IICA in the development of an E-learning module for the IPPC PRA training course.  Further areas of collaboration with IICA on E-learning concerning future possibilities on training were discussed. The IPPC Secretariat and IICA will continue dialogue in this regard.

Agenda Item 5: Any Other Matters

1. IICA

The IICA representative Ms. Ana Marisa Cordero thanked the group for inviting IICA to the meeting and noted that they are looking forward to greater coordination and collaboration with the IPPC. IICA informed the EWG of their assistance provided to the IPPC program of work, in particular the assistance given to the organization of the regional workshops on draft ISPMs in 2010.  IICA expressed their interest in continuing and expanding their collaboration with the IPPC, in particular for distance learning, E-learning and the sharing of technical resources.

The Secretariat thanked the representative for their support in the organization of last year’s workshops and for the support provided to the project proposal for technical resources presented to the STDF.  The Secretariat informed the EWG that it did not have funding for the 2011 round of regional workshops in LAC. It was discussed that a possible area for collaboration with IICA could be a trial run using videoconferencing technology to host the regional workshop on draft ISPMs in either the Caribbean or Latin American regions or both; the idea was well-received.

Further discussions with be held between the Secretariat and IICA over the coming weeks to further formalize the level of cooperation.

VI.	Agenda for the next meeting.

7.  The EWG agreed to follow the same structure as for this year’s meeting.

VII.	Date and venue of the next Meeting.

8. The EWG provisionally agreed that the face-to-face meeting shall be held during the month of May in order to consider inputs from and to consult with, the SC, SPTA and Bureau on a timely basis.  Expressions of interest for hosting the next EWG were received from the Asia and the Southwest Pacific Regions.  The EWG asked those regions to explore the possibility for hosting the meeting and to inform the Secretariat as soon as possible of a decision for the purpose of planning and resource allocation.  The IPPC Secretariat will follow up with the regions and inform the EWG of the final decision in due course.

VIII.	Review and Adoption of the report.

9. The EWG thanked the representatives of Jamaica and in particular Mrs. Sheila Harvey for the excellent arrangements performed for the meeting and the kindness of the treatment received by the participants .

The report was adopted.

Appendix 1

Expert Working Group 2nd Meeting

Updated May 2011

EXPERT WORKING GROUP MEETING

Phytosanitary Capacity Development

Second Meeting

Montego Bay, Jamaica, 23 - 27 May 2011

Agenda

- Opening of the Meeting.

- Purpose of the Meeting.

- Adoption of the Agenda.

- Election of the Rapporteur and Chair.

- Update from IPPC Secretariat

Agenda Item 1:Work Plan and Strategies

1.1 Consideration and preparation of a new version of the IPPC Capacity Development work plan for SPTA 2011.

1.2 Completion of the SWOT analysis for Subsidiary Bodies. Recommendations on the future structure and mode of operation of the EWG including the possibility of forming a subsidiary body on capacity building.

1.3 Preparation of the final version of TOR, rules or procedure and an explanatory paper for the proposed Subsidiary Body on Phytosanitary Development

Agenda Item 2: Information and Decisions

2.1 Finalize the proposals for an IPPC award to Capacity Development and a Roster of Expert, to send them to the SPTA.  Proposal prepared for SPTA include: database shell, guidelines on CV format and recommendation to link with IRSS Help Desk and other mechanism

2.2 Review the work of all databases related to Capacity Development. Note the feedback and decisions from CPM-6. Discuss on how to develop and maintain databases in the future.

Agenda Item 3: Advocacy and Resource Mobilization

3.1 Discussions on completion of the tables “Human resources and organizational development: Ideas and concepts and “Capacity Development Resource Mobilization: Concepts and proposals as a contribution to the overall IPPC Resource Mobilization Strategy“

3.2 Decisions on future procedures for tables “Develop tools and guidelines for preparing National Phytosanitary Action Plans”  and “Advocacy Materials: ISPMs - Proposed Concepts and messages for discussion”

Agenda Item 4: Capacity Development Projects

4.1  Project STDF/PG/350

Discuss on how to implement the approved project STDF/PG/350. Consideration of implementation activities and STDF- IPPC Secretariat concerns.

4.2 IRSS

Consider the activities developed under the IRSS.  Discuss the support to the IRSS by the EWG in relation to capacity development.

4.3 PCE

Training of trainers program and PCE facilitators programs

4.4 PRA E- learning

IDB/USDA/IICA PRA Pilot Project for Central America.

Agenda Item 5: Any Other Matters

5.1 IICA

Presentation by IICA (Inter-American Institute for Cooperation on Agriculture) on project STDF 108 and distance learning  facilities in IICA

VI.	Agenda for the next meeting.

VII.	Date and venue of the next Meeting.

VIII.	Review and Adoption of the report.

Appendix 2

EXPERT WORKING GROUP ON PHYTOSANITARY CAPACITY BUILDING

(Montego Bay, Jamaica, 23-27 May, 2011)

Participant List

|  | Region | Name, mailing, address, telephone | E- mail address |
| --- | --- | --- | --- |
| 1 | Asia | Mr. Ho Haw LENG Deputy Director Crop Protection and Plant Quarantine Division Department of Agriculture 3rd Floor, Wisma Tani Jalan Sultan Salahuddin 50632 Kaula Lumpur, MALAYSIA Tel: 6 03 20301417 (Off. line) 017 67 588 76 (mobile phone) Fax: 6 03 26977164 | hawlengho@doa.gov.my hawlengho@yahoo.com |
| 2 | Europe | Mr. Corné VAN ALPHEN Ministry of Economic Affairs, Agriculture and Innovation Department of Agriculture, Agribusiness and Fisheries NETHERLANDS Phone: +31 (0)70 - 3785552 Fax: +31 (0)70 - 3786123 | c.a.m.van.alphen@minlnv.nl |
| 3 | Latin America & Caribbean | Ms. Shelia HARVEY Chief Plant Quarantine, Produce Officer Ministry of Agriculture and Fisheries 193 Old Hope Rd. Kingston 6 JAMAICA Tel: 1-876-977-0637 1-876-977-6401 Fax:1-876-977-6992 | syharvey@moa.gov.jm sheharv@yahoo.com |
| 4 | Near East | Ms. Nagat MUBARAK EL TAYEB Plant Protection Directorate (PPD) Ministry of Agriculture (MoA) P.O.Box 14 Khartoum North SUDAN Tel: +249 185 33 74 42 +249 185 33 94 23 | neltayb@yahoo.com |
| 5 | North America | Mr. Craig FEDCHOCK U.S Department of Agriculture, Animal and Plant Health Inspection Service USA Tel: +202 257 2715 Fax:+301 734 3396 | craig.fedchock@aphis.usda.gov |
| 6 | Pacific | Dr. Jan Bart Rossel International Plant Health Office of the Chief Plant Protection Officer Biosecurity Services Group Department of Agriculture, Fisheries and Forestry GPO Box 858, Canberra City ACT 260 Ph: 02 6272 5056 Mob: 0408625413 Fax: 02 6272 5835 | Bart.Rossel@daff.gov.au |

Others

|  | Role | Name, mailing, address, telephone | Email address |
| --- | --- | --- | --- |
| 7 | Observes | Ms. Ana Marisa Cordero IICA Sanidad Agropecuaria e Inocuidad de Alimentos Tel. 506 22160222 ext. 0403 | ana.cordero@iica.int |
| 8 | Observers | Mrs Kenza Le Mentec, PhD Economic Affairs Officer Standards and Trade Development Facility (STDF) Agriculture and Commodities Division World Trade Organisation Rue de Lausanne, 154 CH 1211 Genève 21, Suisse Tel: + 41 22 739 65 38 Fax: + 41 22 739 57 60 | Kenza.LeMentec@wto.org |
| 9 | IPPC Secretariat | Ms. Ana PERALTA Implementation Officer International Plant Protection Convention (IPPC), Food and Agriculture Organization of the United Nations, Room B703, Viale delle Terme di Caracalla, 00153, Rome, Italy. Tel: +39-06-5705-5322 Fax: +39-06-5705-4819 | ana.peralta@fao.org |
| 10 | IPPC Secretariat | Mr. Orlando SOSA Agricultural Officer International Plant Protection Convention (IPPC), Food and Agriculture Organization of the United Nations, Room B703, Viale delle Terme di Caracalla, 00153, Rome, Italy. Tel: +39-06-5705-53613 Fax: +39-06-5705-4819 | orlando.sosa@fao.org |
| 11 | IPPC Secretariat | Ms. Johanna GARDESTEN Agricultural Office International Plant Protection Convention (IPPC), Food and Agriculture Organization of the United Nations, Room B703, Viale delle Terme di Caracalla, 00153, Rome, Italy. Tel: +39-06-5705-53678 Fax: +39-06-5705-4819 | johanna.gardesten@fao.org |

Appendix 3. Revised work plan and budget

| IPPC Capacity Development Work Plans - Strategic Area 1: National PS Planning and Management |  | Review | Development Activity | Ongoing Activity |
| --- | --- | --- | --- | --- |

| Activity No: | Output | Sub-Activities | Lead Entity: | Supported by: | Funding Options | Notes/Comments | Estimated Duration | Estimated cost $US 000 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ST1/O1/A1.1 | 1. Fit-for-purpose tools and processes for phytosanitary systems(PS) planning. | Identifying and review tools for PS capacity evaluation | IPPC Sec | NPPO, RPPO | IPPC Sec, FAO-TCP, Donors | Donors includes bilateral, multilateral, regional and sub-regional funded projects | One month in year 1. | 20 |
| ST1/O1/A1.2 |  | Develop new or revise existing fit for purpose tools | IPPC Sec | NPPO, RPPO | IPPC Sec, RPPO, FAO-TCP, Donors | Other activities are depended on tools being revised or developed | Six months over year 1and 2. | 200 |
| ST1/01/A1.3 |  | Development of IPPC core training materials | IPPC | NPPO, RPPO | IPPC Sec, RPPO, FAO-TCP, Donors | Other activities are depended on tools being revised or developed | Through out year 3. | 300 |
| ST1/O2/A2.1 | 2. Critical compentencies available in the national phytosanitary system to undertake national planning, management and provide leadership to the NPPO. | Regional or national policiy discussions including planning management and leadership on the mandate of the NPPO | RPPO | NPPO, IPPC Sec and others | RPPO, National, IPPC Sec, FAO-TCP, Donors, others |  | On-going activity during year 1-6 | 900 |
| ST1/O2/A2.2 |  | Training (project management, proposal writing, administrative and management, leadership, staff training programme development ) | NPPO | IPPC Sec, RPPO, STDF | National, IPPC Sec, RPPO, FAO-TCP, Donors, others | National activities based on needs and priorities | On-going activity during year 1-6 | 3500 |
| ST1/O2/A2.3 |  | Undertake baseline study on planning and management requirements in the national phytosanitary system including stakeholder engagement | NPPO | RPPO, IPPC Sec. | National, IPPC Sec, RPPO, FAO-TCP, Donors | National activities based on needs and priorities | Two months in year 1. | 2500 |
| ST1/O2/A2.4 |  | Develop mentoring opportunities to support national phytosanitary planning and management | NPPO, | RPPO, IPPC Sec, STDF, others | National, IPPC Sec, RPPO, FAO-TCP, Donors |  | Four months per year in year 5 and 6. | 160 |
| ST1/O3/A3.1 | 3. Best practice for national phytosanitary action plans developed. | Develop national phytosanitary action plans and HR plans and succession planing . | NPPO | RPPO, Otherrs,IPPC Sec. | National, IPPC Sec, RPPO, FAO-TCP, Donors | National activities based on needs and priorities | Three months per year in year 2 and 3. | 6000 |
| ST1/O3/A3.2 |  | Develop national emergency response plans for regulated pests that incorporate regional Emergency response plans, where they exist. | NPPO | RPPO, Others, IPPC Sec. | National, IPPC Sec, RPPO, FAO-TCP, Donors | National activities based on needs and priorities | Four months in year 3 and 4. | 1500 |
|  |  |  |  |  |  |  | Total cost | 15080 |

| IPPC Capacity Development Work Plans - Strategic Area 2: Participation in Standard Setting |  | Review | Development Activity | Ongoing Activity |
| --- | --- | --- | --- | --- |

| Activity No: | Output | Sub-activity: | Lead Entity: | Supported by: | Funding Options | Notes/Comments | Estimated Duration | Estimated cost $US |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ST2/O1/A1.1 | 1.Enhanced regional coordination of inputs into the standard setting process | RPPO coordinate discussion fora/workshops on draft standards, new topics, specifications and CPM preparation | RPPO | IPPC Sec, RECs, Other integration organizations | FAO, Donors, IPPC Sec | 1 month per year over 6 years | One month per year over 6 years. | 5 |
| ST2/O1/A1.2 |  | Training RPPOs staff and regional experts on participation in all stages of the standard setting process (e.g. topics, specifications, representation on the SC and in other technical bodes, draft standards) | IPPC Sec | RPPOs, Experts | IPPC Sec, FAO, Donors, RPPOs | 3 months per year over 6 years | Three months per year over 6 years.(This cost is supplementary to the regular cost of meeetings) | 6 |
| ST2/O1/A1.3 |  | Training RPPOs staff and regional experts to facilitate/ coordinate standard setting meetings | IPPC Sec | RPPOs, Experts, RPPOs | IPPC Sec, FAO, Donors, RPPOs | 2 days per year for 6 years (1 month total). Linked to budgeted workshops that the IPPC holds. This expenditure represents an additional days cost to the normal 5 day meeting | Two days per year for 6 years(1 month total) | 15 |
| ST2/O2/A2.1 | 2.Enhanced involvement of stakeholders at national level | Hold multi-stakeholder discussion, fora, training, workshops, web on draft ISPMs, new topics, specifications, CPM, etc | NPPO | RPPOs, RECs Other organizations, IPPC Sec, FAO | Donors, NPPO, RPPO, FAO, IPPC Sec | 1 months per year over 6 years | 1 months per year over 6 years. | 5 |
| ST2/O3/A3. 1 | 3.Quality of contracting parties participation improved | Hold orientation programme for new CPM delegates | IPPC Sec | RPPOs, FAO | Donors, NPPO, RPPO, FAO, IPPC Sec | 1 day per year over 6 years. A meeting of a few hours prior to start of the CPM. | 1 day per year over 6 years. | 10 |
| ST2/O3/A3.2 |  | Peer/coaching/mentoring for new members of subsidiary bodies of the IPPC | IPPC Sec | RPPOs, FAO | Donors, NPPO, RPPO, FAO, IPPC Sec | 1 month per year over 6 years. A meeting of a few hours prior to start of the Subsidiary Body's meeting (e.g. Bureau, SPTA, EWG, TPs, SC etc.) | 1 month per year over 6 years. | 10 |
| ST2/O3/A3.3 |  | Support X participation in EWGs and Technical panels (Max 2 technical standards per year) | IPPC Sec | RPPOs, NPPOs | Donors, NPPO, RPPO, FAO, IPPC Sec | Only done for technical standards for which the members of an EWG or TP need a global view of the topic at hand | 1 month per year over 6 years. | 60 |
| ST2/O3/A3.4 |  | Conduct in depth discussion with all stakeholders, on draft ISPMs | NPPO | RPPOs | Donors, NPPO, RPPO, FAO, IPPC Sec | 8 months over 6 years assuming the IPPC produces 5 standards per year | 8 months over 6 years assuming the IPPC produces 5 standards per year |  |
|  |  | Review of draft standards at national level | NPPO | RPPO, RECs and other organisations |  |  |  | 700 |
|  |  | Review of draft standards at regional level | RPPO | NPPO |  |  |  | 3400 |
| ST2/O3/A3.5 |  | Engage government to comit the human and financial resources for the NPPO to participate in the standard setting process and formalize its commitments using relevant instruments. | NPPO | RPPO, RECs and other organisations | Donors, NPPO, RPPO, FAO, IPPC Sec | 6 days over 6 years - this activity can be combined with other workshops or conducted independently | 6 days over 6 years. |  |
| ST2/O3/A3.6 |  | Monitoring and evaluation | CPM | NPPOs, RPPOs, IPPC Sec, Donors | Donors, NPPO, RPPO, FAO, IPPC Sec |  |  |  |
|  |  | Annual reports |  |  |  | One per year over 6 years. | One per year over 6 years. |  |
|  |  | midterm review |  |  |  | One in the end of year 3. | One in the end of year 3. |  |
|  |  | external evaluation |  |  |  | One in the end of year 6 | One in the end of year 6 |  |
|  |  |  |  |  |  |  | Total | 4206 |

| IPPC Capacity Development Work Plans - Strategic Area 3: Standards Implementation |  | Review | Development Activity | Ongoing Activity |
| --- | --- | --- | --- | --- |

| Activity No: | Output | Sub-activity | Lead Entity: | Supported by: | Funding Optio ns | Notes/ Comments | Estimated Duration | Estimated cost $US 000 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ST3/01/A1 | Enhanced involvement of stakeholders at national level | Identifying implementation issues associated with adopted and draft standards (Approx 5 per year). | NPPO | RPPOs, RECs Other organizations, IPPC Sec, FAO | Donors, NPPO, RPPO, FAO, IPPC Sec | Ongoing, aprox 1 adopted ISPM and 2 specifications per year. | 6 man months per year over 6 years. | 360 |
|  |  | Accompanying draft implementation guidelines with draft standards (Approx 5 per year). | IPPC Sec/Expert | Experts, RPPOs, NPPOs | Donors, NPPO, RPPO, FAO, IPPC Sec | Implementation requirements guideline prepared that goes out with each draft standard sent for country consultation. 12 man months per standard per year. | 12 man months per standard per year. | 3 0.1 0.1 |
|  |  | A. Prepare guideline |  |  |  |  |  |  |
|  |  | B. Circulate / review guideline |  |  |  |  |  |  |
|  |  | C. Distribute guideline at regional workshops |  |  |  |  |  |  |
| ST3/O2/A2 | Improved understanding of implementation requirements of specific standards | Develop manuals; guidelines; factsheets; capacity needs assessment tools for implementing specific standards Implementation of 34 stds @ 2011 | NPPO | NPPO, RPPOs, Donors, IPPC Sec, FAO, Others | NPPO, RPPOs, Donors, IPPC Sec, FAO | 72 months. In total 6 years. Assume materials developed for 6 standards per year Assume ongoing PCE work in year 1 and 4 additional tools over 5 years thereafter | 72 months. In total 6 years Assume materials developed for 6 standards per year Assume ongoing PCE work in year 1 and 4 additional tools over 5 years thereafter | 2250 |
|  |  | Development of new tools for implementation | IPPC/Experts RPPO NPPO | RPPOs, NPPOs |  |  |  | 1250 |
| ST3/O2/A2.1 | Support provided for implementation of priority ISPMs | Training on implementation of ISPMs | RPPO |  | NPPO, RPPOs, Donors, IPPC Sec, FAO-TCP | Estimate 4 months per standard (34 stds @ 2011); Assume a target of 40 developing countries requiring assistance over 6 years; TCP valued at 400K per project. 9 regional workshops For 1 Center of Excellence - development of framework costs approx. 900k | Estimate 4 months per standard (34 stds @ 20119); Assume a target of 40 developing countries requiring assistance over 6 years; TCP valued at 400K per project. 9 regional workshops For 1 Center of Excellence - development of framework costs approx. 900k |  |
|  |  | National level Implementation of 34 stds @ 2011 | Experts,NPPO | RPPO |  |  |  | 16000 |
|  |  | Regional level | RPPO/Experts | IPPC Sec |  |  |  |  |
|  |  | Workshops |  |  |  |  |  |  |
|  |  | Higher level education | RPPO | IPPC Sec, NPPO |  |  |  | 540 |
|  |  | Establishment of centers of excellence |  |  |  |  |  | 900 |
| ST3/O2/A2.2 |  | Establishment of mentoring system for countries to help each other | RPPO | RECs and other organisations, IPPC Sec, NPPOs | NPPOs, RPPOs, RECS AND OTHER ORGANIZATIONSs | 8 months to develop and the programme is ongoing thereafter | 8 months to develop and the programme is ongoing thereafter | 1200 |
| ST3/O2/A2.3 |  | Mobilize resources for implementation of standards | NPPO |  | NPPOs, Donors, STDF, RPPOs, RECS AND OTHER ORGANIZATIONSs, IPPC Sec | Continuous programme and draws on all aspects related in the CD strategy | 72 months |  |
|  |  | Develop advocacy materials | IPPC Sec/FAO | RPPOs, RECs and other organizations, SPTA |  |  | 2 months year 1 | 20 |

|  |  | Advocate and Communicate | NPPO |  |  |  |  | 0 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Develop communication materials | IPPC Sec/FAO | RPPOs, RECS AND OTHER ORGANIZATIONS, SPTA |  |  | 2 months year 1 | 20 |
|  |  | Develop planning tools for specific ISPMs identified by the NPPOs | IPPC Sec/FAO | RPPOs, RECS AND OTHER ORGANIZATIONS |  |  | 2 months year 1 | 20 |
| ST3/O3/A3 | Level of implementation of ISPMs is appropiate for national needs | Develop resource plan | NPPO | RPPOs, RECS AND OTHER ORGANIZATIONS, SPTA |  |  | 2 months year 1 | 20 |
|  |  | Staffing | NPPO |  |  |  |  |  |
|  |  | donor matching | IPPC Sec | RPPOs, RECS AND OTHER ORGANIZATIONSs |  |  |  |  |
|  |  | mentoring (see Activity 2.2) | NPPO | RPPOs, RECS AND OTHER ORGANIZATIONSs, IPPC Sec |  |  |  |  |
|  | Level of implementation of ISPMs is appropriate for national needs | Implement IRSS programme | IPPC Sec | RPPO, NPPO, RECS AND OTHER ORGANIZATIONSs | STDF, WTO, FAO, IPPC | Year 1 to year 3 is development and implementation of the programme | Year 1 to year 3 is development and implementation of the programme Year 4-6, second cycle | 3000 |
|  |  |  |  |  |  |  | Total | 22083.2 |

| IPPC Capacity Development Work Plans - Strategic Area 4: Communication and Coordination |  | Review | Development Activity | Ongoing Activity |
| --- | --- | --- | --- | --- |

| Activity No: | Output | Sub-activity | Lead Entity: | Supported by: | Funding Options | Notes/ Comments | Estimated Duration | Estimated cost $US 000 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ST4/O1/A1 | Information and resources of international, regional and national bodies identified, managed and coordinated. | Establish baseline | IPPC and RPPOs | NPPOs and RPPOs | Donors | 30 days cumultavive in year one. | 30 days cumultative in year one. | 255 |
| ST4/O1/A1.1 |  | Build ICT system accessible to donors and recipients with limited general access | IPPC | NPPOs and RPPOs | Donors | One month in year one. | One month in year one. | 20 |
| ST4/O1/A1.2 |  | Develop and conduct periodic survey of capacity development programs to populate the system | IPPC | NPPOs and RPPOs | Donors | One month per year over 6 years. | One month per year over 6 years. | 30 |
| ST4/O1/A1..3 |  | Train users on system operations. | IPPC | NPPOs and RPPOs | Donors | One month in year one. | One month in year one. | 350 |
| ST4/O2/A2.1 | Methods and pathways for communication used | Establish “help desk” which is empowered to facilitate and maintain partnering between donors and recipients | IPPC | NPPOs and RPPOs | Donors | Costed in the IRSS program | Development during year 1. | On-going activity year 2-6. |  |
| ST4/O2/A2.2 |  | Each successive CPM encourages the use of help desk | CPM | NPPOs and RPPOs | Donors | One week during CPM each year. | One week during CPM each year. |  |
| ST4/O3/A3.2 | Mechanism and synergies for coordination used | Contracting parties or RPPOs reports information to IPPC on ongoing or planned projects in member nations | RPPO | NPPOs and RPPOs | Donors | One month per year over year 2-6. | One month per year over year 2-6. |  |
| ST4/O4/A4.1 | Competencies for resource mobilization and management identified and supported through the national phytosanitary action plan | National networking mechanism established | NPPO | NPPOs and RPPOs | Donors | Initial development activity may require IPPC intervention for providing description of what is required - regional travel | Year one. | 25 |
| ST4/O4/A4.2 |  | National coordination committee ( SPS/biosecurity/trade facilitation , etc) established to engage other ministries/departments in cooperative activities that can benefit plant health efforts | NPPO | NPPOs and RPPOs | Donors | Initial development activity may require IPPC intervention for providing description of what is required - regional travel | Year one. | 25 |
| ST4/O4/A5.1 |  | Develop linkages between and among other regional and other multinational organizations | IPPC/RPPO | NPPOs and RPPOs | Donors | Five donor conferences held on a regional basis at an average cost of $75,000 | Over year 1-6(72 months) | 750 |
|  |  |  |  |  |  |  | Total | 1455 |

| IPPC Capacity Development Work Plans - Strategic Area 5: Pest Information |  | Review | Development Activity | Ongoing Activity |
| --- | --- | --- | --- | --- |

| Activity No: | Output | Sub- activity | Lead Entity: | Supported by: | Funding Options | Notes/ Comments | Estimated Duration | Estimated cost $US 000 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ST5/O1/A1 | Contracting parties updated regulated pest lists and timely report outbreaks of regulated pests. | Gap analysis to determine requirements for surveillance, diagnostics, reference collections, information systems etc. | IPPC | IPPC/RPPO/NPPO and other institutions | Donors |  | Three months year 1. | 350 |
| ST5/O2/A2 | Pest data analysed, especially providing early warning for risk management, market access and risk analysis. | National Planning activities related to surveillance, diagnostics and related activities underpining food security. | NPPOs | IPPC/RPPO/and other institutions | Donors | This is a component frequently integrated into many cooperation projects | Year 1. |  |
| ST5/O/A3.1 |  | Enhancement of surveillance skills through training - especially practical application. | NPPO | RPPOs, IPPC Sec, Technical Assistance providers | Donors | This represents a two year cycle which will include a training workshop (train the trainer), followed by actual surveillance activities culminating in a consolidation workshop. The acitivities are governed by seasonality, and as a result the initial training workshops will need to be held over a six month period. Assuming 80 countries reciving 400.000 each over 2 years. | Year 2-3. | 32000 |
| ST5/O/A3.2 |  | Development of specialized diagnostic support at a regional level. | RPPO | NPPO/IPPC | Donors | Reflected as ongoing over the life of the project. | On-going activity during year 2-6. | 2000 |
| ST5/O/A4.1 |  | Enhancement of diagnostic capability through development of laboratory infrastructure. | NPPO | NPPO/RPPO/IPPC | Donors | Needs determined based on gap analysis and midterm review Assuming 80 countries reciving 500.000 | Developed in the beginning of year 2 and year 4. | 40000 |
| ST5/O/A4.2 |  | Enhancement of diagnostic capability through the provision of diagnostic tools. |  | NPPO/RPPO/IPPC | Donors | This will include taxonomic reference material, electronic or otherwise. | Developed in the beginning of year 2 and year 4. | 200 |
| ST5/O/A4.3 |  | Enhancement of diagnostic capability through development of networking. | IPPC | RPPO/NPPO | Donors | Vision is to establish a network, registers of expertise, etc. | Developed in the beginning of year 2 and year 4. | 1750 |
| ST5/O/A4.4 |  | Enhancement of reference collections and related physical facilities and curation protocols. | NPPO | RPPO/IPPC | Donors | Driven by gap analysis, and revisited periodically | On-going activity in the beginning of year 2 and year 4. | 2000 |
| ST5/O/A4.5 |  | Confirmatory identifications for specimens to assist with reference collections, early warning for risk management, market access and risk analysis | NPPO | RPPO, IPPC | Donors |  | Developed in the beginning of year 2,on-going activity during year 2-6. | 295 |
| ST5/O/A5.1 |  | Create and deploy information systems at national level. Mechanisms created to provide pest information to NPPOs. | NPPO | IPPC/RPPO | Donors |  | Developed during year 1, on-going activity year 2-6. | 480 |
| ST5/O/A5.2 |  | Training in compilation of pest information and management of information systems provided to national actors, including NPPOs. | NPPO | IPPC/RPPO | Donors |  | One month during year 2. | 100 |
| ST5/O/A5.3. |  | Data entry | NPPOs |  | Donors |  | Developed in the end of year 2, on-going activity year 3-6. | 700 |
| ST5/O/A6.1 | Capability to provide plant pest information enhanced. | Training provided in analysis of pest information, preparation of pest reports and issuing of pest alert. | NPPO/RPPO | IPPC | Donors | Dependent on complexity of tasks to be done | Two months in year 3. |  |
| ST5/O1/A7 | . | Pest information analysed; reports and early warnings issued. | NPPOs | IPPC/RPPO/NPPO | Donors |  | On-going activity from end of year 3-year 6. |  |
| ST5/O/A8 |  | Embed IPPC related material in national tertiary and vocational curricula | NPPOs | IPPC/RPPO | Donors |  | Developed in the end of year 3, on-going activity until year 6. |  |
|  |  |  |  |  |  |  | Total | 79875 |

| IPPC Capacity Development Work Plans - Strategic Area 6: Resource Mobilisation (Fundraising) |  | Review | Development Activity | Ongoing Activity |
| --- | --- | --- | --- | --- |

| Activity No: | Output | Sub- activity | Lead Entity: | Supported by: | Funding Options | Notes/ Comments | Estimated Duration | Estimated cost $US 000 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ST6/O1/A1.1 | Enhanced capacity to engage donors at all levels | Donor coordination meetings at all levels | IPPC Sec | NPPO, RPPO | IPPC Sec, Donors |  | On-going activity from year 2-6. | 500 |
| ST6/O1/A1.2 |  | Coordinate and maximise the effectiveness of the funds available from various sources. | STDF, IPPC Sec | NPPO, RPPO, REC’s, Donors | IPPC Sec, RPPO, Trust Funds, Donors |  | On-going activity from year 2-6. | 100 |
| ST6/O1/A1.3 |  | Develop guidelines to be used by NPPOs for engaging donors | IPPC Sec | NPPO, RPPO | IPPC Sec, RPPO, Donors |  | Developed in the beginning of year 3, | 60 |
| ST6/O1/A1.4 |  | Develop recommendations to be used by donors for granting funding support | IPPC Sec | NPPO, RPPO | National, IPPC Sec, RPPO, Donors |  | Developed in the beginning of year 3, | 60 |
| ST6/O1/A1.5 |  | Hire a full-time fundraiser in the IPPC Secretariat | IPPC Sec | NPPO, RPPO, FAO and others | Trust Funds, IPPC Sec, Donors | Staff resource shared with other areas of the IPPC | On-going activity from year 2-6. | 230 |
| ST6/O1/A 1.6 |  | IPPC facilitates meeting with donors (e.g. side meetings at the CPM) | IPPC Sec. | NPPO, RPPO | Trust Fund, IPPC Sec, Donors |  | On-going activity from year 2-6. | 300 |
| ST6/O2/A 2.1 | Enhanced capacity to raise funds from national sources. | Undertake national baseline analysis and determine level of funds required. | NPPO | IPPC Sec, RPPO | National, IPPC Sec, RPPO, FAO-TCP, Donors | National activities will be based on need and cost is considered under ST1 | Two months during year 1. |  |
| ST6/O2/A2.2 |  | Develop a mechanism to ensure sustainability of the operations of an NPPO, including cost sharing /cost-recovery/user-pay models | NPPO | IPPC Sec, RPPO, National stakeholders | National, IPPC Sec, RPPO, National end-user of PS services,Donors | National activities will be based on need and priority and cost is considered under ST1 | On-going activity from year 1- year 6. |  |
| ST6/O2/A2.3 |  | NPPO management develops and pursues appropriate funding level through the national budgetary processes. | NPPO | National stakeholders | IPPC Sec, RPPO, National end-user of PS services,Donors | National activities will be based on need and cost is considered under ST1 | On-going activity from year 1- year 6. |  |
|  |  |  |  |  |  |  | Total | 1250 |

| IPPC Capacity Development Work Plans - Strategic Area 7: Advocacy |  | Review | Development Activity | Ongoing Activity |
| --- | --- | --- | --- | --- |

| Activity No: | Output | Sub- activity | Lead Entity: | Supported by: | Funding Options | Notes/ Comments | Estimated Duration | Estimated cost $US 000 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ST7/O1/A1.1 | Enhanced involvement of the NPPO in formulating relevant national policies | Develop training materials; deliver training; evaluate training impact on policy | Multinational organizations | FAO. IPPC Sec., RPPO/RECS AND OTHER ORGANIZATIONS | IFAD, FAO, WB, NPPO | 6 months | 6 months. Developed in the end of year 1-beginning of year 2. | 1200 |
| ST7/O1/A1.2 |  | National and regional mentoring | NPPO/RPPO | IPPC Sec | NPPO/RPPO | 72 months; ongoing, Costing only staff required by IPPC Sec and RPPO | On-going activity from year 1-6. | 80 |
| ST7/O1/A1.3 |  | Conduct study of policy documents for possible impact on the phytosanitary system | RPPO/RECS AND OTHER ORGANIZATIONSs | FAO | RPPO, RECS AND OTHER ORGANIZATIONS, IFAD, FAO, WB, NPPO | 3 months | Developed during 3 months in year 1. | 60 |
| ST7/O2/A2.2 | Enhanced NPPO capacity to promote their own capacity development needs | Develop guidelines for phytosanitary capacity building based on Paris Principles | IPPC Sec | FAO, NPPOs, RPPOs | STDF,FAO,WB | 1 month | Developed during month year 1. | 60 |
| ST7/O3/A3.1 | NPPOs have better capacity to develop and implement communication/advocacy strategies | Develop training materials | IPPC Sec | FAO | FAO,WB,IFAD, | 6 months; Assuming 20 countries per year | 6 months, in the end of year 1-beginning of year 2. | 160 |
|  |  | Deliver training | RPPOs, RECS AND OTHER ORGANIZATIONS | Expert/NPPO/IPPC Sec |  |  | 6 months, in the end of year 1-beginning of year 2. | 420 |
|  |  | Evaluate training impact | NPPO | Expert |  |  | 6 months, in the end of year 1-beginning of year 2. | 720 |
| ST7/O3/A3.2 |  | Enhance communication skills of NPPO managers to convince senior officials of the government, includiong policy makers | NPPO | RPPO/RECS AND OTHER ORGANIZATIONS/FAO | NPPO,FAO,WB,RPPO,RECS AND OTHER ORGANIZATIONS, | 2 months per year; assume 20 countries conduct 2 national workshops per year | 2 months per year; assume 20 countries conduct 2 national workshops per year | 960 |
| ST7/O4/A4.1 | Enhanced capacity to coordinate national stakeholders | Engage industry and other private sector stakeholders and NGOs | NPPO | RPPO/RECS AND OTHER ORGANIZATIONS | Private Sector, NPPO, RPPO, RECS AND OTHER ORGANIZATIONS | 3 months over 6 years; assume 20 countries conduct 2 national workshops per year | 3 months over 6 years; assume 20 countries conduct 2 national workshops per year | 960 |
| ST7/O4/A4.2 |  | Formalize regular linkages – bridge building with customs, immigration, trade groups and private sector | NPPO | RECS AND OTHER ORGANIZATIONS | Private Sector, NPPO, RECS AND OTHER ORGANIZATIONS | 3 months over 6 years; assume 20 countries conduct 2 national workshops per year | 3 months over 6 years; assume 20 countries conduct 2 national workshops per year | 960 |
| ST7/O4/A4.3 |  | Encourage public private partnership with users of the phytosanitary service | NPPO | RECS AND OTHER ORGANIZATIONS | Private Sector, NPPO, RECS AND OTHER ORGANIZATIONS | 3 months over 6 years; assume 20 countries conduct 2 national workshops per year | 3 months over 6 years; assume 20 countries conduct 2 national workshops per year | 960 |
| ST7/O4/A4.4 |  | Develop and promote case studies of private sector/public sector collaboration to achieve phytosanitary / bio security / market access objectives | STDF, IPPC Sec and others | RECS AND OTHER ORGANIZATIONSs, RPPO, FAO, IPPC Sec | NPPO,FAO,WB,RPPO,RECS AND OTHER ORGANIZATIONS, STDF | 24 months at year 5 and 6; Assume a sample of 120 countries over 6 years = 12 country study. | 24 months at year 5 and 6; Assume a sample of 120 countries over 6 years = 12 country study. | 500 |
| ST7/O5/A5.1 | Enhanced capacity of regional bodies to influence, assist, and promote national policy | Create fora for interchange of experiences and skills on phytosanitary advocacy among regional organizations | RPPO/IPPC Sec | FAO, RECS AND OTHER ORGANIZATIONSs | STDF, NPPO, WB, RECS AND OTHER ORGANIZATIONS, RPPO | 2 meetings per year; 3 months total | 2 meetings per year; 3 months total | 720 |
| ST7/O5/A5.2 |  | Utilize other international fora (e.g. APEC) to advocate for national phytosanitary systems | RPPO/RECS AND OTHER ORGANIZATIONSs | IPPC Sec | STDF, NPPO, WB, RECS AND OTHER ORGANIZATIONS, RPPO | 1 Meeting every quarter; 4 per year; 6 months total; Assuming 10 delegates from 9 RPPOs and the IPPC Sec attending 4 meetings per year | 1 Meeting every quarter; 4 per year; 6 months total; Assuming 10 delegates from 9 RPPOs and the IPPC Sec attending 4 meetings per year | 1200 |
| ST7/O5/A5.3 |  | Conduct baseline study of RPPO relevance | IPPC Sec | NPPO, RECS AND OTHER ORGANIZATIONSs | FAO, NPPO, RECS AND OTHER ORGANIZATIONSs | 3 months | 3 months, review year 1. | 60 |
| ST7/O6/A6.1 | Enhanced the capacity of contracting parties to generate, access and retrieve data and information on advocacy | Develop tools for evidence based advocacy (economic analysis, cost/benefit, etc) | STDF, FAO | NPPOs | RPPO, RECS AND OTHER ORGANIZATIONS, IFAD, FAO, WB, NPPO | Ongoing |  |  |
| ST7/O6/A6.2 |  | Review of current phytosanitary advocacy and communication documentation | NPPO, IPPC Sec, Other organizations | RPPOs, RECS AND OTHER ORGANIZATIONSs | IPPC, FAO, WB, STDF, NPPO, RECS AND OTHER ORGANIZATIONS, RPPO | 3 months | 3 months, developed in year1. | 60 |
|  |  |  |  |  |  |  | Total | 9060 |

| IPPC Capacity Development Work Plans - Strategic Area 8: Monitoring and Evaluation |  | Review | Development Activity | Ongoing Activity |
| --- | --- | --- | --- | --- |

| Activity No: | Output | Sub- activity | Lead Entity: | Supported by: | Funding Options | Notes/ Comments | Estimated Duration | Estimated cost $US 000 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ST8/O1/A1.1 | Monitoring and evaluation tools developed and used throughout the implementation of the global phytosanitary strategy at all levels. | Identify existence and use of M&E tools by contracting parties and others. | IPPC Sec | NPPOs | Donors |  | Developed in one month year 1. | 60 |
| ST8/O1/A1.2 |  | M&E tools developed or adapted, | IPPC Sec | NPPOs and other institutions | Donors |  | Developed in two months year 1. | 80 |
|  |  | Develop and populate a depository tool. | IPPC Sec | NPPOs and other institutions | Donors |  |  | 100 |
| ST8/O1/A1.3 |  | Training in use of M&E tools (including use of the depository) | IPPC Sec |  | Donors |  | Developed in one month in the end of year 1, On-going activity one month year 2. | 400 |
| ST8/O1/A1.4 |  |  |  |  |  |  |  |  |
| ST8/O1/A1.5 |  | IPPC secretariat (and others) promote use of M&E and depository tools. | IPPC Sec, NPPOs and other instiututions |  | Donors |  | Development in the middle of first year; |  |
|  |  |  |  |  |  |  | On-going activity in one month in year 2. |  |

| ST8/O1/A1.7 |  | Adjust M&E tool when necessary | IPPC Sec, NPPOs |  | Donors, Interested NGOs |  | Ongoing activity from year 2 until year 6. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ST8/O2/A2.1 | Periodic review and assessment being conducted | Partner with leading institutions to conduct reviews and assessments. | IPPC Sec |  | Donors |  | Development in the beginning of the first year, | 3000 |
|  |  |  |  |  |  |  | On-going activity until year 6. |  |
| ST8/O3/A3 | Continual process of improvement (adaptive management) | Share review results as appropriate and implement corrective measures. | IPPC |  | Donors | Ongoing | Initially development in year 4. | 250 |
|  |  |  |  |  |  |  | On-going activity until year 6. |  |
| ST8/O4/A4 | Mechanisms for recognition of good practices performed by countries | Criteria for awarding an IPPC recognition for excellence. | IPPC |  | Donors |  | Development in year 2. |  |
|  |  |  |  |  |  |  | On-going activity until year 6. |  |
| ST8/O5/A5 | The global strategy updated every 6 years | Mid term and final reviews conducted for activities in each ST | IPPC Sec, NPPOs | RPPOs | Donors |  | Updated every 6 year. |  |
|  |  |  |  |  |  |  | Total | 3890 |

Appendix 4. Recommendations on the future structure and mode of operation of the expert working group including the possibility of forming a subsidiary body on capacity building.

The EWG analyzed this theme included in its terms of reference and performed a SWOT analysis based in the comparison of the establishment of a new subsidiary body vs. an expert working group.

The SWOT analysis is showed below, followed by an Annex on recommendations about the objectives, functions, structure and membership of a possible Subsidiary Body on Capacity Development (SBCD) and other containing suggested terms of reference and rules of procedure for the SBCD.

The group resolved to recommend to CPM the creation of a SBCD and consider the specific recommendations contained in Annexes 1 and 2 to this Appendix.

## SWOT Analysis on the establishment of a CPM Subsidiary Body on Capacity Development

| Strengths | Weakness | Opportunities | Threats |
| --- | --- | --- | --- |
| Affirmation of the importance of the Capacity development function in the IPPC | Less flexibility due to stricter rules adopted by CPM | Terms of reference can be designed based on lessons learned from other IPPC subsidiary bodies | Costs can overrun if the CPM expectations of the work of the body becomes unrealistic |
| Greater recognition of the value of the produced outputs | Cumbersome to put together participants and call for meetings | The affirmation of the importance of capacity development by CPM-3 prepares the ground for the creation of a SB dedicated to it | Possibility that CPM may mandate the application of procedures/requirements with high costs implications, such as translation/interpretation or a high number of members. |
| Regularity of meetings ensures better planning, continuity and validation of the work of the body | Membership selection process inflexible | Maintain the momentum and interest in capacity development and attract the attention of previously passive contracting parties. | The false impression of some contracting parties that the creation of a SB would lead to the obligation to fund its work programme |
| Commitment to get full representation of regions and members | Regional representation process can affect quality of representation | Build upon the experiences of other standard setting bodies in capacity building | The establishment of the Body would trigger a higher degree of expectations than what is achievable given available resources. |
| Representation of the body by its chair at the CPM and other SB (SPTA) facilitates the presentation and the clarification of the agreed positions |  | Develop linkages with organizations to establish and/or enhance partnerships and create synergies to avoid duplication | The process of election of officers of the Body could lead to weaker leadership |
| Allows expeditious response from CPM |  | A SB would have a greater degree of influence and more weight of decisions | Potential bureaucratic procedures for the SB could reduce the effectiveness of the CD programme. |
| Maintains the momentum and interest in capacity development and attracts the attention of previously passive contracting parties. |  | Early feedback on acceptance of work produced by the SB |  |
| Members influence in regions |  | Members’ influence in regions could be increased |  |
| A SB would have a greater degree of influence and more weight of decisions |  | The process of election of officers of the Body could lead to a strong leadership |  |

# Annex 1

# Objectives, functions, structure and membership of a Subsidiary Body on Capacity Development (SBCD)

The purpose of the SBCD is to contribute to the achievement of the IPPC strategic objective D: develop phytosanitary capacity for members.

The inputs provided for the achievement of this objective will have an impact on the  protection of  sustainable agriculture, enhancement of  global food security through the prevention of pest spread, protection of  the environment, forests and biodiversity against plant pests and to facilitate economic and trade development through the promotion of harmonized, scientifically-based phytosanitary measures.

# Objectives

Objectives of a subsidiary body on capacity development shall be based on contracting parties needs and shall include:

# Implementation of the IPPC national capacity building strategy at all levels.

# Sustainable funding for the IPPC national capacity building strategy

# Implementation of the IPPC and ISPMs by contracting parties.

# Assist and advice the CPM, other SB and organizations.

# Functions and responsibilities

# Inform CPM of its activities.

# Review the IPPC national phytosanitary capacity development strategy, on a regular basis.

# Identify, promote, support and/or develop appropriate capacity development activities in line with the IPPC national phytosanitary capacity development strategy including technical resources, such as manuals, SOPs, guidelines, training materials and databases.

# Assess and prioritize for inclusion in the IPP those manuals, SOPs, guidelines, training materials and databases provided by partners, other public-private organizations, NPPOs and  RPPOs, relevant for the implementation of the IPPC and its ISPMs.

# Monitor and evaluate the implementation of the IPPC national phytosanitary capacity development strategy.

# Enhance links and liaise with donors, partners and other public - private organizations concerned with capacity development in the phytosanitary area.

# Provide guidance and direction to the IPPC Secretariat capacity development and standard setting programs based on the identification of challenges associated with the implementation of the IPPC and its standards.

# Review periodically its functions and procedures.

# Liaise with other CPM Bodies and the Bureau.

# Undertake other functions as directed by the Commission, which may include:

# in consultation with the Chair of the SB, represent the Secretariat in capacity development initiatives of other organizations, provided that those initiatives are consistent with the mandate of the SB;

# provide oversight of the IRSS program;

# report on IPPC related capacity development activities and challenges relevant to the phytosanitary community;

# assist in identifying appropriate experts for capacity building/standard implementation activities;

# coordinate closely, as needed,  with other CPM subsidiary  bodies, on relevant actions;

# coordinate closely with standard setting bodies and capacity development initiatives and mechanisms under the WTO framework.

# Structure and membership of a subsidiary body on capacity development

Composition

The size and composition of the subsidiary body shall be based on geographical representation  with one delegate being from each FAO region and at minimum of three members being from developing countries. The quorum shall consist of 4 members.

Qualifications and experience

It is considered essential that members of the SB shall have an interest and experience in capacity development.

The members should possess the following:

demonstrated experience in managing phytosanitary systems;

demonstrated experience in delivering phytosanitary capacity development activities;

in depth knowledge of the IPPC and International Standards for Phytosanitary Measures;

experience in the application of phytosanitary regulations/legislation; and

preferably knowledge, qualifications and/or experience in developing training materials.

Commitment of Contracting parties

Contracting Parties shall allocate the time, resources, and support necessary for its nominee to fulfil their role in the SB. Contracting Parties shall submit in written a statement of commitment to this effect to the IPPC Secretariat.

Administration of the Body

The subsidiary body Shall elect its Chairperson from among its membership.

Members of the subsidiary body shall serve for a minimum of two years, and a maximum of six years.

The SBCD shall meet once a year

Review

# The SB shall review periodically its functions and procedures.

The need for a subsidiary body, and its functions and operation will be reviewed by the Commission every six years, taking into account experience and changing conditions.

# Resources consideration

The SBCD shall meet as a Body annually, have extraordinary meetings when necessary and  make use when possible of innovative work options, such as videoconference, teleconference, work by mail, facsimile and e-mail, in the most cost-effective manner within the available resources.

The resources for the annual meeting shall be allocated in accordance with Rule 11 of the Rules of procedures of the CPM.

Relationship with other bodies

During the process of assessing technical resources, and as needed, the subsidiary body shall coordinate actions with other relevant CPM bodies.

# Annex 2

# Suggested terms of references and rules of procedure for the a SB on Capacity Development

# Terms of Reference

# 1. Scope of the Subsidiary Body on Capacity Development

The Subsidiary Body on Capacity Development contributes to the achievement of the IPPC strategic objective to develop the phytosanitary capacity of its members.

The work of this Body shall be guided by the IPPC national phytosanitary capacity building strategic framework adopted by the Commission

# 2. Objectives

Objectives of a subsidiary body on capacity development shall be based on contracting parties needs and shall include:

# Implementation of the IPPC national capacity building strategy at all levels.

# Sustainable funding for the IPPC national capacity building strategy

# Implementation of the IPPC and ISPMs by contracting parties.

# Assist and advice the CPM, other SB and organizations.

3. Structure of the Subsidiary Body on Capacity Development

The size and composition of the subsidiary body shall be based on geographical representation  with one delegate being from each of 7 FAO regions and at minimum of three members being from developing countries. The quorum shall consist of 4 members. The members shall have no personal interest in providing independent technical assistance.

# 4. Functions of the Subsidiary Body on Capacity Development

The Subsidiary Body on Capacity Development has the following functions:

# Inform CPM of its activities.

# Review the IPPC national phytosanitary capacity development strategy, on a regular basis.

# Identify, promote, promote  and/or develop appropriate capacity development activities in line with the IPPC national phytosanitary capacity development strategy including technical resources, such as manuals, SOPs, guidelines, training materials and databases.

# Assess and prioritize for inclusion in the IPP those manuals, SOPs, guidelines, training materials and databases provided by partners, other public-private organizations, NPPOs and  RPPOs, relevant for the implementation of the IPPC and its ISPMs.

# Monitor and evaluate the implementation of the IPPC national phytosanitary capacity development strategy.

# Enhance links and liaise with donors, partners and other public - private organizations concerned with capacity development in the phytosanitary area.

# Provide guidance and direction to the IPPC Secretariat capacity development and standard setting programs based on the identification of challenges associated with the implementation of the IPPC and its standards.

# Review periodically its functions and procedures.

# Liaise with other CPM Bodies and the Bureau.

# Undertake other functions as directed by the Commission, which may include:

# in consultation with the Chair of the SB, represent the Secretariat in capacity development initiatives of other organizations, provided that those initiatives are consistent with the mandate of the SB;

# provide oversight of the IRSS program;

# report on IPPC related capacity development activities and challenges relevant to the phytosanitary community;

# assist in identifying appropriate experts for capacity building/standard implementation activities;

# coordinate closely, as needed,  with other CPM subsidiary  bodies, on relevant actions;

# coordinate closely with standard setting bodies and capacity development initiatives and mechanisms under the WTO framework.

# 5. IPPC Secretariat

# The Secretariat provides administrative, technical and editorial support as required by the Subsidiary Body on Capacity Development. The Secretariat is responsible for reporting and record keeping regarding the capacity development activities.

# Rules of Procedure

# Rule 1. Membership

Membership of the SBCD is open to contracting parties.

The size and composition of the subsidiary body shall be based on geographical representation  with one delegate being from each FAO region and at minimum of three members being from developing countries.

Members serve for terms of two years, with a maximum of six years. Regions may submit requests for additional exemptions for the same member on a term-by-term basis. Partial terms served by replacements shall not be counted as a term under these Rules.

# Rule 2. Replacement of members

A potential replacement shall be nominated for each region for members of the SBCD and submit it to the Commission for confirmation. Once confirmed, potential replacements are valid for the same period of time as specified in Rule 1. These potential replacements should meet the qualifications for membership set forth in these Rules.

A member of the SBCD will be replaced by a confirmed potential replacement from within the same region if the member resigns, no longer meets the qualifications for membership set forth in these Rules, or fails to attend two consecutive meetings of the SBCD.

The national IPPC contact point should communicate to the Secretariat any circumstances where a member from its country needs to be replaced.

A replacement will serve through the completion of the term of the original member, and may be nominated to serve additional terms.

# Rule 3. Chair

The subsidiary body shall elect its Chairperson and Vice-Chairperson from among its membership.

# Rule 4. Qualifications of subsidiary body members

Members shall have interest and experience in capacity development.

The members should possess the following:

demonstrated experience in managing phytosanitary systems;

demonstrated experience in delivering phytosanitary capacity development activities;

in depth knowledge of the IPPC and International Standards for Phytosanitary Measures;

experience in the application of phytosanitary regulations/legislation; and

preferably knowledge, qualifications and/or experience in developing training materials.

# Rule 5. Sessions

The SBCD shall meet as a Body annually, have extraordinary meetings when necessary and  make use when possible of innovative work options, such as videoconference, teleconference, work by mail, facsimile and e-mail, in the most cost-effective manner within the available resources.

A meeting of the SBCD shall not be declared open unless there is a quorum of 4 members.

# Rule 6. Observers and participation of  invited experts

Meetings of the subsidiary body are generally open according to Rule VII of the Rules of Procedure for the Commission.

In specific cases, with prior agreement of the subsidiary members, the Chair of the SBCD may invite individuals or representatives of organizations with specific expertise to participate on an ad hoc basis at a specified meeting or part of a meeting or for specified business, as invited experts.

However, the subsidiary body may determine that certain meetings or business need to be conducted without observers, in particular where controversial information is involved.

# Rule 7. Decision-making

The subsidiary body shall strive for consensus on all decisions but may vote where necessary using a 2/3 majority to take decisions. Decisions shall include dissenting opinions where requested.

Rule 8. Review

The SBCD shall periodically review its functions and procedures.

The Commission  shall review every six years the need for a subsidiary body, and its functions and operation, taking into account experience and changing conditions.

# Rule 9. Amendments

Amendments to the functions and procedures of the subsidiary body will be promulgated by the Commission as required, upon recommendation of the body.

# Rule 10. Confidentiality

The subsidiary body shall exercise due respect for confidentiality where sensitive information is identified.

# Rule 11. Language

The meetings of the SBCD shall be conducted in English.

Appendix 5. Terms of reference for an award on Capacity Development

The EWG considered that a possible mechanism for increasing awareness of IPPC capacity building efforts, and possibly a means to improve those efforts, would be to establish an annual award or awards. Example, there could be an award for a country which has achieved significant goals over the course of a year: best use of training, best use of personnel and resources, most effective contribution to plant health in a country, etc.  Alternatively, there could be an award for the best individual capacity building project, thus including the recognition of all the participants, or there may be additional alternative possibilities, such as recognition of the best projects by specific field.

Objective: to recognize plant health related capacity building efforts over the course of a year.  Granted to the best efforts in creating national phytosanitary capacity and

Procedure:  The  process for determining the winner should be highly competitive and have very specific criteria.  It shall be a single award per year alternating by subject annually, i.e. project or country.

Confidentiality

Members of the EWG or SBCD shall be bound by the specific rule of procedure on confidentiality and shall affirm in writing to be so bound.

Method of nomination

Make an open call by the IPPC Secretariat.

Selection process

The EWG or SBCD shall be the group that determine eligibility and granting of the award, based on the following criteria:

- Effectiveness and efficiency in the delivery of CD

- Long term sustainability of the developed improvements

- Practicality, replicability and innovation

- Value to the phytosanitary community

- Stakeholders inclusiveness

- Promotional value within and outside of the phytosanitary community

- Contribution to the fulfilment of the IPPC strategic objectives

- Contributions to the fulfilment of obligations and responsibilities under the IPPC.

Eligibility

Proposal presented by an IPPC contracting party

Award

The award shall be conferred at CPM by the Secretary of the IPPC and so recorded in the CPM report. (The award could be sponsored).

Appendix 6.  Advocacy: Human resources and organizational development: Ideas and concepts (Promotion of IPPC issues in curricula of Universities, Centers of Excellence and other institutions at national and international level to build capacities). Table of ideas and concepts for discussion.

| IPPC issue to promote | Ideas and concepts | Comments |
| --- | --- | --- |
|  | Who are the audience? What is the social/economic context? What communication tools can be used? What kind of message do we have to communicate? |  |
| Biosecurity curriculum Establishing the necessity for PRA capacity Improving understanding of IPPC concepts | University students, not directly related to plant health; building staff capacities for the future; engage University, provide materials; protect the world plant resources. Technical resources of Universities and Centres of Excellence; as a national food security and environmental issue; national policy discussion with government , Universities and Centres of Excellence; no PRA increases risk of a pest affecting your agriculture. Broad range of stakeholders: environmental related staff; commodity groups, national policy makers; trade and environmental protection and donor funding prioritization; guidelines, manuals policy documents, factsheets, video, E learning, etc; approaching actors to trade safely. | Could be presented to donors to be developed on an universal basis. Encourage incoming students to take up this discipline. |

Appendix 7. Capacity Development Resource Mobilization: Concepts and proposals as a contribution to the overall IPPC Resource Mobilization Strategy.

| Strategy Topic (see IPPC BNPC Strategy) | Proposal/concept | Details |
| --- | --- | --- |
| 1. NPPO management | Develop a course on how to manage an NPPO. Emergency management framework. Development of curricula for Universities and Centres of Excellence. Document on modalities for the establishment of an NPPO. Good practices for participating in IPPC activities. |  |
| 2. Participation in standard setting | Distance training on standard setting process. |  |
| 3. Standards Implementation | Cataloguing of existing manuals, SOPs, treatments, etc Development of new technical resources, where gaps exist. |  |
| 4.Communication and coordination | Develop a communication plan specific to capacity development. Partnering, donor fora, improving dialogue . |  |
| 5. Pest information | Pest factsheets Surveillance and sample processing training modules Gap analysis to determine requirements for surveillance, diagnostics, reference collections, information systems etc. Development of specialized diagnostic support at a regional level. |  |
| 6. Resource mobilization | Donor coordination. Guidelines for engaging donors. |  |
| 7. Advocacy | Guidelines for Phytosanitary Capacity building based on Paris Principles. Develop training materials for advocacy for use at all levels. |  |
| 8. Monitoring and evaluation | Identify existence and use of M&E tools by contracting parties and others. M&E tools developed or adapted, Develop and populate a depository tool Training in use of M&E tools (including use of the depository) Partner with leading institutions to conduct reviews and assessments. Mid Term and Final Reviews |  |

Appendix 8.  Table from the discussion on possible topics for Manuals.

| Generic inspection for import/export | Export certification | Surveillance and diagnostic | Import Verification | NPPO management | Status and pest listing | Emergency response |
| --- | --- | --- | --- | --- | --- | --- |
| Green houses | Packinghouses specifications | Determination of surveillance plans | Post entry quarantine | Setting up an NPPO | Preparation of lists of regulated pests . | Contingency planning |
| Storage places | Silos | Collection of samples | Treatments | Client management | Information sharing on pest status | Funding mechanisms |
| Containers | General export procedures | Processing of samples for analysis | Systems approaches | Customers service |  | Stakeholders coordination |
| Grain and seeds, including turf | Treatments | Surveillance information management | Preclearance | Stakeholder fora |  | Declaration of regulated areas. |
| Handicrafts | Systems approaches | PFA and ALPP | Documentary verification | Phytosanitary information system management |  |  |
| Lumber and timber and sawn wood products | Preclearance | PFPP and PFPS | Emergency procedures | Hazard profiling |  |  |
| Packaging Material | PFA and ALPP | Trapping for specific pests | Handling of non-compliance cases | Cost recovery/Fees structure |  |  |
| Air Passenger Baggage | PFPP and PFPS |  | Offsite inspection | Policy and legislation |  |  |
| Air Cargo | Field inspection |  | Sampling for diagnostics | Human resources management |  |  |
| Maritime and inland waterways cargo | Issuance of PC |  | Processing of biological control agents for import | Import permits |  |  |
| Mail Facility | Traceability of consignments |  | Leakage surveys | Market access negotiations |  |  |
| Passenger Vehicles | Maintenance of identity and integrity of consignments |  |  | Training requirements for public officers and designated officers |  |  |
| Overland Cargo | Sampling for diagnostics |  |  | Participation in IPPC activities |  |  |
| Heavy used machinery | Handling of transit consignments |  |  | Performance management |  |  |
| Animals | Processing pest specimens for confirmatory diagnostics |  |  | Audits |  |  |
| Pedestrian |  |  |  | Quality assurance |  |  |
| Pre departure Air Passenger |  |  |  | Third parties authorization |  |  |
| Rail Cargo |  |  |  | Service providers supervision |  |  |
| Feed inspection |  |  |  | Branding and promotion |  |  |
| Express Carrier |  |  |  | Prosecuting cases of offenses |  |  |
| Cruise Ship |  |  |  |  |  |  |
| Nursery Stock |  |  |  |  |  |  |
| Ornamentals |  |  |  |  |  |  |
| Garbage |  |  |  |  |  |  |
| Soil |  |  |  |  |  |  |
| Organic Fertilizers |  |  |  |  |  |  |
| Ship Ballast |  |  |  |  |  |  |
| Handling of transit consignments |  |  |  |  |  |  |
| Sampling for diagnostics. |  |  |  |  |  |  |

Appendix 9 . Indicative program for training of trainers

Phytosanitary Capacity Building Facilitators

Training: Provisional Agenda

[VENUE]

[DATE]

| Day 1 - |
| --- |
| am | Introduction to Workshop Programme Capacity Building Introduction to the IPPC Phytosanitary Principles and Concepts for the Protection of Plants- ISPM 1 Global phytosanitary/trade environment as defined by International Treaties(IPPC,WTO,SPS, CBD) SPS IPPC Standard Setting procedure IPPC Dispute settlement |
| pm | International Standards for Phytosanitary Measures (ISPMs) – content and implementation issues ISPMs and implications for international trade Requirements for implementation of the IPPC Roles functions as defined by the IPPC of: IPPC and NPPO NPPOs and RPPOs National Obligations |
| Day 2 - |
| am | Operational/procedural issues confronting NPPOs Developing country problems Information exchange Guidelines for inspection Consignments in transit |
| pm | Operational/procedural issues confronting NPPOs IPPC and alien invasive species Wood packaging materials Non-compliance Pest reporting, pest status |
| Day 3 - |
| am | Phytosanitary systems evaluation (PCE) for implementation of selected standards Introduction to PCE and the International Standards PCE tool |
|  | Skills training in Pest Risk Analysis and review of PRA procedures PRA for quarantine pests and PCE module PRA-RNQP PRA-LMOs |
| pm | Skills training in Pest Risk Analysis and review of PRA procedures Import regulation & PRA |
|  | Technical tools in PRA |
|  | Information sources Negotiations/bilateral discussions regarding PRA decisions in terms of market access: experience sharing |

| Day 4 - |
| --- |
| am | Legal frameworks and capacity requirements for NPPO for consistency with the IPPC Establishing NPPOs and Bio-security approaches Legislation and Institutional modules - PCE Import Regulatory Structure |
| pm | Export Certification and PCE module Surveillance and PCE module |
| Day 5 - |
| am | Phytosanitary Systems Analysis: Phytosanitary Capacity Evaluation (PCE) and strategic planning Stakeholder Analysis Problem analysis |
| pm | Phytosanitary Systems Analysis: Phytosanitary Capacity Evaluation (PCE) and strategic planning SWOT analysis Logical Framework approach |
| Day 6 - |
| am | Project identification, formulation and funding options The FAO project cycle Funding options |
| pm | Project formats TCP programme Standard Project document format TCP Guidelines Model letter government request |
| Day 7 - |
| am | Regional/sub regional perspective, initiatives and coordination Important phytosanitary/trade issues in the region Discussions regarding priority issues & experiences |
| pm | Field visit – (Point of entry inspection point, field surveillance activity, export certification activity etc.) |