PROGRAMME FOR THE DEVELOPMENT OF THE “IPPC IMPLEMENTATION REVIEW AND SUPPORT SYSTEM”

Components to be developed

The “IPPC Implementation Review and Support System” has two major components: the Implementation review system (IRS) and the Implementation support system (ISS). These are both used along with other information from the International Phytosanitary Portal (IPP - https://www.ippc.int), the Technical Consultation among RPPOs (TC-RPPOs), the report on the use of the Phytosanitary Capacity Evaluation (PCE) tool and reports from other relevant organizations, to produce the Implementation review response.

The Implementation review response (IRR) summarizes the situation of the implementation of the IPPC and its standards by contracting parties. From this summary, action plans are developed, for input into the proposed work programme for consideration by the CPM. The recommended action plans will be a key input into the strategic and technical assistance planning of the CPM.

The various parts of the components are listed below, and are presented in Table 1 with approximate dates for action.

Implementation review system

First element: IPPC Secretariat monitors the fulfilment of the reporting requirements of contracting parties through the IPP. This involves:

IPPC Secretariat informs contracting parties again of their reporting requirements

Contracting parties respond by submitting reporting requirements if not already done

IPPC Secretariat reporting on contracting parties' difficulties with the reports annually requirements, by publishing on the IPP a list of contracting parties facing such difficulties. An annual summary report would also be presented to the CPM.

Second element: triennial review to evaluate the implementation of other obligations (non-reporting) contained in the IPPC. This involves:

development of a questionnaire by the Secretariat to gather information from contracting parties regarding implementation of IPPC obligations, in particular in relation to Articles IV, V, VII, and VIII.

review of this questionnaire by the Bureau and other experts

distribution of the pilot questionnaire to a limited number of contracting parties representing the seven FAO regions, to evaluate and improve it

review of the questionnaire by the Bureau and other experts for possible improvement

distribution of the questionnaire to contracting parties for completion

collation and analysis of the data

establishment of a triennial review group

analysis of questionnaire replies by a meeting of the triennial review group. This would include suggestions for improvement of the questionnaire prior to its next use

submission of the report of the triennial review to the Bureau for the purpose of ISS. Note the Bureau also uses the triennial review as part of the Implementation review response

submission of the report of the triennial review to SPTA

submission of the report of the triennial review to CPM.

Implementation support system

IPPC Secretariat to establish an IPPC Help Desk. This would involve the appointment of a Standards Implementation Officer to the IPPC Secretariat. This officer would coordinate the implementation activities of the Secretariat's activities so as to:

help with finding assistance for those contracting parties requesting help with the implementation of ISPMs

provide advice relating to the implementation of ISPMs

monitor, identify and report implementation difficulties

ensure that contracting parties requesting assistance are put in contact with potential donors

provide a summary report of IPPC Help Desk activities to the CPM.

This officer would use the services, as appropriate, of the IPPC Secretariat, the CPM Bureau, the CPM subsidiary bodies, the FAO legal office and other units in discharging these functions

Implementation review response

The Bureau will develop an Implementation review response every three years. This will be based on:

the report of the triennial review

a summary report of the IPPC Help Desk activities

a report on implementation difficulties from the Technical Consultation among RPPOs

a summary report on implementation trends from the PCE

the annual Secretariat IPP reports on the fulfilment of contracting reporting requirements

reports from other relevant international organizations.

The implementation review response (which will be in the form of a report) will include appropriate action plans. On the basis of this response, recommendations for future activities to enhance implementation of the IPPC and ISPMs could be developed for incorporation into the CPM work programme, and these should be a key input for the IPPC strategic and technical assistance planning. In addition, this response could address a number of recommendations of the report of the Independent Evaluation of the IPPC, specifically the review of the state of plant protection in the world and the development of procedures to monitor the implementation of standards.

The response will be considered by the SPTA then the CPM.

As noted earlier this response will provide recommendations for future activities to enhance the implementation of the IPPC and ISPMs for incorporation into the operational work programme of the CPM.

Table 1:	A three year work plan with proposed milestones and dates

| Proposed dates | Actions | Component |
| --- | --- | --- |
| Year 1 |
| April | IPPC Secretariat annual report to the CPM on: contracting parties' difficulties with reporting requirements based on reporting through the IPP; and the IPPC Help Desk activities. | Implementation Review System (first element) |
| May | IPPC Secretariat informing contracting parties again of their reporting requirements (first time in 2008) | IRS (first element) |
| June | Appointment of the Standards Implementation Officer | Implementation Support System (ISS) |
| August | Development of a questionnaire by the Secretariat to gather information from contracting parties regarding implementation of other (non-reporting) IPPC obligations, in particular in relation to Articles IV, V, VII, and VIII | IRS (second element) |
| September | Review of the questionnaire by the Bureau and other experts | IRS (second element) |
| September | Initiation of IPPC Help Desk | ISS |
| October | Distribution of pilot questionnaire | IRS (second element) |
| November | Review of the questionnaire by the Bureau and other experts | IRS (second element) |
| December | Evaluation (plus comments) by limited number of contracting parties followed by second review by the Bureau and other experts | IRS (second element) |
| Year 2 |
| March | Distribution of questionnaire to contracting parties | IRS (second element) |
| March | Collation and analysis of data for the IPPC Secretariat report. | IRS (first element) |
| April | IPPC Secretariat annual report to the CPM on: contracting parties' difficulties with reporting requirements based on reporting through the IPP; and the IPPC Help Desk activities. | IRS (first element) |
| April | Establishment of a triennial review group | IRS (second element) |
| May | Analysis of questionnaire replies and suggestions for improvement of the questionnaire by a meeting of the triennial review group | IRS (second element) |
| June | Reports on implementation by the TC-RPPOs and other relevant international organizations | Implementation Review Response (IRR) |
| Reports received by Secretariat June Prepared by CPM Bureau July-August | Report prepared • based on the following elements: - the report of the triennial review - a summary report of the IPPC Help Desk - a report on implementation difficulties from the TC-RPPOs - a summary report on implementation trends from the PCE - reports from other relevant international organizations • and containing action plans. | IRR |
| October | Review by the SPTA | IRR and IRS |
| November | Prepare paper (IRR response) for the CPM | IRR |
| Year 3 |
| March | Collation and analysis of data for the IPPC Secretariat report. | IRS (first element) |
| April | Present report of the triennial review (first time at CPM-5 in 2010) | IRS (second element) |
| April | IPPC Secretariat annual report to the CPM on: contracting parties' difficulties with reporting requirements based on reporting through the IPP; and the IPPC Help Desk activities. | IRS (first element) |
| April | Report of the IRR considered by CPM | IRR |

# Footnotes

This mechanism could also deal with significant elements involved in undertaking the global review of status of plant protection in the world as per IPPC.