OPEN ENDED WORKING GROUP

BUILDING NATIONAL PHYTOSANITARY CAPACITY

Discussion Paper Submitted by KEPHIS

Contact Person

Washington Otieno

KEPHIS

Tel +254 20 3536171/2

Fax +254 20 3536175

E-mail: direcor@kephis.org; wotieno@kephis.org

November 2008

Introduction

The decision to establish the OEWG on phytosanitary capacity building was an excellent move with potential to benefit countries with weak phytosanitary systems which are also characterized with slow development of phytosanitary capacity. For Kenya, this came at a time when an initiative to address concerns about weak phytosanitary capacity through development a Centre for phytosanitary Excellence (COPE) is in the offing. Although COPE domiciled at KEPHIS, the project has the support of the IAPSC. Its scope covers several eastern and southern African countries.

This paper presents an overview of the COPE, a project co-funded by the STDF and KEPHIS with national and international collaborators and highlights its activities to date.

Strategy of COPE

- Maximizes the use of African expertise and existing capacities.

- Established nationally but used regionally.

- Consult widely during establishment.

- Essentially a public sector agency but:

  - Takes account needs of clientele in private sector.

- Proactive & practical provision of capacity needed to develop phytosanitary capacity.

- Founded on exemplary model facilities & procedures to support training.

- Aims for regional ownership and self-sustaining business model.

- Expect other centres in Africa – See output of 23rd GA IAPSC.

Partnerships/Synergies

- Partners: KEPHIS, UoN, CABI, IPPC, NPPS (possibly USDA - APHIS)

- Funders: STDF, KEPHIS and NPPS

- Duration: May 2008-April 2010

- Project Management Committee:

- Partners

- NPPOs (not Kenyan)

- 2 private sector agencies (1 Kenyan, 1 non Kenyan) – active consumers of phytosanitary services

- Appropriate regional bodies (e.g. IAPSC)

- Donor agency/agencies!!!

Overall objective

To re-orient development & utilization of phytosanitary capacity in Africa towards:

- Better management of contemporary phytosanitary issues

- More focus on improved protection of plant resources

- Easing market access for African products

Specific Objectives

- To set up the legal and institutional framework

- To set up a training unit

- To set up a PRA unit

- To promote the centre and its services

Legal & Institutional framework

- Management structure for centre

- Registration as a legal entity

- Development of a business plan

Training Unit

- Needs assessment (regional workshop)

- Curriculum development and design of courses (short courses up to PG Diploma)

- Training of trainers (NPPO Staff)

- Upgrading airport inspection facilities (equipment, training)

- Information system for NPPOs (software, training)

- Improve documented procedures at NPPOs

PRA Unit

- PRA training needs assessment (regional workshop)

- African pest risk analysts network

- Provision of information resources

- Provision of software (e.g. climate matching)

- Training of PRA staff

Promotion of the Centre

- Website

- Promotional materials

- Regional dissemination meeting

Current Situation

  - The three main partners of COPE – KEPHIS, UoN and CABI have signed memorandum of understanding (MoU). Although other MoUs are needed e.g. KEPHIS and NPPS.

  - The Project Management Committee (PMC) has met twice i.e. 28th to 29th July 2008 and 23rd to 24th October 2008. The PMC is the advisory arm of the project. The three managers from KEPHIS, CABI and UoN do the day-to-day implementation of the project.

  - The training needs assessment (TNA) activity has began with the following activities undertaken – the TNA questionnaire developed to collect data from Eastern African countries, the questionnaire sent to various Eastern African countries, questionnaires have been received from some countries and more still being received. The TNA workshop is set for 3rd to 8th December 2008 at KEPHIS HQ, Nairobi. During the workshop discussion will be based on country phytosanitary gap analysis, among others.

Next Steps

During the second PMC meeting, Dr. Jean Gerard Mezui M’ella presented a proposal by IAPSC for the development of an African Strategy for Phytosanitary Capacity Building.

PMC provided the following input: IAPSC would need to contact relevant persons in African countries to join the African working group on developing the strategy. Also the PMC suggested various background papers be developed. Various issues were also proposed to be included in the strategy to make African issues be more evident in the international arena.

Members of African working group proposed

Four additional countries were selected to join the African working group currently having Kenya and Ghana as members: Zambia, Cote D’Ivoire, Cameroon and Nigeria.

Rwanda, South Africa, Tanzania, Gabon and Senegal were considered as other possibilities.

It was proposed that IAPSC contacts relevant persons in Zambia, Cote D’Ivoire, Cameroon and Nigeria to join the African working group on developing the strategy.

Background papers proposed

PMC suggested the following background papers:

- Documentation of roles and mandates of key institutions involved in phytosanitary activities in the region, such as COPE, IAPSC, RECs, & NPPOs.

- Listing of on-going initiatives and activities in the region (Action: Hannah Clarendon of FAO, Ghana to provide information for West Africa, and Arundel Sakala of Zambia NPPO for Southern Africa.

- A description of existing collaboration, partnerships and synergy between key institutions, including how they related to the IAPSC in terms of coordination, harmonization and dissemination of activities and results.

Issues to include in the strategy

It was proposed that the strategy should address the following amongst others:

- Resource mobilization & partnerships;

- How to build a core group of resource persons at regional level as part of the regions self-empowerment;

- How to position Africa issues in global affaires. For example, how would Africa bring out the issues of bio-invaders that are relevant to Africa onto the international arena and agenda? One possibility is to set up technical committees or groups to work on specific technical issues that are meant to be discussed at the global level;

- How to strengthen the role of IAPSC as the champion for Africa and to become an effective RPPO – for example, how to enhance its capacity to support NPPOs, as opposed to IAPSC doing similar activities. This will require a gap analysis between current IAPSC activities and its vision & mission. IAPSC should have certain expectations and demands to the NPPOS.

- How to enhance partnerships between the IAPSC’s and regional and global bodies, e.g. the FAO.

Message to the OEWG

It was agreed that IAPSC, in its observer status, would share the contributions of PMC with members of the OEWG meeting; PMC members who are also in the OEWG would make COPE visible by introducing it to the group as well as presenting capacity building needs identified during the upcoming TNA workshop.