COMMISSION ON PHYTOSANITARY MEASURES

Fifth Session

Rome, 22-26 March 2010

2010 Budget and Operational Plan

Agenda Item 13.4.2 of the Provisional Agenda

1.	As requested by the Bureau and the informal working group on strategic planning and technical assistance (SPTA), the Secretariat has consolidated and simplified the presentation of the 2010 budget and operational plan.

2.	Anticipated contributions which will finance the IPPC Secretariat 2010 activities are from FAO’s Regular Programme, the Trust Fund for the IPPC, the Trust Fund of the European Union and reimbursement from FAO projects for seconded staff.  For the Trust Funds, only contributions brought into the consolidated contributions for 2010 are presented in Annex 1, and the Trust Fund for the IPPC balance (including carry forward from previous years) is presented separately in Annex 3.

3.	Planned expenditures for all 2010 activities, aggregated by the seven 5-year goals of the CPM Business Plan, are presented in Annex 1 to this paper.  Planned expenditures for staff posts are also aggregated and presented separately as it is difficult to allot staff costs to the seven goals.

4.	A summary of anticipated contributions and planned expenditures are presented in Annex 1.

5.	In 2010 planned expenditures exceed contributions.

6.	A list of staff posts is presented in Annex 2 to provide a better understanding of the staffing situation in the Secretariat and as the Secretariat posts are not fully staffed, the expected percentage they will be staffed is indicated. This list does not include consultants, hired or provided in-kind, for defined activities under specific goals. However, the totals per goal presented in Annex 1 include the expenditures for such consultants.

7.	For comparison, the actual contributions and expenditures for 2009, from CPM 2010/25, are also presented in Annex 1.

8.	If decisions taken at CPM-5 require additional financial resources, it may be necessary to modify some of the activities identified in the Operational Plan. Depending on availability of resources (funding and staff) the Secretariat may have to update the Operational Plan for 2010 after CPM-5 to reflect decisions made at CPM-5.

FAO Regular Programme

9.	The allocation of resources from the Regular Programme is approved by the FAO Conference, which meets biennially. Consequently, the FAO budget is biennial with the cycles being 2010-11, 2012-13, etc. The FAO Regular Programme contribution for the first year of the 2010-11 biennium is estimated (as at February 2010) as USD 2,630,000.

Trust Fund for the IPPC

10.	The 2010 Budget for the Trust Fund for the IPPC is presented in Annex 3. This Annex outlines the anticipated contributions, carry forward and expenditures to the Trust Fund for the IPPC. The Secretariat has received no notification from any donor of an intention to contribute to the Trust Fund in 2010. This Trust Fund is subject to the Financial Guidelines for the Trust Fund for the IPPC which stipulates that the Secretariat will distribute the budget on the Trust Fund to Members of the Commission.

Contributions to other Trust Funds

11.	During 2010, it is expected that additional contributions will be made to bilateral trust funds between the IPPC and donors. In 2010 these included the Trust Fund of the European Union and Associate Professional Officer trust fund (United States of America).  The anticipated contributions and expenditures for the European Trust Fund are reported in Annex 1 as these are used to fund activities in the operational plan. The contributions and expenditures from the Associate Professional Officer trust fund, which only fund APOs, are not included in Annex 1.  The budgets for contributions and expenditures from these funds are not reported in detail in this document, as specific reporting requirements are established when each of these trust funds were created.

FAO Projects

12.	When staff are seconded to FAO projects such as TCPs, the cost for the staff member is reimbursed. This amount was previously not displayed separately in the contributions, but offset the expenditures and this is the first year this figure is presented to the CPM.

Extra budgetary funding

13.	In order to meet the requirements of the CPM’s Business Plan: 2007-2011, extra budgetary funding through members’ voluntary contributions to the Trust Fund for the IPPC or other trust funds, and/or in-kind contributions, are required to supplement funds made available from FAO’s Regular Programme budget. In this regard members are encouraged to consider ways to contribute.  Some in-kind contributions of staff members have already been offered for 2010 and are listed in Annex 2.

CPM Operational Plan

14.	It was agreed at CPM-2 that the CPM’s Business Plan would be supported by an annual Operational Plan, with an associated budget, that would describe the activities for the forthcoming year aimed at achieving the seven five-year goals. The  2010 Operational Plan is presented in Annex 4.  This plan lists activities to be performed by all stakeholders involved in implementing the IPPC by goal and strategic area outlined in the CPM’s Business Plan.

15.	The Operational Plan was finalized in early 2010 based on the recommendations of the SPTA and Bureau and the anticipated ability of the Secretariat to deliver on the Plan. However, a number of agenda items for consideration by CPM-5 may have a significant impact on the Operational Plan for 2010. The Secretariat will prepare an updated Operational Plan for 2010 as soon as possible after CPM-5 taking into account the decisions made and any additional information on Trust Fund contributions.

16.	Whilst the majority of the activities will be delivered by the IPPC Secretariat, all contracting parties are encouraged to help deliver these described activities through assisting the Secretariat. Members of subsidiary bodies to the CPM, including the Bureau and SPTA are fundamentally important to ensuring the delivery of the IPPC work programme. The Secretariat will report back to the CPM on which activities were not completed, with an explanation, and list additional activities that were completed.

Calendar of Meetings

17.	A proposed Calendar of meetings for IPPC activities planned for 2010 and matching the Operational Plan is presented in Annex 5. Dates may change due to resource availability and operational considerations. An updated version of the Calendar is available at any time on the IPP: https://www.ippc.int/index.php?id=1110501 .

18.	The CPM is invited to:

Note the anticipated contributions and budgeted expenditures of the IPPC Secretariat for 2010 as presented in Annex 1.

Note the staffing situation of the IPPC Secretariat for 2010 as presented in Annex 2.

Adopt the 2010 Budget for the Trust Fund for the IPPC as presented in Annex 3.

Note the Commission on Phytosanitary Measures Operational Plan for 2010 as presented in Annex 4

Note the Calendar of meetings for IPPC activities planned for 2010 as presented in Annex 5

Note that the activities identified in the Operational Plan may be modified depending on availability of resources (funding and staff).

Request the Secretariat to update the budget and Operational Plan for 2010 to reflect decisions made at CPM-5.

Note that as at 31 December 2009, the Secretariat had received no notification from any donor of an intention to contribute to the Trust Fund in 2010.

Urgently encourage contracting parties to contribute to the Trust Fund for the IPPC.

Encourage contracting parties to contribute in kind to help deliver activities in the CPM’s Operational Plan.

Annex 1

Summary of 2010 anticipated contributions and planned expenditures
for the IPPC Secretariat

| in USD | 2010 anticipated | % Trust fund | 2009 Actual CPM 2010/25 | % Trust fund |
| --- | --- | --- | --- | --- |
| Contributions: |  |  |  |  |
| Regular Programme | 2,630,00 |  | 2,854,262 |  |
| IPPC Trust fund | 370,500 | 100% | 90,473 | 100% |
| European Trust fund | 310,000 | 100% | 225,691 | 100% |
| FAO projects | 50,000 |  | 102,434 |  |
| Total Contributions: | 3,360,500 | 20% | 3,272,860 | 10% |
| Expenditures: |  |  |  |  |
| Staff costs (does not incl. consultants) | 1,800,000 | 16% | 1,242,289 | 4% |
| Goal 1: Standard setting | 440,000 | 9% | 390,149 |  |
| Goal 2: Information exchange | 135,000 |  | 192,905 |  |
| Goal 3: Dispute settlement | 10,000 |  | -1,067 |  |
| Goal 4: Capacity Building | 85,000 | 9% | 530,062 | 9% |
| Goal 5: CPM | 605,000 | 38% | 578,017 | 31% |
| Goal 5: Sustainable implementation | 460,000 | 15% | 296,689 | 3% |
| Goal 6: International promotion and cooperation | 170,000 |  | 39,787 |  |
| Goal 7: Review status plant protection in the world | 35,000 |  | 4,029 |  |
| Total Expenditure | 3,740,000 | 18% | 3,272,860 | 16% |
| Deficit | (379,500) |  | ---- |  |

Annex 2

Staff Posts 2010

| Type of staff | % of year post staffed | % funded by TFs |
| --- | --- | --- |
| HQ staff on regular posts: |  |  |
| D-1, Secretary | 100% | 0% |
| P-5, Coordinator | 10% | 0% |
| P-4, Standards Officer | 100% | 0% |
| P-4, Information Exchange | 100% | 0% |
| P-4, Capacity Building/IPPC implementation | 60% | 0% |
| P-3, Standards Officer | 100% | 0% |
| G-5, Administrative Support | 50% | 0% |
| G-3, Administrative Support | 100% | 0% |
| G-2, Administrative Support | 0% | 0% |
| Divisional Administrative Support (percentage of management, finance and support staff) | n/a | 0% |
| Fixed term and short term posts: |  |  |
| P-3, Implementation Review and Support System (IRSS) | 60% | 0% |
| P-3, Standard setting | 50% | 0% |
| P-3, Standard setting Project staff (TF for IPPC) | 80% | 100% |
| P-3, Information Exchange / Capacity Building Project staff (TF for IPPC) | 100% | 100% |
| P-2, Programmer for IPP | 50% | 0% |
| P-2, Standard setting | 10% | 0% |
| P-1, - Standard setting | 50% | 0% |
| P-2, APO (USA) - Information Exchange (Yr 3 of 3)- US Trust Fund | 40% | 100% |
| P-2, APO (USA)- - Standard setting (Yr 1 of 2) US Trust Fund | 100% | 100% |
| P-4 level, Full time staff on Loan (USA) - Standard setting (Yr 2 of 3) | 100% | contribution in kind |
| P-4 level, 25% staff on Loan (Canada) Standard setting (Yr 1 of 3) | 25% | contribution in kind |
| P-4 level, 25% staff on Loan (Canada) Standard setting (Yr 1 of 4) | 25% | contribution in kind |

Annex 3

Budget for the Trust Fund for the IPPC
Details of 2010 consolidated contributions and expenditures (USD)

| in USD | 2010 budgeted | Balance |
| --- | --- | --- |
| Carry forward from previous years |  | 546,408 |
| Contributions: |  |  |
| NO PLEDGES |  |  |
| Total Contributions: | 0 | 546,408 |
| Expenditures: |  |  |
| Staff costs to partially fund a P2 Short Term post | 130,000 |  |
| Staff costs to fully fund a P3 Short Term post | 160,000 |  |
| Goal 5: Sustainable implementation - Partially fund the development of an On line comment system for collecting and compiling member comments. | 50,000 |  |
| Goal 5: Sustainable implementation - Administration and support costs | 30,500 |  |
| Total Expenditure | 370,500 | 175,908 |
| Anticipated carry forward to 2011 |  | 175,908 |

Annex 4

The Commission on Phytosanitary Measures Operational Plan for 2010

| Goal 1: A robust international standard setting and implementation programme |
| --- |
| Background: Standard development, adoption and revision: Under the IPPC (Article X), contracting parties agree to cooperate in developing international standards to be adopted by the CPM. Such standards are the means by which contracting parties can harmonize their phytosanitary measures. |
| Strategic Area 1.1 Standard development, adoption and revision |
| (i) Expert drafting groups and Standards Committee meet to develop standards |  |
|  | Two meetings of the Standards Committee (SC) (April and November) will be organized |  |
|  | One meeting of the SC-7 (May) will be organized |  |
|  | SC documents will be developed and posted on the IPP, including new draft ISPMs for the April SC meeting, draft ISPMs revised considering member comments for the SC-7 meeting and draft ISPMs considering SC-7 revisions for the November SC meeting. Reports from these meetings will be posted on the IPP. |  |
|  | Two SC meetings (twenty sessions) will be interpreted into requested languages (Arabic, Chinese, English, Spanish with the current SC composition) |  |
|  | *Work of five Technical Panels (TP) will be coordinated to ensure their work plans are delivered, including one meeting for each TP. Reports from these meetings will be posted on the IPP. |  |
|  | Phytosanitary treatments will be refined and submissions from the December 2009 call will be reviewed by the TPPT. |  |
|  | Diagnostic protocols are under development by editorial teams under the oversight of the TPDP |  |
|  | Four draft ISPMs, eight phytosanitary treatments and two diagnostic protocols will be developed by TPs. |  |
|  | *Two expert working group meetings will be organized and documents will be developed and posted on the IPP. Reports from these meetings will be posted on the IPP. Two draft ISPMs will be developed |  |
|  | One requests for nominations of experts (for TPs, EWGs, and authors of diagnostic protocols) will be made |  |
|  | Two draft specifications will be developed and made available for member comments |  |
|  | Five draft ISPMs (or equivalent) will be edited (included status box on cover), translated and circulated for member comments in June-September. |  |
|  | Member comments from June-September member consultation will be compiled and posted on the IPP. |  |
|  | A request for data on phytosanitary treatments will be circulated to NPPOs and RPPOs. |  |
|  | Member comments 14 days prior to CPM-5 will be compiled |  |
| (ii) Increase efficiency of standard development and adoption. |  |
|  | New collaborative internet tools will be used for developing and revising draft ISPMs (e.g. google docs). |  |
|  | Adopted ISPMs will be published on the IPP in 5 languages. |  |
|  | Language versions of the book of standards will be published on the IPP in English, French, Spanish and, for the first time, in Chinese. |  |
| (iii) Establish staff to maintain the standard setting programme. |  |
|  | Consultants will be contracted to assist with document preparation, meeting organization and publishing of ISPMs. |  |
| (iv) Environmental and biodiversity aspects considered |  |
|  | A task for expert drafting groups to consider the environmental impact of each standard will be added to all Specifications developed. |  |
| Strategic Area 1.2 Standards implementation |
| (i) Identify and address constraints in implementation |  |
|  | Support the IRSS (see goal 7) |  |
|  | Data on the implementation of ISPMs will be collected via the IPP. |  |
|  | Develop a systematic and extensive training programme for the implementation of four ISPMs to be used by NPPOs and RPPOs. |  |
|  | A questionnaire will be developed and distributed to NPPOs to identify constraints in the implementation of ISPMs. |  |
|  | Results from the questionnaire will be compiled and analysed to help direct the IPPC capacity building programme. |  |
|  | Consultant study on ISPM 15 symbol: - Secretariat will ask CPM members to help find a qualified legal expert to undertake study - study will be conducted pending extra-budgetary funds |  |
|  | Legal support for ISPM 15 symbol registration -no activity planned |  |
|  | Further population, compilation and presentation of the IPP Wiki for FAQs on the implementation of ISPM 15. |  |
| (ii) RPPOs assist members with implementation, including the development/revision of their regulations |  |
|  | RPPOs identify constraints and suggest ways of addressing these issues and report regularly at the Technical Consultation among RPPOs (TC-RPPO) and to CPM |  |
| * Partially funded by other organizations or through 2009 funds via Letters of Agreements |
| Goal 2: Information exchange systems appropriate to meet IPPC obligations |
| Background: The IPPC specifies the type of phytosanitary information to be exchanged in support of implementation. This includes the information exchange/communication among contracting parties, between contracting parties and the Secretariat, and at times, between contracting parties and their RPPOs. In addition, there is also general operational/administrative communication related to the meetings and operation of the CPM and its subsidiary bodies. |
| Strategic area 2.1: Implementation of information exchange as required under the IPPC |
| (i) Assist NPPOs with the use of the International Phytosanitary Portal (IPP), through capacity building activities undertaken by the Secretariat and/or RPPOs |  |
|  | 10 national/sub-regional capacity building workshops on Information Exchange. |  |
|  | The Secretariat will monitor information posted on the IPP by NPPOs (to meet their IPPC reporting obligations), analyse the data and adjust the delivery of assistance accordingly. |  |
| (ii) Secretariat to fulfil reporting obligations and communicate administrative matters efficiently in all FAO languages |  |
|  | Relevant information is made available to contracting parties in a timely manner (including posting of reports and meeting documents, outcome of meetings, updates to the calendar, etc.). |  |
| (iii) Further develop joint work programmes as necessary |  |
|  | Joint work programmes with two RPPOs will be agreed to for national pest reporting. |  |
| Strategic area 2.2: IPP supported by an effective development and maintenance programme |
| (i) Develop and document procedures for the ongoing use of the IPP |  |
|  | Secretariat maintains, improves and manages the IPP to enable the exchange of phytosanitary information in accordance with the Convention. |  |
|  | Hardware and software for the IPP will be maintained and updated |  |
|  | IPP Information Exchange Manual will be developed and made available. |  |
| (ii) Establish staff to maintain and develop the IPP |  |
|  | Consultants will be contracted to programme the IPP and for web design. |  |
| Goal 3: Effective dispute settlement systems |
| Background If required, contracting parties have access to dispute settlement described in Article XIII of the IPPC for which rules and procedures have been developed by the CPM. Although any recommendations from a committee considering the question in dispute are non-binding, parties agree that the recommendations will become the basis for renewed consideration of the dispute. |
| Strategic area 3.1: Encouragement of the use of dispute settlement systems |
| (i) Publicise the availability of the IPPC dispute settlement system |  |
|  | A brochure on the IPPC dispute settlement process will be developed and published on the IPP. |  |
| (ii) RPPOs to ensure members are aware of, and able to use, the dispute settlement system |  |
|  | The Secretariat will update the presentation on the IPPC dispute settlement process and ensure it is presented at five regional meetings. |  |
| Strategic area 3.2: Support for the IPPC dispute settlement system |
| (i) Provision of Secretariat support for disputes that may arise |  |
|  | Should a dispute(s) arise most costs for this activity should be recovered from those involved. Otherwise, no activity planned, except for responding to informal enquiries |  |
| (ii) Report to the CPM on dispute settlement activities |  |
|  | A report on the 2010 dispute settlement activities will be prepared for CPM-6. |  |
| (iii) Other activities |  |
|  | A meeting of the Subsidiary Body on Dispute Settlement will be organized as required. |  |
| Goal 4: Improved phytosanitary capacity of members |
| Background: Under Article XX of the IPPC, contracting parties agree to promote the provision of technical assistance to other contracting parties, especially to those that are developing country contracting parties, either bilaterally or through appropriate international organizations, with the purpose of building capacity for the implementation of the Convention. |
| Strategic area 4.1: Methods and tools in place that enable contracting parties to evaluate and improve their own phytosanitary capacity and evaluate requirements for technical assistance |
| (i) Updating, maintaining and distributing the PCE tool |  |
|  | Develop a stand-alone PCE tool and field test in at least 3 developing countries and make necessary adjustments , including seeking extra-budgetary resources for the field-testing phase |  |
|  | Distribute on flash drives and make available online |  |
|  | Secretariat to provide input to the East Africa Phytosanitary Information Committee for the development of the Pest Information Management System. 4 national visits supported by the One-UN funded projects in East Africa |  |
|  | Populate the rosters of consultants and experts and make available on the IPP |  |
|  | Resource database (training material, treatments, diagnostic protocols) will be populated and made available on the IPP |  |
| (ii) Use of the PCE and other inter-active learning tools for strategic planning and project development |  |
|  | One workshop to train/update selected personnel will be organized and conducted |  |
| Strategic area 4.2: The work programme of the IPPC is supported by technical cooperation |
| (i) Regional workshops, seminars (in cooperation with/assisted by RPPOs) |  |
|  | **1 regional workshop for Russian speaking countries will be organized in Georgia for the implementation of ISPMs |  |
|  | **7 Regional Workshop to review draft ISPMs |  |
| (ii) Formulation and implementation of capacity building projects |  |
|  | Five project formulation missions to assist developing countries in formulating phytosanitary projects. |  |
|  | Begin implementing three Capacity Building projects or programmes provided extra-budgetary funding is made available from donors or agencies other than FAO. |  |
|  | IPPC Secretariat supports approximately four FAO Capacity building projects (e.g. TCP). |  |
| Strategic area 4.3: Contracting parties are able to obtain technical assistance from donors |
| (i) Donor awareness of phytosanitary capacity needs |  |
|  | Activity is dealt with under 5.2(ii) |  |
| (ii) Make contracting parties aware of possible donors and their criteria for assistance |  |
|  | A presentation for promoting awareness of the IPPC will be developed and used on 10 occasions. |  |
|  | Preparation and distribution of donor criteria information |  |
| Strategic area 4.4: Development of a phytosanitary capacity building strategy which addresses implementation, funding and linkages to FAO resources. |
| (i) Develop and facilitate the implementation of the phytosanitary capacity building strategy |  |
|  | **IPPC Secretariat staff will be trained on the use of a monitoring and evaluation tool for the implementation of the Building National Phytosanitary Capacity (BNPC) framework. |  |
|  | Establish staff to maintain the capacity building programme. Consultants will be contracted to assist with the implementation of the Capacity Building Strategy. |  |
| ** Funded by other organizations or through 2009 funds via Letters of Agreements |
| Goal 5: Sustainable implementation of the IPPC |
| Background: The Commission, as the governing body of the IPPC, is the primary mechanism whereby the internationally agreed programme of standards development, information exchange and capacity building can be effectively and successfully implemented. |
| Strategic area 5.1: The IPPC is supported by an effective and sustainable infrastructure |
| CPM - Meeting |  |
|  | One CPM meeting (March) will be organized |  |
|  | 65 participants from developing countries will have their travel and subsistence costs fully or partially funded to attend CPM-5 (EU Trust Fund) |  |
|  | Translation of CPM-5 documents and report, and printing. |  |
|  | Twelve sessions of the CPM-5 will be interpreted into languages (Ar, En, Es, Fr, Zh) |  |
|  | General operating costs and temporary help will be hired to assistance in the organization of the CPM-5 (temporary assistance and messengers). |  |
|  | Travel for FAO Regional Officers to attend CPM |  |
| Other Goal 5 |  |
| General Operating Costs FAO back charges (e.g. utilities, phone, fax etc.) |  |
| Information Systems |  |
|  | The system behind the Phytosanitary Capacity Evaluation (PCE) tool will be revised and updated (three months programmer, translation into four languages: Ar, Es, Fr, Ru) |  |
|  | A new online comment system will be developed and implemented for compiling 2010 member comments on draft ISPMs (development of the system and programming) |  |
|  | ***Translation of non CPM documents (e.g. draft ISPMs, correspondence, website (IPP)) and printing. |  |
|  | Administration of the IPPC Trust Fund |  |
| (i) Necessary management and operational bodies identified and formalised within the CPM (or its subsidiary bodies) |  |
|  | One SPTA Meeting will be organized |  |
|  | Three CPM Bureau Meetings will be organized |  |
| (ii) Transparency and accountability resulting in more effective use of scarce resources |  |
|  | Activity for this item is dealt with under 5.2. |  |
| (iii) Preparation of an annual report to CPM on the operational plan by the Secretariat |  |
|  | Prepare and present budget, financial reports and work plans for each goal, including identifying any areas that were not completed and reasons for such, as well as additional activities |  |
|  | The IPPC procedural manual will be produced, and updated annually, to be transparent on processes followed in IPPC activities, including amalgamation of standard setting procedures (as decided by CPM-3) |  |
| (iv) Secretariat negotiates assistance from RPPOs with the implementation of the annual CPM programme |  |
|  | A work programme on Cooperation in the delivery of IPPC activities will be developed between the IPPC and RPPOS at the annual TC-RPPO meeting, and presented to CPM-6. |  |
| (v) Adequate Secretariat staff |  |
|  | The Secretary will fully staff current vacant positions within the Secretariat. |  |
|  | Consultants will be contracted to assist with the sustainable implementation of the IPPC. |  |
|  | The Secretary will develop a staffing plan to identify sufficient staff resources to meet the requirements of the CPM Business Plan and build a strong Secretariat team. |  |
|  | Staff training and development. |  |
|  | The Secretary will visit donors to solicit contributions to trust funds to cover long term (<3 years) staff costs identified in the staffing plan. |  |
| Strategic area 5.2: A sustainable financial base established for the IPPC |
| (i) Transparent budgets indicating the real cost of implementing the CPM programme |  |
|  | A consolidated Budget and Operational plan for 2010 will be prepared for CPM-5. This document will combine revenue from all sources and outline planned activities for 2010 which can be used by CPM-6 to measure deliverables. Variations from planned activities will be explained and sources of funding for new activities shown. |  |
|  | The Secretariat will prepare a detailed budget (2011) and present it to the Bureau and SPTA to support the activities undertaken in the annual operational plan for 2011. The budget will include both Regular Programme and trust funds. |  |
| (ii) Develop means to cover the (ongoing) biennial FAO shortfall |  |
|  | Secretary will develop a draft resource mobilization strategy which addresses means to cover the biennial FAO shortfall. |  |
|  | Raise donor awareness by providing assistance in formulating projects, presenting projects to donors for their consideration and coordinate donor awareness meetings |  |
| (iii) Encourage in-kind contributions |  |
|  | Secretariat to liaise with Contracting Parties to secure in kind contributions to deliver work programme. (costs to cover meetings, travel, logistics, translation, editing, stewards, compiling member comments and staff time) |  |
| (iv) Develop, implement and promote a multi year funding strategy |  |
|  | Activity under this item is provided under 5.2(ii) above. |  |
| Strategic area 5.3: IPPC programmes have a strong scientific base |
| (i) Form strong links with appropriate research and education institutions |  |
|  | The Secretariat will provide support for the continued development of a Centre of Phytosanitary Excellence (COPE) for East Africa |  |
|  | Develop and populate an IPP database for contacts and consultants from research and educational institutions (IPP programmer). |  |
| Strategic area 5.4: Developing contracting parties fully participate in all appropriate IPPC activities |
| (i) Secure funding for developing country participation in IPPC activities |  |
|  | The Secretariat, in cooperation with the Bureau, will approach traditional and potential donors to secure funding for assistance for those developing countries to attend CPM and other IPPC meetings. |  |
| *** partly funded by other organizations or through 2009 funds |
| Goal 6: International promotion of the IPPC and cooperation with relevant regional and international organizations |
| Background: The IPPC is an international treaty, which applies (directly or indirectly) to all nations involved with international trade in any commodity that could act as a means of introducing a new pest of plants into an endangered area. |
| Strategic area 6.1: The CPM has global recognition as the worldwide authority in the field of plant health |
| (i) Develop a communication strategy with an integrated public relations plan to achieve global recognition, build and manage the positive image of the CPM and to promote the IPPC |  |
|  | The Secretariat will update the Guide to the IPPC, translate it in FAO languages and publish it |  |
|  | The Secretary and Bureau will finalize a communication strategy in support of the resource mobilization strategy for presentation to SPTA. |  |
|  | A public relations consultant will be hired to develop a communication strategy, promotional plan and associated materials, including consideration of a new logo |  |
| Strategic area 6.2: The IPPC is an active partner in specific programmes of mutual interest |
| (i) Ongoing liaison with specific international and regional organizations to identify and implement areas of common interest (mutual benefit) |  |
|  | Ten relevant meetings will be attended by the IPPC Secretariat or Bureau in order to maintain strong links with international organizations with which the IPPC shares common interests. Travel funding for Secretariat staff and/or Bureau members to attend relevant meetings is required to liaison with organizations such as: - Biological and Toxins Weapons Convention, Convention on Biological Diversity, Global Invasive Species Programme, International Atomic Energy Agency International Civil Aviation Organization International Maritime Organization International Seed Federation International Seed Testing Association Ozone Secretariat / Montreal Protocol International Forest Quarantine Research Group Standards and Trade Development Facility World Trade Organization Sanitary and Phytosanitary Committee (WTO-SPS) Codex alimentarius World Organisation for Animal Health (OIE) |  |
|  | The IPPC Secretariat will provide support to three Regional Workshops on the WTO Agreement on Sanitary and Phytosanitary Measures |  |
|  | Two relevant meetings will be attended by the IPPC Secretariat or Bureau in order to maintain strong links with regional organizations (other than RPPOs) with which it shares common interests (such as the African Sanitary and Phytosanitary Standards Setting Organizations Programme (PAN-SPSO)).. |  |
| Strategic area 6.3: Efficient and effective communication between the RPPOs and the IPPC Secretariat |
| (i) Liaison and collaboration between the Secretariat and RPPO executive staff |  |
|  | The Secretariat will coordinate and fund the first meeting of Near East Plant Protection Organisation (NEPPO). |  |
|  | The TC-RPPOs meeting will be convened and attended by Secretariat staff. |  |
|  | Two meetings of RPPOs will be attended by Secretariat staff. |  |
| Goal 7: Review of the status of plant protection in the world |
| Background: One of the requirements of the CPM is to maintain an overview of the state of plant protection in the world. An important aspect of this is the need to be aware of, and ready to react to, any new or emerging issues and/or incorporate new technologies. |
| Strategic area 7.1: Regular examination of the overall strategic direction and goals of the CPM with the adaptation of programmes to reflect/respond to new and emerging issues |
| (i) Include an agenda item for the CPM meeting identifying new and emerging issues that may need IPPC action |  |
|  | A scientific session will be organized for CPM-5 on “Threats to biosecurity and biodiversity as a result of international trade”, including travel costs for speakers as needed |  |
|  | Topics and speakers for CPM-6 will be discussed by the Bureau and SPTA |  |
| (ii) RPPOs develop discussion documents on new and emerging issues which assist the CPM in determining further action |  |
|  | Secretariat ensures that a discussion paper on new and emerging plant protection issues is developed by the RPPOs for discussion at the TC-RPPOs meeting. |  |
| (iii) Contracting parties that are implementing E-certification assist others, via the Secretariat, to do so |  |
|  | An IPPC strategy for electronic certification will be developed and presented for adoption at CPM-5. |  |
|  | The Secretariat will participate in e-Cert meetings and activities identified in the work programme (CPM-5). |
| (iv) Use of the UN/CEFACT phytosanitary project for standardization |  |
|  | The Secretariat will ensure any IPPC Phyto eCert programme is UN/CEFACT compliant |  |
| (v) Adoption of relevant existing standards covering secure communication and validation of origin |  |
|  | The Secretariat will provide input into the review of existing standards covering secure eCert communication and validation of origin. |  |
| (vi) ISPMs developed/modified to take alien invasive plant species (e.g. aquatic invasive plants) into account |  |
|  | A paper on Invasive Alien Species will be developed by the Secretariat, in cooperation with GISP and CBD. This paper will be presented to the Bureau and SPTA for discussion |  |
| Strategic area 7.2: The IPPC is supported by an implementation programme |
| (i) Prepare recommendations for an implementation programme |  |
|  | The Secretariat will develop an approach for the development of appropriate indicators for the national implementation of ISPMs and submit it to SPTA for discussion. |  |
| (ii) Implement an IPPC Implementation Review and Support System |  |
|  | Implement the first year of the three year work plan (CPM-3) |  |
|  | The “IPPC Help Desk” will be established and become operational |  |
|  | Develop tools to collate information on the implementation of the IPPC and ISPMs |  |

Annex 5

Calendar of meetings for IPPC activities planned for 2010, tentative

The tentative IPPC meeting calendar for 2010 is given below, as well as a list of meetings, organized by the IPPC or with IPPC participation, which are planned according to the operation plan in Annex 4 but not yet scheduled. The calendar and list of meetings is subject to change depending on CPM decisions and budget allocations.

The IPPC Secretariat maintains the IPPC meeting calendar on the International Phytosanitary Portal (IPP - https://www.ippc.int/index.php?id=calendar) and contracting parties are encouraged to visit the site often to check for meeting updates.

Some meetings of other organizations are also listed, when dates were known.

1- Scheduled IPPC meetings for 2010

| Start date | End date | Activity | Type | Location |
| --- | --- | --- | --- | --- |
| 01 Feb | 05 Feb | Importation of Plant Breeding Material | Expert Working Group | Amsterdam, the Netherlands |
| 18 Mar | 19 Mar | CANCELLED: 8th Meeting of the Subsidiary Body on Dispute Settlement (SBDS) 2010 |  | Rome, Italy |
| 18 Mar | 19 Mar | CPM Bureau meeting | CPM | Rome, Italy |
| 22 Mar | 26 Mar | Commission on Phytosanitary Measures - 5th Session | CPM | Rome, Italy |
| 19 Apr | 23 Apr | Capacity building workshop on information exchange and the IPPC website | Workshop | Bogota, Colombia |
| 19 Apr | 24 Apr | Capacity building workshop on information exchange and the IPPC website | Workshop | New Delhi, India |
| 26 Apr | 29 Apr | Capacity building workshop on information exchange and the IPPC website | Workshop | Caracas, Venezuela |
| 26 Apr | 30 Apr | Capacity building workshop on information exchange and the IPPC website | Workshop | Beijing, China |
| 26 Apr | 30 Apr | Standards Committee | Standards Committee | Rome, Italy |
| 03 May | 07 May | Capacity building workshop on information exchange and the IPPC website | Workshop | Jakarta, Indonesia |
| 03 May | 07 May | Standards Committee Working Group (SC-7) | Standards Committee | Rome, Italy |
| 04 May | 07 May | Capacity building workshop on information exchange and the IPPC website for southern Africa | Workshop | South Africa |
| 08 Jun | 11 Jun | CPM Bureau meeting | CPM | Rome, Italy |
| 14 Jun | 18 Jun | Movement of soil and growing media in association with plants in international trade | Expert Working Group | Ottawa, Canada |
| 05 Jul | 09 Jul | Technical Panel on Forest Quarantine | Technical panel | Izmit, Turkey |
| 05 Jul | 08 Jul | Near East - Regional Workshop for the review of draft ISPMs - 2010 | Regional Workshops on draft ISPMs | Cairo, Egypt |
| 19 Jul | 23 Jul | Latin America - Regional Workshop for the review of draft ISPMs - 2010 | Regional Workshops on draft ISPMs | Mexico City, Mexico |
| 19 Jul | 23 Jul | Caribbean - Regional Workshop for the review of draft ISPMs - 2010 | Regional Workshops on draft ISPMs | St. Lucia, West Indies |
| 26 Jul | 30 Jul | Technical Panel on Phytosanitary Treatments | Technical panel | Japan |
| 26 Jul | 30 Jul | Russian speaking countries - Regional workshop for the review of draft ISPMs - 2010 | Regional Workshops on draft ISPMs | Bykovo, Moscow Region, Russian Federation |
| 26 Jul | 30 Jul | Technical Panel on Diagnostic Protocols | Technical panel | United States of America |
| 02 Aug | 06 Aug | Africa - Regional Workshop for the review of draft ISPMs - 2010 | Regional Workshops on draft ISPMs | Kenya |
| 23 Aug | 26 Aug | 22nd Technical Consultation among Regional Plant Protection Organizations | Technical Consultation of RPPOs | Portugal |
| 06 Sep | 10 Sep | Asia - Regional Workshop for the review of draft ISPMs - 2010 | Regional Workshops on draft ISPMs | South Korea |
| 06 Sep | 10 Sep | South West Pacific - Regional Workshop for the review of draft ISPMs - 2010 | Regional Workshops on draft ISPMs | Port Moresby, Papua New Guinea |
| 27 Sep | 01 Oct | Capacity building workshop on information exchange and the IPPC website for southeast Asia | Workshop | Thailand |
| 03 Oct | 07 Oct | Technical Panel on Fruit Flies | Technical panel | Valencia, Spain |
| 04 Oct | 04 Oct | CPM Bureau meeting | CPM | Rome, Italy |
| 05 Oct | 08 Oct | Informal Working Group on Strategic Planning and Technical Assistance (SPTA) |  | Rome, Italy |
| 11 Oct | 15 Oct | Technical Panel for the Glossary | Technical panel | Rome, Italy |
| Nov | Nov | Workshop for Russian speaking countries regarding the implementation of ISPMs | Technical Assistance | Georgia |
| 01 Nov | 05 Nov | Standards Committee | Standards Committee | Rome, Italy |

2- Other meetings organized by the IPPC or with IPPC participation
planned for 2010 but still to be scheduled

Under Goal 2

- 3 additional capacity building workshops on information exchange and the IPPC website

Under Goal 4

- 1 Train the trainers workshop to outline the revisions to the PCE tool

- 5 Project formulation missions to assist developing countries in formulating phytosanitary projects

- 3 National events to field test the revised PCE tool

- 4 National visits to support the East Africa Phytosanitary Information Committee

Under Goal 5

- 3 Meetings of the Steering Committee for the Centre of Phytosanitary Excellence (Nairobi, Kenya)

Under Goal 6

- 1 First meeting of the Near East Plant Protection Organisation (NEPPO)

- 10 relevant meetings for liaison with relevant international organisations, e.g. Codex Alimentarius Commission, World Organisation for Animal Health, International Atomic Energy Association, Biological and Toxin Weapons Convention, Convention on Biodiversity, Global Invasive Species Programme, International Civil Aviation Organization, International Maritime Organization, Ozone Secretariat, International Seed Federation, International Seed Testing Association

- 2 meetings of RPPOs

- 2 non-RPPO meetings of relevant organisations such as the Steering Committee for Participation of African Nations in Sanitary and Phytosanitary Standard-setting Organisations

Under Goal 7

- 1 meeting of the E-certification steering committee

3- Meetings organized by Regional and International Organizations with active participation
by the IPPC Secretariat and/or CPM Bureau

| Start date | End date | Activity | Type | Location |
| --- | --- | --- | --- | --- |
| 17 Mar | 18 Mar | Committee on Sanitary and Phytosanitary Measures | WTO meetings | Geneva, Switzerland |
| 19 Mar | 19 Mar | Working Group on Standards and Trade Development Facility | WTO meetings | Geneva, Switzerland |
| 29 Jun | 30 Jun | Committee on Sanitary and Phytosanitary Measures | WTO meetings | Geneva, Switzerland |
| 29 Jun | 30 Jun | Committee on Sanitary and Phytosanitary Measures | WTO meetings | Geneva, Switzerland |
| 18 Oct | 18 Oct | Workshop - Sanitary and Phytosanitary Measures - Transparency | WTO meetings | Geneva, Switzerland |
| 20 Oct | 21 Oct | Committee on Sanitary and Phytosanitary Measures | WTO meetings | Geneva, Switzerland |
| 22 Oct | 22 Oct | Working Group on Standards and Trade Development Facility | WTO meetings | Geneva, Switzerland |
| Nov | Nov | 3 WTO-SPS Regional Workshops | WTO meetings | TBD |
| 27 Sep | 01 Oct | International Forest Quarantine Research Group | Other working group | Beirut, Lebanon |