TECHNICAL CONSULTATION AMONG REGIONAL PLANT PROTECTION ORGANIZATIONS

22nd Session

Azores, Portugal, 22-26 August 2010.

Update on the IRSS

An Update on the Implementation Review and Support System (IRSS)

Background

1.	At its Third Session, the Commission on Phytosanitary Measures (CPM-3, 2008) adopted the Programme for the Development of the “Implementation Review and Support System” (IRSS) and requested that it be implemented as soon as practically possible and as resources allowed. The Programme for the Development of the IRSS envisions a three-year operational trial timeline.

Current Activities

2.	A number of aspects of the IRSS are already functional as part of the regular CPM work programme. These include information gleaned from the International Phytosanitary Portal (IPP), the Technical Consultation among RPPOs (TC-RPPOs), the report on the use of the Phytosanitary Capacity Evaluation (PCE) tool and reports from other relevant organizations, to produce the Implementation review response.

Future

3.	The core activities under the IRSS are new, namely the establishment of an “IPPC Help Desk” and the development, distribution and analysis of a questionnaire on the implementation of the Convention by the Contracting Parties. The “IPPC Help Desk” would deal with:

- countries requesting assistance on the implementation of ISPMs;

- provision of advice relating to ISPMs (with assistance of the Subsidiary Body on Dispute Settlement);

- monitoring, identification and reporting of compliance and implementation issues; and

- ensuring contracting parties requesting assistance are put in contact with potential funding sources.

4.	IRSS programme started in 2010 with the recruitment of a project staff member whose role will include the establishment of the “IPPC Help Desk”.

- The IPPC Secretariat does not currently have funding to continue providing staff for this post past 31 December 2010, but has been negotiating with the EU to get expanded support to the IRSS, with the expectation to begin the implementationplan before the end of 2010.

- For information, Table 1 in annex , is the anticipated work programme as adopted by CPM-3.

- A theoretical first year implementation plan can be found in Annex 1.

Table 1:	A three year work plan with proposed milestones and dates

| Proposed dates | Actions | Component |
| --- | --- | --- |
| Year 1 |
| April | IPPC Secretariat annual report to the CPM on: contracting parties' difficulties with reporting requirements based on reporting through the IPP; and the IPPC Help Desk activities. | Implementation Review System (first element) |
| May | IPPC Secretariat informing contracting parties again of their reporting requirements (first time in 2008) | IRS (first element) |
| June | Appointment of the Standards Implementation Officer | Implementation Support System (ISS) |
| August | Development of a questionnaire by the Secretariat to gather information from contracting parties regarding implementation of other (non-reporting) IPPC obligations, in particular in relation to Articles IV, V, VII, and VIII | IRS (second element) |
| September | Review of the questionnaire by the Bureau and other experts | IRS (second element) |
| September | Initiation of IPPC Help Desk | ISS |
| October | Distribution of pilot questionnaire | IRS (second element) |
| November | Review of the questionnaire by the Bureau and other experts | IRS (second element) |
| December | Evaluation (plus comments) by limited number of contracting parties followed by second review by the Bureau and other experts | IRS (second element) |
| Year 2 |
| March | Distribution of questionnaire to contracting parties | IRS (second element) |
| March | Collation and analysis of data for the IPPC Secretariat report. | IRS (first element) |
| April | IPPC Secretariat annual report to the CPM on: contracting parties' difficulties with reporting requirements based on reporting through the IPP; and the IPPC Help Desk activities. | IRS (first element) |
| April | Establishment of a triennial review group | IRS (second element) |
| May | Analysis of questionnaire replies and suggestions for improvement of the questionnaire by a meeting of the triennial review group | IRS (second element) |
| June | Reports on implementation by the TC-RPPOs and other relevant international organizations | Implementation Review Response (IRR) |
| Reports received by Secretariat June Prepared by CPM Bureau July-August | Report prepared • based on the following elements: - the report of the triennial review - a summary report of the IPPC Help Desk - a report on implementation difficulties from the TC-RPPOs - a summary report on implementation trends from the PCE - reports from other relevant international organizations • and containing action plans. | IRR |
| October | Review by the SPTA | IRR and IRS |
| November | Prepare paper (IRR response) for the CPM | IRR |
| Year 3 |
| March | Collation and analysis of data for the IPPC Secretariat report. | IRS (first element) |
| April | Present report of the triennial review (first time at CPM-5 in 2010) | IRS (second element) |
| April | IPPC Secretariat annual report to the CPM on: contracting parties' difficulties with reporting requirements based on reporting through the IPP; and the IPPC Help Desk activities. | IRS (first element) |
| April | Report of the IRR considered by CPM | IRR |

Annex 1

| 2010 |
| --- |
| Timeline | Principal activities |
| July | IPPC Secretariat informing contracting parties again of their reporting requirements. |
| July – August | Development of a questionnaire by the Secretariat to gather information from contracting parties regarding implementation of other (non-reporting) IPPC obligations, in particular in relation to Articles IV, V, VII, and VIII. |
| July – November | Planning for the implementation of the Help Desk. |
| September | Review of the questionnaire by the SPTA, SBDS and other experts. |
| October - November | Review of the questionnaire by the SPTA. |
| October | Distribution of pilot questionnaire. |
| December | IPPC Secretariat annual report to the CPM on: contracting parties’ difficulties with reporting requirements based on reporting through the IPP. |
| November – December | Pilot IPPC Help Desk. |
| 2011 |
| Timeline | Principal activities |
| January – February | Evaluation (plus comments) by limited number of contracting parties followed by second review by the Bureau and other experts. |
| February | IPPC Secretariat informing contracting parties again of their reporting requirements. |
| January – May | Help Desk more widely tested and launched. |
| June | Bureau mid-year review of the IPPC Help Desk activities. |